## Quality Information
Document Change Log This section is used to track content changes to the project's Basis of Estimate (BoE). As the BoE is updated at regular intervals, this section should only identify the date of any updates and only significant updates. If there is a need to determine the detailed changed variances, the previous saved verson of the BoE can be used for comparison.
Document Revision No. | Change in Content | Date Released | Released By
Template Quality Information (This section is used to track changes to the BoE template design)
Document Revision No. | Revisions | Date Released | Released By
V1.0 | Released for use | 2016-02-22 | Ron Amann
V1.1 | Updated formula E41-J41, minor wording change to instructions | 2016-02-26 | Krista Molinski
V1.2 | Updated BOE Cost Detail and EX_BOE Cost Detail, row 70 adjusted formula to calculate in thousands. | 2016-03-02 | Krista Molinski
V1.3 | Added extra rows in Overheads for customization, warning for future year estimate year, cleaned up yearly headings and formulae, aligned Overhead/Admin cost wording with FM004 | 2016-03-18 | Krista Molinski
V1.4 | Added extra column to allow for 6 years of estimates | 2016-04-14 | Krista Molinski
V1.5 | Row 70 formula incorrect, amended Cover Sheet to include details from Summary page | 2016-04-25 | Krista Molinski
V1.6 | Changed formula in row 70 to hard code the Corporate Admin rate | 2016-05-03 | Krista Molinski

## Template Instructions
Basis of Estimate (BoE) Template Instructions
This template identifies the key elements that formulate the Cost Estimate for an investment. The Basis of Estimate (BoE) is the foundation for the "Ask" number in the Business Case (BC). The BoE is a companion-document of an Investment's BC. Although the BC and the BoE may be updated multiple times (and at different times) as an investment matures along the project life-cycle, the BoE and BC need to be tightly integrated and aligned at specific milestones - such as when the investment is submitted with the Departmental Investment Plan as part of the budget submission. The objective is to have a standardized template across the City that identifies the entire cost of an investment. The intended result is that all stakeholder's will know what to expect when they ask for the BoE Template.
** An Example BoE is included. The BOE Template contains five Example tabs (noted with an "EX" in the title) that outlines an example of how the BoE could look for a generic project. The intent of the Example is to provide a simple view of how the data is applied within the template. The data is not from an actual project; rather, the intent is to illustrate the concepts and how the template can be used. The data is not reflective of a real project.
The BoE is intended to be a stand-alone document that can be shared with project stakeholder's so that everyone understands the key elements that make up the cost of an investment.
There are four parts to the BoE Template: 1) BoE Cover Sheet Tab This tab is used as the cover page for when sharing the BoE in hardcopy format.
2) BoE Summary Tab Identifies information that supports the financial dollars in the "BoE Cost Detail" tab. Specific information from this tab can be copied directly into or from the Business Case.
3) BoE Cost Detail Tab Itemized costs to perform all activities to deliver the investment. The concept is to identify costs at the level of detail necessary based on industry sector and project life-cycle status. These costs are then spread out over the length of the project in order to apply inflationary interest costs. ** It is important that specific cost groups and cost items not be deleted or left blank but inserted as $0 if the items are not applicable. The intent is that a BoE reviewer can see that the BoE author had considered these cost items but that they are not applicable. Rationale: If the cost items were deleted (entire line), the reviewer would not be able to determine if the author considered them.
4) Estimate Classification Tab This sheet helps the BoE author to rationalize the Class of Estimate by identifying key elements that define a specific Class of Estimate per AACE.
5) Example Tabs There are four worksheets that are examples of how the BoE is filled out. These sheets are indicated by the four "EX_" tabs. An explanation of these tabs are detailed in the below instructions.
Follow the instructions below for each of the BoE Summary field descriptions to complete the BoE Template.
BoE Summary Tab
Investment | The Investment Name exactly as on the Business Case.
Date | The date on which the BoE was first approved, or the date of each subsequent approved update/revision.
BoE Author | Name of the individual responsible for preparing the information in the BoE Template.
BoE Reviewer(s) | Name of the individual(s) who reviewed the BoE.
BoE Approved by | Name of the individual who approved the BoE. This should be (but not always) the same individual who approved the BC.
Department | Full name of the responsible Department.
BC ID | The Departmental Business Case ID.
Project Scope Description | Provide a narrative that describes the Project's scope. This needs to include scope, cost and time elements that are associated with this investment.
Estimate Classification | This is derived from the CoW Estimate Classification table per the Estimate Classification tab (based on AACE Standards). Select the Class from the drop-down menu.
Key Scope Elements or Requirements | List or reference (in an attached document) the key deliverables and/or requirements that the Business Owner has agreed to.
Assumptions | Identify and list key assumptions made in developing the estimate. Identify only KEY assumptions. If listed elsewhere, make reference to the document (such as the Business Case (BC) or Project Delivery Plan (PDP).
Out of Scope | Identify and reference the specific items or activities that are NOT part of the project scope or included in the estimate.
Risks and Opportunities | List or reference the detailed Risk Assessment that identifies the key risks and opportunities.
Contingencies | Identify key Contingencies associated with each Risk Event. Refer to a detailed Risk Assessment where specific Contingency dollars have been assigned to a Risk Event.
Operating Impact | Identify any impact to operations. This includes not only financial impacts but also resource impacts if operations participation on the Project is critical.
Estimating Team | Identify and list the individual(s) who have contributed to the development of the BoE.
Reference Documents | List reference material used in the development of the BoE such as the Preliminary Design Report. This section will be used to support your Class of Estimate.
Major Changes from Previous Estimate | Identify items that changed from the previous version of the BoE. The Estimator must use discretion as to how much detail to include; a suggestion would be to note only the items that have substantially changed the estimate. Note: Be sure to indicate any changes into the Change Log under the Quality Information tab.
General Comments | Provide any comments that are not identified above.
BoE Cost Detail Tab
Key Elements of the Cost Detail sheet: 1) Entering Data: Data should be entered only in the areas that are shaded in YELLOW. To allow flexibility the spreadsheet is not locked, therefore, all cells can be edited - however, exercise extreme caution to not delete or break any of the formulas that are linked.
2) "Estimate Detail" groupings: The objective of this tab is to capture all the costs associated with the investment. The Estimator has the flexibility to identify the cost elements within each "Estimate Detail" grouping. That is, within the Construction Cost group, the Estimator can identify any number of cost items that are appropriate for their specific investment.
3) Entering Costs: Enter the cost for the specific cost items in the "Estimate Year" column. Then enter what "%" of work that will be completed in a specific year and the inflation rate for that year(starting with column "L"). Note: for most projects, 100% of the work will be completed in the first two years. NOTE: the years do not need to be sequential and the inflation rate does not need to be the same for each year. Enter data that is appropriate for the type of investment and industry that is associated with the BoE.
4) Charges: The charges at the bottom of the template are generated automatically. The Overhead, Administrative and Interim financing charges are costs that are applicable to most, if not all, of the project. Contact your Departmental PMO to determine if your project is not applicable.
5) Operating Impact: Enter any operational charges associated with the capital investment.
Investment Title | Transferred from the BoE Summary tab.
Date | Transferred from the BoE Summary tab.
Class of Estimate | Transferred from the BoE Summary tab.
Cost Escalation / Construction Inflation | This is the Construction Inflation Rate for the industry sector that the estimate-work is associated. Contact your Departmental AMO for additional support in determining the rate.
Estimate Year | This is the year in which the cost estimates have been based. A warning note is in place if the estimate year entered is greater than current year to notify the Estimator. The Estimator can determine if future estimate year was intended. If intended and accurate, delete the formula in the message cell.
Estimate Detail | Include the cost items based on Industry Sector and the Class of Estimate. Group the cost items based on logical groupings for the industry sector (i.e. Construction and Engineering may not be applicable to the IT industry sector. If no costs are associated with the following cost groups or their respective detailed line item, HOWEVER for the items below, do not delete or leave blank, but insert $0 : - Utility costs - Others Costs
Contingency Costs | Note the specific contingency allotment for each risk. This grouping cannot be deleted but the Estimator has flexibility to note the specific risk line items. The contingency line items should be generated form the Risk Management Plan template found on City net on the Infrastructure Planning site: http://citynet/finance/infrastructure/ The specific Contingency line items need to be determined based on the risk assessment results, industry type and Class of Estimate.
Overhead and Administrative Charges | Refer to FM-004, Asset Management Administrative Standard (Appendix J). These charges are automatically generated but there are some modifications that the Estimator needs to be aware of: If is it 3rd party funding: Include the cost of any funds that will be provided. If you are not aware of any, leave it blank. Overhead & Admin: The % noted are typically standard but may change over time. Adjust as necessary. Research (SMIR) is applicable only to Public Works and construction cost items. * Note to Estimator: Check Formula to ensure construction costs are included Blank rows have been added for Estimator to add any additional charges or fees. These rows do not have formulas so if Estimator adds a charge or fee, the Estimator must enter applicable formulas to that row.
Financing Charges | Delete formulas if no funds are borrowed for the investment. The borrowing rate is obtained from Corporate Finance. Concept: The interim financing charges are similar to what an individual would incur if they built a house and needed to utilize a personal Line of Credit to pay project costs due to cash flow reasons.
Operating Budget Impact | For most projects, just enter any cost associated with "Salaries and Benefits", "Materials, Parts and Supplies" or "Other". This section should be completed in consultation with the Portfolio Financial Analyst.
Estimate Classification Tab
The purpose of this tab is provide guidance to the Estimator in how to assess the Cost Classification. Assess the estimate against each of the guideline criteria, and based on how complete or defined the estimate is the Class of Estimate can be determined. This is not an exact science as the Estimator's judgment needs to be applied.
Purpose: To assist Business Case (BC) authors in determining the Cost Classification of their estimate based on an independent analysis (based on AACE Recommended Practice 56R-08).
General Instructions Follow the five steps below. The objective is to highlight the appropriate cell based on the estimate status so that by visually checking the tables, a determination is made as to the Class of Estimate. The process provides the supporting rational for the Estimator to defend the Class of Estimate decision.
Step 1 - Table 1: Determine the Classification for each of the Four Primary Classification Characteristics For each of the four Classification Descriptors in Table 1, identify which Class most accurately defines its current estimate status. To highlight the appropriate Classification Descriptor: 1) Click on the desired cell. 2) In the Home tab, click the Format Painter icon. 3) Move the cursor to the characteristic in the table you wish to choose. 4) Click the Format Painter icon to apply the green highlight to that cell. 5) Repeat the above steps until all selections are made. To un-highlight a Classification Descriptor: 1) Click on the desired highlighted cell. 2) Click the Fill Icon and select "No Fill".
Step 2 - Table 2: Determine the Status of each Deliverable In Table 2, determine the status that best supports the primary Classifications in Table 1. 1) Highlight the appropriate cell for each deliverable item. 2) If the deliverable is not relevant to the estimate, leave the default "n/a" ; otherwise, from the drop-down list select the "blank" option. This serves as a Quality Assurance step.
Step 3 - Add Comments If necessary, add relevant details in the Comments columns that support the characteristic selected.
Step 4 - Determine the Overall Class When each deliverable item has been analyzed and classified, the highlighted selections will help to visually determine the Class in which the Cost Classification is currently at. 1) Select the appropriate Class from the Overall cell's drop-down menu.
Example Premise Tab
The purpose of these four "EX_" tabs is to provide an example of how to use the BoE template. This tab provides an overall premise for the example used to developed this Example BoE. The example is not real and the information and data is to illustrate the concepts and not that of a real project.
Example BoE Summary Tab
The information in the Example BoE Summary shows the type of information that should be included in the Summary. The level of detail will be based on maturity of the investment along the project life-cycle and what details can be referenced vs. included in the Summary.
Example BoE Detail Tab
The information shows how cost information is entered into the sheet. Note: the Years in which work occurs are not sequential, and the Inflation Rate is not the same.
Example Estimate Classification Tab
This tab shows how the Example BoE was classified. Note: As an example, some assumptions were made in the Rationale section.
Example Risk Assessment Tab
The Risk Assessment was copied from the Risk Management Plan Template (check the Infrastructure Planning area on CityNet for the template) that was developed for this example. The Risk Assessment should not be copied into the BoE Template and used as an actual BoE but should be referred to in the Reference Documents (Summary Tab).

## BoE Cover Sheet
Asset Management –
Basis of Estimate (BoE)
0
Prepared by: | 0
0
Department: | 0

## BOE Summary
BoE Summary
Investment Title
Date
BoE Author
BoE Reviewer(s)
BoE Approved by
Department
Business Case ID
Project Scope Description
Estimate Classification
Key Scope Elements or Requirements
Assumptions
Out of Scope
Risks and Opportunities
Contingencies
Operating Budget Impact
Estimating Team
Reference Documents
Major Changes from Previous Estimate
General Comments

## BOE Cost Detail
Basis of Estimate Cost Detail
| Investment | 0
|  | FALSE | [5 empty] | Estimate Date |  | 0
| Class of Estimate |  |  | 0
Cost Escalation / Construction Inflation
| ($ thousands) |  | Estimate Year | Year Project Work Undertaken | [7 empty] | % of Project Work Undertaken | [5 empty] | Check
| Estimate Detail | % of Const. | [7 empty] | Total |  | 0 | 0 | 0 | 0 | 0 | 0 | Total %
Construction Costs
|  | - |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 100% |  |  | 100%
|  | - |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0%
|  | - |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0%
|  | - |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0%
|  | - |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0%
|  | - |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0%
|  | - |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0%
| Sub-total | - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Engineering Costs |  | % of Const
|  | - |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0%
|  | - |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0%
|  | - |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0%
|  | - |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0%
| Sub-total | - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Construction & Engineering Sub-total |  | 0
Utility Costs |  | % C&E
| Hydro | - |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0%
| Communication - MTS | - |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0%
| Communication - Shaw | - |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0%
|  | - |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0%
| Sub-total | - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Other Costs |  | % C&E
| Land Acquisition | - |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0%
|  | - |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0%
|  | - |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0%
|  | - |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0%
|  | - |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0%
| Sub-total | - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Project Costs before Contingencies Sub-total |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Contingencies Costs |  | % Proj Cost
|  | - |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0%
|  | - |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0%
|  | - |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0%
|  | - |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0%
|  | - |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | % Proj Cost | [6 empty] | 0%
| Sub-total | - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -
% increase from base
| Project Sub-total before Charges |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -
Summary of Interest and Admin Overhead Charges
| Overhead / Admin Charges | - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Corporate Interest | 2% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
% increase over base
Total Project Cost |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -
Administrative Overhead Charges Detail
Total
| Total Project Costs |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 3rd Party Share of Project Costs |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0%
| City's Share of Project Costs |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Overhead & Administrative Charges
| Departmental | 2% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Corporate Admin (max $100,000) | 1.25% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Research (SMIR) (Const only) | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Overhead & Admin Charges Sub-total | - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -
Financing Charges
| Corporate Interest | 2% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Operating Budget Impact Detail
|  |  | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9
Salaries and Benefits
Materials, Parts and Supplies
Other
| Total Operating Impact |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Note on E6: Amann, Ron: Indicate the Escalation % per year starting from the Estimate Year. Typically, it is the same for each but can change based on the investment. The Escalation Rate in future years will be reflected in the costs of each line item based on the year that the work occurs.
Note on D7: Molinski, Krista: Year in which costs are based.
Note on E8: Amann, Ron: Enter the year that the work will occur. The years do not need to be sequential. That is, work does not need to start the first year after the Estimate Year and work does not have to occur for 1 or more years.
Note on A45: Amann, Ron: The categories below are provided as examples and should be defined by the estimator as part of the Risk Management process.
Note on A55: Molinski, Krista: See Appendix J of FM-004
Note on B71: Amann, Ron: Applies to Public Works only.
Note on B72: Molinski, Krista: Rows added for Estimator to customize additional fees or charges. Estimator needs to add formulas to columns D - J
Note on B80: Amann, Ron: Based on current year project costs. (Similar to paying L/C interest only).

## Estimate Classification
Class of Estimate
| Investment | 0 |  |  | Date | 0
| Description |  |  |  | BC ID | 0
Legend
| Blank | Development of the deliverable has not begun. |  |  | C | Deliverable has been reviewed and approved as appropriate.
| S | Rough work on the deliverable has begun. |  |  | n/a | Not applicable. The deliverable does not apply to the project.
| P | Work on the deliverable is advanced and may be complete, excepting final review and approvals. |  |  |  | BoE Author's Determination (highlighted selection)
Table 1 - Classification of Estimate Analysis
| Characteristic | Weighting | Class 1 | Class 2 | Class 3 | Class 4 | Class 5 | Comments
1 | Project Definition | Primary | 65% to 100% | 30% to 75% | 10% to 40% | 1% to 15% | 0% to 2%
2 | End Usage | Secondary | Tender Check | Semi-Tender | Budget | Study | Screening
3 | Methodology | Secondary | Detailed Unit Cost with Detailed Take-off Cost | Detailed Unit Costs with Forced Detailed Take-off Cost | Semi-detailed Unit Cost with Assembly Level Line Items | Parametric Models, Assembly-Driven Models | SF (sq.ft.) Factoring, Parametric Modeling, Judgment, Analogy
4 | Expected Accuracy (from Appendix 2 - Cap Bug) | Secondary | High: +3% to +10% Low: -3% to -5% | High: +10% to +20% Low: -5% to -10% | High: +20% to +30% Low: -10% to -20% | High: +30% to +60% Low: -20% to -30% | High: +60% to +100% Low: -30% to -50%
Table 2 - Supporting Class of Estimate Rationale
The following table is used to provide the supporting rationale for selecting the above characteristics.
General Project Data
1 | General Scope Description |  | Defined | Defined | Defined | Preliminary | Assumed | n/a
2 | Project Location |  | Specific | Specific | Specific | Approximate | General | n/a
3 | Functional Space Req (m2) |  | Specific | Specific | Defined | Preliminary | Started | n/a
4 | Standards Requirements |  | Defined | Defined | Defined | Preliminary | Assumed | n/a
5 | Total Capacity |  | Defined | Defined | Defined | Defined | Preliminary | n/a
6 | Electrical Capacity |  | Defined | Defined | Defined | Defined | Preliminary | n/a
7 | Soils / Hydrology Report |  | Defined | Defined | Defined | Preliminary | None | n/a
8 | Integrated Project Plan |  | Defined | Defined | Defined | Preliminary | None | n/a
9 | Project Master Schedule |  | Defined | Defined | Defined | Defined | Approximate | n/a
10 | Work Breakdown Structure |  | Defined | Defined | Defined | Defined | Preliminary | n/a
11 | Project Code of Accounts |  | Defined | Defined | Defined | Defined | Preliminary | n/a
12 | Contracting Strategy |  | Defined | Defined | Defined | Preliminary | Assumed | n/a
13 | Escalation Strategy / Basis |  | Defined | Defined | Defined | Preliminary | Assumed | n/a
Design Deliverables
14 | Standards Drawings |  | C | C | C | S/P |  | n/a
15 | Site Plan |  | C | C | C | S/P | S | n/a
16 | Existing Site Plan |  | C | C | C | S/P | S | n/a
21 | Demolition Plan and Drawings |  | C | C | P | S/P |  | n/a
22 | Utility Plan and Drawing |  | C | C | P | S/P |  | n/a
23 | Site Electrical Plan / Drawing |  | C | C | P | S/P |  | n/a
24 | Site Lighting Plan / Drawing |  | C | C | P | S/P |  | n/a
25 | Site Comm Plan / Drawing |  | C | C | P | S/P |  | n/a
26 | Erosion Control Plan / Drawing |  | C | C | P | S/P |  | n/a
27 | Stormwater Plan / Drawing |  | C | C | P | S/P |  | n/a
28 | Landscaping Plan / Drawing |  | C | C | P | S/P |  | n/a
29 | External Elevations (Structure) |  | C | C | P | S/P |  | n/a
30 | Interior Elevations (Structure) |  | C | P | S |  |  | n/a
31 | Interior Section Views |  | C | C | P | S/P |  | n/a
32 | Partition or Wall Types |  | C | C | S/P | S/P |  | n/a
33 | Finish Schedule |  | C | C | P | S/P |  | n/a
34 | Door Schedules |  | C | P | P | S/P |  | n/a
35 | Window Schedules |  | C | P | P | S/P |  | n/a
36 | Restroom Schedules |  | C | P | P | S/P |  | n/a
37 | Furniture Plans / Schedules / Drawings |  | C | C | P | S/P |  | n/a
38 | Signage Drawings / Schedules |  | C | P | P | S/P |  | n/a
39 | Fire Protection Plan / Drawings |  | C | C | P | S/P |  | n/a
40 | Room Layout Plan / Drawings |  | C | C | P | S/P |  | n/a
41 | Foundation Plan / Drawings |  | C | C | P | S/P |  | n/a
42 | Foundation Section / Details |  | C | C | P | S/P |  | n/a
43 | Structural Plan / Drawings |  | C | C | P | S/P |  | n/a
44 | Structural Section / Details |  | C | C | P | S/P |  | n/a
45 | Roof Plan Drawings / Details |  | C | C | P | S/P |  | n/a
46 | Material / Equipment Specs |  | C | C | P | S/P |  | n/a
47 | Building Envelope / Moisture Protection / Flashing Details |  | C | C | P | S/P |  | n/a
48 | Mechanical / HVAC Plan / Drawings |  | C | C | P | S/P |  | n/a
49 | Mechanical / HVAC Details |  | C | P | S/P |  |  | n/a
50 | Mechanical / HVAC Schedules |  | C | P | S/P |  |  | n/a
51 | Flow Control Designs |  | C | P | P | S/P |  | n/a
52 | Plumbing Plan / Drawings |  | C | C | P | S/P |  | n/a
53 | Plumbing Details |  | C | P | S/P |  |  | n/a
54 | Plumbing Riser Diagram |  | C | P | S/P |  |  | n/a
55 | One-Line Electrical Diagram |  | C | C | P | S/P |  | n/a
56 | Electrical Power Plan |  | C | C | P | S/P |  | n/a
57 | Interior Lighting Plan / Drawings |  | C | P | S/P |  |  | n/a
58 | Security Plan / Drawings |  | C | P | S/P |  |  | n/a
59 | Emergency Communication Plan / Drawings |  | C | P | S/P |  |  | n/a
60 | Life Safety Plan / Drawings |  | C | C | S/P | S |  | n/a
61 | Lightning Protection Plan |  | C | P | S/P |  |  | n/a
62 | Motor Control Diagram |  | C | P | S/P |  |  | n/a
63 | Lighting Control Drawings |  | C | P | S/P |  |  | n/a
64 | Lighting Schedules |  | C | P | S/P |  |  | n/a
65 | Electrical / Panel Drawings |  | C | P | S/P |  |  | n/a
66 | Equipment Schedule |  | C | P | S/P | S |  | n/a
67 | Info Systems / Telecom Plan |  | C | P | S/P |  |  | n/a
68 | Info Systems / Telecom Details |  | C | P | S/P |  |  | n/a
[7 empty] | Overall |  | Class 3

## EX_Premise
Example Premise
| Premise | An investment to construct a railway overpass. The investment is in the Planning Phase and is currently a Class 3 Estimate.
| Cost Items | Cost items are noted such as Engineering and Construction. The PM also determined there were Utility Costs associated with this investment.
| Costing and Cash Flow | The staging of the project is also noted in the BoE Cost Tab, starting in column "L".
| Contingencies | The Contingencies were determined as per the risk assessment completed in the Risk Management Plan (RMP) Template which has been embedded in the tab called "RMP".
| 3rd Party Funding | There is 3rd party funding from the Province.

## EX_BOE Summary
BoE Summary (Example)
Investment | Cho-Cho Bridge
Estimate Date | 2016-01-01
Prepared By | Mr. Base Of Estimate (BOE)
BoE Reviewer(s) | Tim Highway Jim Bridge
BoE Approved by | Dan Austin
Department | Public Works
Business Case ID | BC_PW_CHO CHO Overpass _2017_001 V2.0
Project Scope Description | To Design and Construct a Railway Bridge at Over Street. The bridge needs to accommodate 15000 vpd and not impact railway operation during construction. The bridge will include all necessary land purchases and engage the Public, as necessary, through the entire design - construction life-cycle. The project needs to completed by Fall of 2021.
Estimate Classification | 3
Key Scope Elements or Requirements | The Key Scope Element for the final 2 phases are: Detailed Design and Construction Commissioning and Transfer
Assumptions | Land can be purchased without expropriation. Council will approve this budget authorization request by Fall 2018.
Out of Scope | Insurance is to address any risk associated with railway traffic during construction. Corporate Risk to address this event via City's insurance.
Risks and Opportunities | Risks are identified in the Project's RMP.
Contingencies | As noted in the BoE Cost Detail Sheet.
Operating Budget Impact | There is an Operating Budget Impact as noted in the BoE Cost Detail Sheet. Additional Maintenance Supervisers are required to manage the complex bridge development.
Estimating Team | Mr. Bob Olive Einstein
Reference Documents | Initial BC (V1.0) Service Level Report (Performance Gap) Facility Risk Assessment Service Strategic Plan - Facilities Section Purchase Land Assessment Report Requirement Definition Report Stakeholder Engagement & Communication Plan Feasibility Analyst & Preliminary Design
Major Changes from Previous Estimate | BoE now incorporates the deliverables from the Preliminary Design Report and is now a Class 3 Estimate.
General Comments

## EX_BOE Cost Detail
Basis of Estimate Cost Detail (Example)
| Investment | Cho-Cho Bridge
|  | FALSE |  |  |  |  | Estimate Date |  | 2016-01-01
| Class of Estimate |  |  | 3
|  |  | Cost Escalation / Construction Inflation | 5% | 8% | 8% | 7% | 8%
| ($ thousands) |  | Estimate Year | Year Project Work Undertaken | [6 empty] | % of Project Work Undertaken |  |  |  |  | Check
| Estimate Detail | % of Const. | 2016 | 2017 | 2019 | 2020 | 2022 | 2023 | Total |  | 2017 | 2019 | 2020 | 2022 | 2023 | Total %
Construction Costs
| Water & Sewer | 2.833% | 5000 | 2625 | 3150 | 0 | 0 | 0 | 5775 |  | 50% | 50% |  |  |  | 100%
| Roadway | 1.416% | 2500 | 0 | 0 | 851 | 938 | 2143 | 3932 |  |  |  | 25% | 25% | 50% | 100%
| Bridge | 84.99% | 150000 | 0 | 0 | 51019 | 112555 | 64269 | 227843 |  |  |  | 25% | 50% | 25% | 100%
| Railway Realignment | 5.666% | 10000 | 0 | 0 | 3402 | 0 | 12854 | 16256 |  |  |  | 25% |  | 75% | 100%
| Active Transportation | 0.8499% | 1500 | 0 | 0 | 0 | 0 | 2571 | 2571 | [5 empty] | 100% | 100%
| Sound Attenuation | 4.249% | 7500 | 0 | 0 | 0 | 2814 | 9641 | 12455 |  |  |  |  | 25% | 75% | 100%
|  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0%
| Sub-total | 100% | 176500 | 2625 | 3150 | 55272 | 116307 | 91478 | 268832
Engineering Costs |  | % of Const
| Geotechnical Engineering | 0.1416% | 250 | 263 | 0 | 0 | 0 | 0 | 263 |  | 100% |  |  |  |  | 100%
| Detailed Design (Bridge and Roadway) | 5.666% | 10000 | 2625 | 6299 | 3402 | 0 | 0 | 12326 |  | 25% | 50% | 25% |  |  | 100%
| Detailed Design (W&S) | 0.4249% | 750 | 394 | 473 | 0 | 0 | 0 | 867 |  | 50% | 50% |  |  |  | 100%
| Railway Design | 0.1416% | 250 | 0 | 315 | 0 | 0 | 0 | 315 |  |  | 100% |  |  |  | 100%
| Sub-total | 6.374% | 11250 | 3282 | 7087 | 3402 | 0 | 0 | 13771
| Construction & Engineering Sub-total |  | 187750
Utility Costs |  | % C&E
| Hydro | 0.7989% | 1500 | 0 | 945 | 1021 | 0 | 0 | 1966 |  |  | 50% | 50% |  |  | 100%
| Communication - MTS | 0.3995% | 750 | 0 | 473 | 511 | 0 | 0 | 984 |  |  | 50% | 50% |  |  | 100%
| Communication - Shaw | 0.05326% | 100 | 0 | 63 | 69 | 0 | 0 | 132 |  |  | 50% | 50% |  |  | 100%
|  | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0%
| Sub-total | 1.252% | 2350 | 0 | 1481 | 1601 | 0 | 0 | 3082
Other Costs |  | % C&E
| Land Acquisition | 5.326% | 10000 | 2625 | 9448 | 0 | 0 | 0 | 12073 |  | 25% | 75% |  |  |  | 100%
| Legal | 0.2663% | 500 | 0 | 315 | 0 | 188 | 215 | 718 |  |  | 50% |  | 25% | 25% | 100%
| IS / IT | 0.05326% | 100 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0%
| Field Office | 0.05326% | 100 | 0 | 32 | 35 | 38 | 43 | 148 |  |  | 25% | 25% | 25% | 25% | 100%
| Security | 0.1065% | 200 | 0 | 63 | 69 | 76 | 86 | 294 |  |  | 25% | 25% | 25% | 25% | 100%
| Sub-total | 5.806% | 10900 | 2625 | 9858 | 104 | 302 | 344 | 13233
| Project Costs before Contingencies Sub-total |  | 201000 | 8532 | 21576 | 60379 | 116609 | 91822 | 298918
Contingencies Costs |  | % Proj Cost
| Geotechincial Issue (Groundwater) | 0.2488% | 500 | 0 | 630 | 0 | 0 | 0 | 630 |  |  | 100% |  |  |  | 100%
| Design Costs due to RR Requirements | 0.2488% | 500 | 263 | 315 | 0 | 0 | 0 | 578 |  | 50% | 50% |  |  |  | 100%
| Construction Delays (due to land purchases) | 2.488% | 5000 | 5250 | 0 | 0 | 0 | 0 | 5250 |  | 100% |  |  |  |  | 100%
| Higher-than-Estimated Land Costs | 2.488% | 5000 | 5250 | 0 | 0 | 0 | 0 | 5250 |  | 100% |  |  |  |  | 100%
| Design Escalation (Design Evolution) - Known - Unknown | 0.5597% | 1125 | 591 | 709 | 0 | 0 | 0 | 1300 |  | 50% | 50% |  |  |  | 100%
| Construction Cost Increase - Known - Unknowns | 8.781% | 17650 | 0 | 4447 | 12007 | 7947 | 0 | 24401 |  |  | 20% | 50% | 30% |  | 100%
| Unknown - Unknowns | 5% | 10050 | 2639 | 3166 | 3419 | 3771 | 0 | 12995 | % Proj Cost | 25% | 25% | 25% | 25% |  | 100%
| Sub-total | 19.81% | 39825 | 13993 | 9267 | 15426 | 11718 | 0 | 50404 | 16.86%
% increase from base
Project Sub-total before Charges |  |  | 240825 | 22525 | 30843 | 75805 | 128327 | 91822 | 349322 | 145.1%
Summary of Interest and Admin Overhead Charges
| Overhead / Admin Charges | 2.422% | 5710.8 | 563.7 | 640.1 | 1775.5 | 3123.2 | 2243.9 | 8346.4
| Corporate Interest | 2% | 4716.5 | 450.5 | 616.9 | 1491.1 | 2541.6 | 1786.5 | 6886.6
% increase over base
Total Project Cost |  |  | 251252.3 | 23539.2 | 32100 | 79071.6 | 133991.8 | 95852.4 | 364555 | 145.1%
Overhead and Admin Charges Detail
Total
| Total Project Costs |  | 240825 | 22525 | 30843 | 75805 | 128327 | 91822 | 349322
| 3rd Party Share of Project Costs |  | 5000 | 0 | 0 | 1250 | 1250 | 2500 | 5000 |  |  |  | 25% | 25% | 50% | 100%
| City's Share of Project Costs |  | 235825 | 22525 | 30843 | 74555 | 127077 | 89322 | 344322
Overhead & Administrative Charges
| Departmental | 2% | 4716.5 | 450.5 | 616.9 | 1491.1 | 2541.6 | 1786.5 | 6886.6
| Corporate Admin (max $100,000) | 1.25% | 100 | 100 | 0 | 0 | 0 | 0 | 100
| Research (SMIR) (Const only) | 0.5% | 894.3 | 13.2 | 23.2 | 284.4 | 581.6 | 457.4 | 1359.8
| Overhead & Admin Charges Sub-total | 2.422% | 5710.8 | 563.7 | 640.1 | 1775.5 | 3123.2 | 2243.9 | 8346.4 | 2.424%
Financing Charges
| Corporate Interest | 2% | 4716.5 | 450.5 | 616.9 | 1491.1 | 2541.6 | 1786.5 | 6886.6
Operating Budget Impact Detail
|  |  | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025
| Salaries and Benefits |  |  |  |  | 100 | 100 | 100 | 100 | 100 | 100
| Materials, Parts and Supplies |  | 2020: 5; 2021: 2; 2022: 10
Other
| Total Operating Impact |  | 0 | 0 | 0 | 105 | 102 | 110 | 100 | 100 | 100
Note on E6: Amann, Ron: Indicate the Escalation % per year starting from the Estimate Year. Typically it is the same for each but can change based on the investment. The Escalation Rate in future years will be reflected in the costs of each line item based on the year that the work occurs.
Note on D8: Molinski, Krista: Year in which costs are based.
Note on E8: Amann, Ron: Enter the year that the work will occur. The years do not need to be sequential. That is, work does not need to start the first year after the Estimate Year and work does not have to occur for 1 or more years.
Note on A19: Amann, Ron: The items below are provided as example elements. The Estimator needs to identify the cost elements based on the type of project.
Note on A45: Amann, Ron: The categories below are provided as examples and should be defined by the estimator as part of the Risk Management process.
Note on A57: Molinski, Krista: See Appendix J of FM-004
Note on B73: Amann, Ron: Applies to Public Works only.
Note on B74: Molinski, Krista: Rows added for Estimator to customize additional fees or charges. Estimator needs to add formulas to columns D - J
Note on B82: Amann, Ron: Based on current year project costs. (similar to paying L/C interest only).

## EX_Estimate Classification
Class of Estimate
| Investment | Cho-Cho Bridge |  |  | Date | 2016-01-01
| Description |  |  |  | BC ID | BC_PW_CHO CHO Overpass _2017_001 V2.0
Legend
| Blank | Development of the deliverable has not begun. |  |  | C | Deliverable has been reviewed and approved as appropriate.
| S | Rough work on the deliverable has begun. |  |  | n/a | Not applicable. The deliverable does not apply to the project.
| P | Work on the deliverable is advanced and may be complete, excepting final review and approvals. |  |  |  | BoE Author's Determination (highlighted selection)
Table 1 - Classification of Estimate Analysis
| Characteristic | Weighting | Class 1 | Class 2 | Class 3 | Class 4 | Class 5 | Comments
1 | Project Definition | Primary | 65% to 100% | 30% to 75% | 10% to 40% | 1% to 15% | 0% to 2%
2 | End Usage | Secondary | Tender Check | Semi-Tender | Budget | Study | Screening
3 | Methodology | Secondary | Detailed Unit Cost with Detailed Take-off Cost | Detailed Unit Costs with Forced Detailed Take-off Cost | Semi-detailed Unit Cost with Assembly Level Line Items | Parametric Models, Assembly-Driven Models | SF (sq.ft.) Factoring, Parametric Modeling, Judgment, Analogy
4 | Expected Accuracy (from Appendix 2 - Cap Bug) | Secondary | High: +3% to +10% Low: -3% to -5% | High: +10% to +20% Low: -5% to -10% | High: +20% to +30% Low: -10% to -20% | High: +30% to +60% Low: -20% to -30% | High: +60% to +100% Low: -30% to -50%
Table 2 - Supporting Class of Estimate Rationale
The following table is used to provide the supporting rationale for selecting the above characteristics.
General Project Data
1 | General Scope Description |  | Defined | Defined | Defined | Preliminary | Assumed | n/a
2 | Project Location |  | Specific | Specific | Specific | Approximate | General | n/a
3 | Functional Space Req (m2) |  | Specific | Specific | Defined | Preliminary | Started | n/a
4 | Standards Requirements |  | Defined | Defined | Defined | Preliminary | Assumed | n/a
5 | Total Capacity |  | Defined | Defined | Defined | Defined | Preliminary | n/a
6 | Electrical Capacity |  | Defined | Defined | Defined | Defined | Preliminary | n/a
7 | Soils / Hydrology Report |  | Defined | Defined | Defined | Preliminary | None | n/a
8 | Integrated Project Plan |  | Defined | Defined | Defined | Preliminary | None | n/a
9 | Project Master Schedule |  | Defined | Defined | Defined | Defined | Approximate | n/a
10 | Work Breakdown Structure |  | Defined | Defined | Defined | Defined | Preliminary | n/a
11 | Project Code of Accounts |  | Defined | Defined | Defined | Defined | Preliminary | n/a
12 | Contracting Strategy |  | Defined | Defined | Defined | Preliminary | Assumed | n/a
13 | Escalation Strategy / Basis |  | Defined | Defined | Defined | Preliminary | Assumed | n/a
Design Deliverables
14 | Standards Drawings |  | C | C | C | S/P |  | n/a
15 | Site Plan |  | C | C | C | S/P | S | n/a
16 | Existing Site Plan |  | C | C | C | S/P | S | n/a
21 | Demolition Plan and Drawings |  | C | C | P | S/P |  | n/a
22 | Utility Plan and Drawing |  | C | C | P | S/P |  | n/a
23 | Site Electrical Plan / Drawing |  | C | C | P | S/P |  | n/a
24 | Site Lighting Plan / Drawing |  | C | C | P | S/P |  | n/a
25 | Site Comm Plan / Drawing |  | C | C | P | S/P |  | n/a
26 | Erosion Control Plan / Drawing |  | C | C | P | S/P |  | n/a
27 | Stormwater Plan / Drawing |  | C | C | P | S/P |  | n/a
28 | Landscaping Plan / Drawing |  | C | C | P | S/P |  | n/a
29 | External Elevations (Structure) |  | C | C | P | S/P |  | n/a
30 | Interior Elevations (Structure) |  | C | P | S |  |  | n/a
31 | Interior Section Views |  | C | C | P | S/P |  | n/a
32 | Partition or Wall Types |  | C | C | S/P | S/P |  | n/a
33 | Finish Schedule |  | C | C | P | S/P |  | n/a
34 | Door Schedules |  | C | P | P | S/P |  | n/a
35 | Window Schedules |  | C | P | P | S/P |  | n/a
36 | Restroom Schedules |  | C | P | P | S/P |  | n/a
37 | Furniture Plans / Schedules / Drawings |  | C | C | P | S/P |  | n/a
38 | Signage Drawings / Schedules |  | C | P | P | S/P |  | n/a
39 | Fire Protection Plan / Drawings |  | C | C | P | S/P |  | n/a
40 | Room Layout Plan / Drawings |  | C | C | P | S/P |  | n/a
41 | Foundation Plan / Drawings |  | C | C | P | S/P |  | n/a
42 | Foundation Section / Details |  | C | C | P | S/P |  | n/a
43 | Structural Plan / Drawings |  | C | C | P | S/P |  | n/a
44 | Structural Section / Details |  | C | C | P | S/P |  | n/a
45 | Roof Plan Drawings / Details |  | C | C | P | S/P |  | n/a
46 | Material / Equipment Specs |  | C | C | P | S/P |  | n/a
47 | Building Envelope / Moisture Protection / Flashing Details |  | C | C | P | S/P |  | n/a
48 | Mechanical / HVAC Plan / Drawings |  | C | C | P | S/P |  | n/a
49 | Mechanical / HVAC Details |  | C | P | S/P |  |  | n/a
50 | Mechanical / HVAC Schedules |  | C | P | S/P |  |  | n/a
51 | Flow Control Designs |  | C | P | P | S/P |  | n/a
52 | Plumbing Plan / Drawings |  | C | C | P | S/P |  | n/a
53 | Plumbing Details |  | C | P | S/P |  |  | n/a
54 | Plumbing Riser Diagram |  | C | P | S/P |  |  | n/a
55 | One-Line Electrical Diagram |  | C | C | P | S/P |  | n/a
56 | Electrical Power Plan |  | C | C | P | S/P |  | n/a
57 | Interior Lighting Plan / Drawings |  | C | P | S/P |  |  | n/a
58 | Security Plan / Drawings |  | C | P | S/P |  |  | n/a
59 | Emergency Communication Plan / Drawings |  | C | P | S/P |  |  | n/a
60 | Life Safety Plan / Drawings |  | C | C | S/P | S |  | n/a
61 | Lightning Protection Plan |  | C | P | S/P |  |  | n/a
62 | Motor Control Diagram |  | C | P | S/P |  |  | n/a
63 | Lighting Control Drawings |  | C | P | S/P |  |  | n/a
64 | Lighting Schedules |  | C | P | S/P |  |  | n/a
65 | Electrical / Panel Drawings |  | C | P | S/P |  |  | n/a
66 | Equipment Schedule |  | C | P | S/P | S |  | n/a
67 | Info Systems / Telecom Plan |  | C | P | S/P |  |  | n/a
68 | Info Systems / Telecom Details |  | C | P | S/P |  |  | n/a
[7 empty] | Overall |  | Class 3

## EX_Risk Assessment
Risk Management Plan (RMP)
Project | Cho-Cho Bridge |  |  | Date | 2016-01-01
Description | Design and construct a railway overpass |  |  | File No.
Bid Opp. No.
Risk Event Identification |  |  |  |  | Risk Severity | Risk Response | Action(s) to be Undertaken | Contingency Plan | Cost to Manage Risks (Identified in BOE with cost breakdown detail shown on separate worksheet) | Risk Owner
Risk Event Outcome | Threat or Opportunity? | As a result of (Risk Cause) | This event may occur (Uncertain Event) | Which leads to (Effect on objectives)
Bridge Foundation Re-design and De-watering Pump Station (Temp and Permanent pumps required) | Threat | Excavation for bridge foundation | Groundwater table is hit | Extra costs to pump and re-design the bridge foundation | Critical | Reduce | Perform Geotechnical Drilling - Analysis Allow Contingency for construction de-watering | Have Typical Design for Permanent Dewatering Station available | Geotechnical study included in scope - 250K Contingency allowance for Site De-watering 500K. | PM
Design Scope increase due to railway demands | Threat | Railway negotiations not being completed | Additional Design Scope is needed | Cost for Design modifications and additions | Serious | Reduce | Early discussion with Railway Engineers to understand requirements. | Ensure Design Consultant has experience with Railway requirements and has staff to address this risk | Contingency allowance for additional Design $500K | PM
Construction cost increase due to land purchase delays | Threat | Land not being secured in a timely fashion | Access to land is delayed | Delay in construction starting | Critical | Reduce | Have City realtors engage land owners early and ensure urgency of land purchases is understood. Do not tender contract if not confident that land can be secured. | Use Contingency to pay added construction costs due to inflation. Pay more $ for Land. | Contingency set at $5M | PM
Cost to Pubic Engagement Activities over Budget | Threat | More involvement of Councillor and local citizen | Additional PE activities and communication requirements than budgeted for | More costs than estimated | Acceptable | Accept | Allow for additional PE session in Cost Estimate | Take funds from General Contingency as will be in the $20k range. | n/a | PM
Land Costs exceed Budget | Threat | Expropriation activities are needed | Higher than estimated land costs | Additional funds needed and Council approval required | Serious | Reduce | Early communication with Land Owners. Have City realtors engage land owners early and ensure urgency of land purchases is understood. | Include allowance in Contingency. Engage Mayor & Councillor if risk increases. | Contingency set at $5M | PM
Design cost increase | Threat | The detailed-design refinement of the end product, review meetings, requirement clarifications all impact the time spend finalizing the detailed design. | Additional time is spend during Detailed Design | Costs increasing over contract value | Important | Reduce | Mange the design process Regular review and assess design schedule with production Limit stakeholder influence | Use Contingency Get more money | Assume 10% of Design budget (Known - unknown) | PM
Construction cost increase | Threat | Design clarifications, modifications cause incremental increases to construction costs | Construction cost increasing | Costs increasing over contract value | Serious | Reduce | Mange the Change Control process Assess type of changes and allocate costs accordingly | Use Contingency Get money | Assume 10% of Construction budget (Known - unknown) | PM
Note on H6: Amann, Ron: Avoid: Remove the cause of the risk in order to eliminate the risk event form occurring. Transfer: Utilize insurance or bonding. Reduce: Under-take additional activities to reduce the effect or impact of the risk event occurring. Accept: If the risk event occurs and utilize contingency funds to address the risk outcome if it occurs.
Note on J6: Amann, Ron: If mitigation does not work and risk event outcome occurs, what will you do?

## Data (hidden)
|  | 1 | 2 | 3 | 4 | 5
|  | 6 | 7 | 8 | 9 | 10
1
2
3
4
5
n/a
Class 1
Class 2
Class 3
Class 4
Class 5