## Quality information
Risk Management Plan (RMP) Template
Document Change Log This section is used to track content changes to the Risk Management Plan. As the Risk Log is updated at regular intervals, this section should only identify the date of any updates - and only significant updates - to the Risk Management Plan. Updates to specific Risk Events do not need to be captured here, unless those risks need special identification.
Document Revision No. | Change in Content | Date Released | Released By
Template Quality Information (This section is used to track changes to the template design)
Document Revision No. | Revisions | Date Released | Released By
V1.0 | Released for use |  | Jason Ruby
v1.1 | Improvements to Risk template | 2016-02-09 | RFA
V1.2 | 1) Added columns to identify how the risk event will be managed. 2) Added an example tab | 2016-02-22 | RFA

## Template Instructions
How to use the Risk Management Plan (RMP) Template
The Risk Management Plan (RMP) Template is used in conjunction with the Project Delivery Plan (PDP) Short Form Template and the Project Risk Identification Checklist. This is a qualitative Risk Management Plan.
Complete the RMP by following the instructions for each of the columns as described below.
RMP Tab
Project | The Project Name as on the Business Case.
Description | A description of the project that is used in the Project Charter and/or PDP.
Date | The date when the Risk Management Plan was first approved (format: MM/DD/YYYY)
Business Case ID | The Business Case ID.
Bid Opp. No. | The Bid Op Number if available, or put "N/A" if not available.
Risk Event | Identify the Risk Event. Refer to the Risk Identification Checklist located on the City's CityNet.
Threat or Opportunity? | Select the option from the drop-down list within the cell. |  |  | Risk Severity Options and Chart
As a Result of (Risk Cause) | Identify the cause of the Risk Event.
This Event may occur (Uncertain Event) | Identify what specific Event will occur.
Which Leads to (Effect on Objectives) | Identify the end result of the Risk Event.
[6 empty] | 1 | 2 | 3 | 4 | 5
Risk Severity | Decide the severity of the risk and select one of the following Severity Options from the cell's drop-down list: Critical, Serious, Important, or Acceptable. See the Risk Severity Options and Chart below. | Critical | Risk has a high consequence and likelihood of impacting the objectives of the project and is unacceptable. The response is to eliminate the Risk Event. |  | 5 | 5 | 10 | 15 | 20 | 25
Risk Response | Identify how the risk will be addressed based on a specific category. Click the red triangle in the column's heading for an explanation of the Responses. Select one of the following Response Options from the cell's drop-down list: Avoid, Transfer, Reduce or Accept. | Serious | Risk that needs to be eliminated if no acceptable option is available to manage or reduce the risk consequence or likelihood. |  | 4 | 4 | 8 | 12 | 16 | 20
Action(s) to be Undertaken | Identify the specific actions that will undertaken to manage the risk. These actions will need to be reviewed by the PM on a regular basis as part of the Risk Management activities. | Important | Risk that is tolerable but needs to be managed or transferred with a Risk Management Plan. |  | 3 | 3 | 6 | 9 | 12 | 15
Contingency Plan | Identify what action(s) will be undertaken should the risk mitigation or other activities not address the risk and the risk event occurs. | Acceptable | Risk that can be dealt with as part of the project or when the product is transferred to the Business Owner. |  | 2 | 2 | 4 | 6 | 8 | 10
Cost to Manage Risk | Identify the costs to manage the risk. The costs can include the costs needed to be included in the project scope of work and/or the cost for contingency allowance dollars that will be used to address a specific portion or all the costs should the risk event occur. |  |  |  | 1 | 1 | 2 | 3 | 4 | 5
Risk Owner | The individual who is in the best position to be responsible for managing the risk.
EX_RMP
This Worksheet shows a sample risk assessment that illustrates how to use the template. The data and identified risks are not intended to represent actual data from an actual project.
Template Data Tab
This Worksheet is hidden as it contains attribute data used to populate specific cells which must not be deleted.

## RMP Template
Risk Management Plan (RMP)
Project |  |  |  | Date | MM/DD/YYYY
Description |  |  |  | Business Case ID
Bid Opp. No.
Risk Event Identification |  |  |  |  | Risk Severity | Risk Response | Action (s) to be undertaken | Contingency Plan | Cost to Manage Risks (Identified in BOE with the "cost breakdown" detail shown on separate worksheet) | Risk Owner
Risk Event Outcome | Threat or Opportunity? | As a result of (Risk Cause) | This event may occur (Uncertain Event) | Which leads to (Effect on objectives)
Note on G5: Amann, Ron: Avoid: Remove the cause of the risk in order to eliminate the Risk Event from occurring. Transfer: Utilize insurance or bonding. Reduce: Undertake additional activities to reduce the effect or impact of the Risk Event occurring. Accept: If the Risk Event occurs, utilize Contingency Funds to address the risk outcome.
Note on I5: Amann, Ron: If mitigation does not work and Risk Event outcome occurs, what will you do?

## EX_RMP
Risk Management Plan
Project |  |  |  | Date | MM/DD/YYYY
Description |  |  |  | Business Case ID
Bid Opp. No.
Risk Event Identification |  |  |  |  | Risk Severity | Risk Response | Action (s) to be undertaken | Contingency Plan | Cost to Manage Risks (Identified in BOE with cost breakdown detail shown on separate worksheet) | Risk Owner
Risk Event Outcome | Threat or Opportunity? | As a result of (Risk Cause) | This event may occur (Uncertain Event) | Which leads to (Effect on objectives)
Bridge foundation re-design and de-watering pump station (Temporary and Permanent pumps required) | Threat | Excavation for bridge foundation | Ground water table is hit | Extra costs to pump and re-design of the bridge foundation | Critical | Reduce | Perform Geotechnical Drilling - Analysis Allow Contingency for Construction de-watering. | Have Typical Design for Permanent Dewatering Station available. | Geotechnical study included in scope- 100K. Contingency allowance for Site De-watering 500K. | PM
Design Scope increase due to Railway demands | Threat | Railway negotiations not being completed | Additional Design scope is needed | Cost for Design modifications and additions | Serious | Reduce | Early discussion with Railway Engineers to understand requirements | Ensure Design Consultant has experience with Railway requirements and has staff to address this risk. | Contingency allowance for additional Design $500K. | PM
Construction cost increase due to Land Purchase delays | Threat | Land not being secured in a timely fashion | Access to land is delayed | Delay in construction starting | Critical | Reduce | Have City realtors engage land owners early and ensure urgency of land purchases is understood. Do not tender contract if not confident that land can be secured. | Use Contingency to pay added construction costs due to inflation. Pay more $ for land. | Contingency set at $2M | PM
Cost to Pubic Engagement activities over budget | Threat | More involvement of Councillor and local citizen | Additional PE activities and communication requirements than budgeted | More costs than estimated | Acceptable | Accept | Allow for additional PE session in Cost Estimate. | Take funds from General Contingency as will be in the $20k range. | n/a | PM
Land Costs exceed Budget | Threat | Expropriation activities are needed | Higher than estimated land costs | Additional funds needed and Council approval required | Serious | Reduce | Early communication with Land Owners. Have City realtors engage land owners early and ensure urgency of land purchases is understood. | Include allowance in Contingency. Engage Mayor & Councillor if risk increases. | Contingency set at $1M | PM
Design cost increase | Threat | The detailed-design refinement of the end product, review meetings, requirement clarifications all impact the time spend finalizing the detailed design. | Additional time is spend during Detailed Design | Costs increasing over contract value | Important | Reduce | Mange the design process Regular review and assess design schedule with production Limit stakeholder influence | Use Contingency Get more money | Assume 10% of Design budget (Known - unknown) | PM
Construction cost increase | Threat | Design clarifications, modifications cause incremental increases to construction costs | Construction cost increasing | Costs increasing over contract value | Serious | Reduce | Mange the Change Control process Assess type of changes and allocate costs accordingly | Use Contingency Get money | Assume 10% of Construction budget (Known - unknown) | PM
Note on G5: Amann, Ron: Avoid: Remove the cause of the risk in order to eliminate the Risk Event from occurring. Transfer: Utilize insurance or bonding. Reduce: Undertake additional activities to reduce the effect or impact of the Risk Event occurring. Accept: If the Risk Event occurs, utilize Contingency Funds to address the risk outcome.
Note on I5: Amann, Ron: If mitigation does not work and Risk Event outcome occurs, what will you do?

## Template Data - drop-down list (hidden)
| Critical | Serious | Important | Acceptable
Threat
Opportunity |  |  |  |  | Avoid
Transfer
Reduce
Accept
Note on H5: Amann, Ron Avoid: Remove the cause of the risk in order to eliminate the risk event form occurring
Note on H6: Amann, Ron: Transfer: Utilize insurance or bonding
Note on H7: Amann, Ron: Under-take additional activities to reduce the effect or impact of the risk event occurring