THE CITY OF WINNIPEG

TENDER

Tender No. Click or tap here to enter text.

Click or tap here to enter text.

Contract Title (maximum 80 characters & although appears in uppercase only the first letter of each word should be typed uppercase & subsequent letters of each word in lowercase)

DO NOT USE TRACK CHANGES OR MARKUP.

IT WILL OVER RIDE THE FORMATTING AND YOUR DOCUMENT WILL BE UNUSABLE

SPEC NOTE: Do not use hard returns ( ¶ ) within the Contract Title.

SPEC NOTE: After inserting Tender No. (nnnn for PeopleSoft numbers: nnnn-yyyy for PurTrac numbers) and Contract Title between the bookmark brackets, update fields (click Print Preview) to update all required references to the Tender No. and Contract Title.

SPEC NOTE: All clauses included in this template are mandatory and may not be deleted or modified unless approved in writing by the Manager of Purchasing.

SPEC NOTE: Where a Spec Note is provided, modifications may only be made in accordance with the Spec Note, unless approved in writing by the Manager of Purchasing.

*** SPEC NOTE: If there are any funding agreements related to a Tender, then the Contract Administrator should review the funding agreement to ensure that the General Conditions include clauses to ensure compliance with the funding agreement, particularly in the areas of Insurance, Indemnity, Document Retention and Third Party Contract requirements.  The Contract Administrator should consult with Legal Services, to ensure the General Conditions wording aligns with the applicable funding agreement and the potential for a new Supplemental Conditions, by submitting a Legal Services Request to Legal Services Request Form with the proposed wording included.

Version 2025 11 01 Construction w Bid Security

TABLE OF CONTENTS

SPEC NOTE: The Table of Contents is automatically generated.  When the template is first opened, page numbers may be incorrect.  To update, right click anywhere in the field (shaded area) and select Update Field, Update entire table.  When printing, the update prompt may display if any changes have been made since the previous update.

PART A - BID SUBMISSION

Form A: Bid/Proposal

Form B: Prices

Form G1: Bid Bond and Agreement to Bond

PART B - Bidding Procedures

B1.	Contract Title	1

B2.	Submission Deadline	1

B3.	Site Investigation	1

B4.	Bidders' Conference	2

B5.	Enquiries	2

B6.	Confidentiality	3

B7.	Addenda	3

B8.	Substitutes	3

B9.	Bid Components	4

B10.	Bid	5

B11.	Prices	5

B12.	Disclosure	6

B13.	Conflict of Interest and Good Faith	7

B14.	Qualification	8

B15.	Bid Security	9

B16.	Opening of Bids and Release of Information	10

B17.	Irrevocable Bid	10

B18.	Withdrawal of Bids	10

B19.	Evaluation of Bids	10

B20.	Award of Contract	12

PART C - General Conditions

C0.	General Conditions	1

PART D - Supplemental Conditions

General

D1.	General Conditions	1

D2.	Scope of Work	1

D3.	Definitions	1

D4.	Contract Administrator	1

D5.	Contractor's Supervisor	2

D6.	Furnishing of Documents	2

Submissions

D7.	Authority to Carry on Business	2

D8.	Safe Work Plan	2

D9.	Insurance	2

D10.	Contract Security	3

D11.	Detailed Prices	4

D12.	Subcontractor List	4

D13.	Equipment List	5

D14.	Detailed Work Schedule	5

D15.	Requirement for Site Accessibility Plan	5

Schedule of Work

D16.	Commencement	6

D17.	Work By Others	7

D18.	Working Days	7

D19.	Critical Stages	7

D20.	Substantial Performance	8

D21.	Total Performance	8

D22.	Liquidated Damages	9

D23.	Scheduled Maintenance	9

Control of Work

D24.	Job Meetings	10

D25.	Prime Contractor – The Workplace Safety and Health Act (Manitoba)	10

D26.	The Workplace Safety and Health Act (Manitoba) – Qualifications	10

D27.	Responsibility for Plant and Materials	10

Payment

D28.	Payment	10

D29.	Payment Schedule	11

Warranty

D30.	Warranty	11

Indemnity

D31.	Indemnity	12

Form I: Detailed Prices	13

Form J: Subcontractor List	15

Form K: Equipment	16

Form L: Detailed Work Schedule	18

Form L: Detailed Work Schedule	19

PART E - Specifications

General

E1.	Applicable Specifications and Drawings	1

E2.	Soils Investigation Report	2

General Requirements

E3.	Office Facilities	2

E4.	Hazardous Materials	2

E5.	Mobilization and Demobilization Payment	2

E6.	Cash Allowance for Additional Work	2

E7.	Traffic Control	3

E8.	^	4

PART F - Security Clearance

F1.	Security Clearance	1

Security Clearance for Site Investigations at Winnipeg Police Service Buildings or Stations

Security Clearance for Work at Winnipeg Police Service Buildings or Stations

Bidding Procedures

Contract Title

Click or tap here to enter text.

SPEC NOTE: The Contract Title will reflect the bookmark entry made on the cover page after a field update.

DO NOT USE TRACK CHANGES OR MARKUP.  IT WILL OVER RIDE THE FORMATTING AND YOUR DOCUMENT WILL BE UNUSABLE

Submission Deadline

SPEC NOTE: Insert month, day and year of Submission Deadline scheduled by the Purchasing Division.

The Submission Deadline is 12:00 noon Winnipeg time, ^month day, year.

The Contract Administrator or the Manager of Purchasing may extend the Submission Deadline by issuing an addendum at any time prior to the time and date specified in B2.1.

Site Investigation

SPEC NOTE: Use B3 only if the Bidder must be advised of restrictions on or special reasons for investigating the Site.

VERSION 1 - Use this version when providing a limited number of opportunities to view the Site is reasonable and the Contract Administrator should be in attendance, e.g., soil test holes to be drilled.  Insert times, month(s), day(s) and year when the Site will be attended by the Contract Administrator.  Advise the Purchasing Division of the requirement to ensure that it is included in the advertisement of the Tender.

Further to C3.1, the Contract Administrator or an authorized representative will be available at the Site at ^start time on ^month day, year to provide Bidders access to the Site.

The Bidder is advised that ^SPEC NOTE: Identify any special reason(s) the Bidder should view the site, e.g., demonstration of operations, test borings, etc.  Delete B3.2 if there are no such reasons.

The Bidder shall not be entitled to rely on any information or interpretation received at the Site investigation unless that information or interpretation is the Bidder’s direct observation, or is provided by the Contract Administrator in writing.

The Bidder is responsible for inspecting the Site, the nature of the Work to be done and all conditions that might affect their Bid or their performance of the Work, and shall assume all risk for conditions existing or arising in the course of the Work which have been or could have been determined through such inspection.

VERSION 2 - Use this version when providing multiple opportunities to view the Site is reasonable but the Contract Administrator should be in attendance, e.g., to provide access to a locked building.

    - Further to C3.1, the Bidder may make an appointment to view the Site by contacting the Contract Administrator.

The Bidder is advised that ^SPEC NOTE: Identify any special reason(s) the Bidder should view the site, e.g., demonstration of operations, test borings, etc.  Delete B3.2 if there are no such reasons.

The Bidder shall not be entitled to rely on any information or interpretation received at the Site investigation unless that information or interpretation is the Bidder’s direct observation, or is provided by the Contract Administrator in writing.

The Bidder is responsible for inspecting the Site, the nature of the Work to be done and all conditions that might affect their Bid or their performance of the Work, and shall assume all risk for conditions existing or arising in the course of the Work which have been or could have been determined through such inspection.

VERSION 3 - Use this version when the Site is accessible without the Contract Administrator being in attendance, e.g., open field in a public right of way.

    - Further to C3.1, the Bidder may view the Site without making an appointment.

The Bidder is advised that ^SPEC NOTE: Identify the reason(s) the Bidder should view the site, e.g., existing snow cover, etc., or any restrictions on access such as days of the week or time of day.  Delete B3.2 if there are no such reasons.

The Bidder is responsible for inspecting the Site, the nature of the Work to be done and all conditions that might affect their Bid or their performance of the Work, and shall assume all risk for conditions existing or arising in the course of the Work which have been or could have been determined through such inspection.

VERSION 4 - Use this version when attendance at a Site meeting is Mandatory. For mandatory site meetings you shall provide two dates and times for Bidders to attend.  Advise the Purchasing Division of the date and time of the site meetings to ensure that it is included in the posted Tender.  Minutes and attendance shall be taken at the Site meeting and kept on file (provide a copy to the Contracts Officer in the Purchasing Division).

    - Further to C3.1, the Bidder shall attend a Site meeting at ^start time on ^month day, year  or ^start time on ^month day, year.   Attendance is mandatory, and the Bid of any Bidder not having attended will be rejected on the basis that it is non-responsive.

The Bidder is advised that ^SPEC NOTE: Identify the reason(s) the Bidder must view the site, e.g., demonstration of operations, test borings, etc.

The Bidder shall not be entitled to rely on any information or interpretation received at the Site Meeting unless that information or interpretation is the Bidder’s direct observation, or is provided by the Contract Administrator in writing.

The Bidder is responsible for inspecting the Site, the nature of the Work to be done and all conditions that might affect their Bid or their performance of the Work, and shall assume all risk for conditions existing or arising in the course of the Work which have been or could have been determined through such inspection.

VERSION 5 - Use this version when one opportunity to view the Site is reasonable, and the Contract Administrator should be in attendance, e.g., soil test holes to be drilled.  Insert time, month, day and year when the Site will be attended by the Contract Administrator.  Advise the Purchasing Division of the requirement to ensure that it is included in the advertisement of the Tender.

    - Further to C3.1, a Site meeting will be held at start  time on ^month day, year to provide Bidders access to the Site.

The Bidder is advised that ^SPEC NOTE: Identify any reason(s) the Bidder should view the site, e.g., demonstration of operations, test borings, etc.  Delete B3.2 if there are no such reasons.

The Bidder shall not be entitled to rely on any information or interpretation received at the Site investigation unless that information or interpretation is the Bidder’s direct observation, or is provided by the Contract Administrator in writing.

The Bidder is responsible for inspecting the Site, the nature of the Work to be done and all conditions that might affect their Bid or their performance of the Work, and shall assume all risk for conditions existing or arising in the course of the Work which have been or could have been determined through such inspection.

Bidders' Conference

SPEC NOTE: Use B4 only when a Bidders’ conference is necessary.

VERSION 1 - Use this version only when a Bidders’ conference is reasonably necessary but attendance is voluntary.  Insert location, times, month, day and year.  Advise the Purchasing Division of the requirement to ensure that it is included in the advertisement of the Tender.  Minutes of any discussion at the Bidders’ conference must be kept and an addendum must be issued naming the Bidders who attended and addressing any issues (e.g., interpretations or answers to questions raised at the Bidders’ conference) reasonably requiring such.

Further to C3.1, the Contract Administrator will hold a Bidders’ conference at ^location at ^start time on ^month day, year.

The Bidder is advised that, at the Bidders’ Conference, ^SPEC NOTE: Identify the reason(s) the Bidder should attend the conference.

The Bidder shall not be entitled to rely on any information or interpretation received at the Bidders’ Conference unless that information or interpretation is provided by the Contract Administrator in writing.

VERSION 2 - Use this version only when attendance at a Bidders’ conference is absolutely essential and therefore compulsory.  Insert location, times, month, day and year.  Advise the Purchasing Division of the requirement to ensure that it is included in the advertisement of the Tender.  Minutes of the Bidders’ conference must be kept and an addendum must be issued naming the Bidders who attended and addressing any issues (e.g., interpretations or answers to questions raised at the Bidders’ conference) reasonably requiring such.

    - Further to C3.1, the Bidder shall attend a Bidders’ conference at ^location at ^start time on ^month day, year.  Attendance is mandatory, and the Bid of any Bidder not having attended will be rejected on the basis that it is non-responsive.

The Bidder is advised that, at the Bidders’ Conference, ^SPEC NOTE: Identify the reason(s) the Bidder must attend the conference.

The Bidder shall not be entitled to rely on any information or interpretation received at the Bidders’ Conference unless that information or interpretation is provided by the Contract Administrator in writing.

Enquiries

All enquiries shall be directed to the Contract Administrator identified in D4.1.

If the Bidder finds errors, discrepancies or omissions in the Tender, or is unsure of the meaning or intent of any provision therein, the Bidder shall notify the Contract Administrator of the error, discrepancy or omission, or request a clarification as to the meaning or intent of the provision at least five (5) Business Days prior to the Submission Deadline.

Responses to enquiries which, in the sole judgment of the Contract Administrator, require a correction to or a clarification of the Tender will be provided by the Contract Administrator to all Bidders by issuing an addendum.

Responses to enquiries which, in the sole judgment of the Contract Administrator, do not require a correction to or a clarification of the Tender will be provided by the Contract Administrator only to the Bidder who made the enquiry.

The Bidder shall not be entitled to rely on any response or interpretation received pursuant to B5 unless that response or interpretation is provided by the Contract Administrator in writing.

Any enquiries concerning submitting through MERX should be addressed to:

MERX Customer Support

Phone: 1-800-964-6379

Email: merx@merx.com

Confidentiality

Information provided to a Bidder by the City or acquired by a Bidder by way of further enquiries or through investigation is confidential. Such information shall not be used or disclosed in any way without the prior written authorization of the Contract Administrator.  The use and disclosure of the confidential information shall not apply to information which:

was known to the Bidder before receipt hereof; or

becomes publicly known other than through the Bidder; or

is disclosed pursuant to the requirements of a governmental authority or judicial order.

The Bidder shall not make any statement of fact or opinion regarding any aspect of the Tender to the media or any member of the public without the prior written authorization of the Contract Administrator.

Addenda

The Contract Administrator may, at any time prior to the Submission Deadline, issue addenda correcting errors, discrepancies or omissions in the Tender, or clarifying the meaning or intent of any provision therein.

The Contract Administrator will issue each addendum at least two (2) Business Days prior to the Submission Deadline, or provide at least two (2) Business Days by extending the Submission Deadline.

Addenda will be available on the MERX website at www.merx.com.

The Bidder is responsible for ensuring that they have received all addenda and is advised to check the MERX website for addenda regularly and shortly before the Submission Deadline, as may be amended by addendum.

The Bidder shall acknowledge receipt of each addendum in Paragraph 10 of Form A: Bid/Proposal.  Failure to acknowledge receipt of an addendum may render a Bid non-responsive.

Notwithstanding B5, enquiries related to an Addendum may be directed to the Contract Administrator indicated in D4.

Substitutes

The Work is based on the Plant, Materials and methods specified in the Tender.

Substitutions shall not be allowed unless application has been made to and prior approval has been granted by the Contract Administrator in writing.

SPEC NOTE: Increase or decrease the five (5) Business Days depending on the complexity of the Work.  Four (4) Business Days is the minimum feasible.

Requests for approval of a substitute will not be considered unless received in writing by the Contract Administrator at least five (5) Business Days prior to the Submission Deadline.

The Bidder shall ensure that any and all requests for approval of a substitute:

provide sufficient information and details to enable the Contract Administrator to determine the acceptability of the Plant, Material or method as either an approved equal or alternative;

identify any and all changes required in the applicable Work, and all changes to any other Work, which would become necessary to accommodate the substitute;

identify any anticipated cost or time savings that may be associated with the substitute;

certify that, in the case of a request for approval as an approved equal, the substitute will fully perform the functions called for by the general design, be of equal or superior substance to that specified, is suited to the same use and capable of performing the same function as that specified and can be incorporated into the Work, strictly in accordance with the proposed work schedule and the dates specified in the Supplemental Conditions for Substantial Performance and Total Performance;

certify that, in the case of a request for approval as an approved alternative, the substitute will adequately perform the functions called for by the general design, be similar in substance to that specified, is suited to the same use and capable of performing the same function as that specified and can be incorporated into the Work, strictly in accordance with the proposed work schedule and the dates specified in the Supplemental Conditions for Substantial Performance and Total Performance.

The Contract Administrator, after assessing the request for approval of a substitute, may in their sole discretion grant approval for the use of a substitute as an “approved equal” or as an “approved alternative”, or may refuse to grant approval of the substitute.

The Contract Administrator will provide a response in writing, at least two (2) Business Days prior to the Submission Deadline, to the Bidder who requested approval of the substitute.

The Contract Administrator will issue an Addendum, disclosing the approved materials, equipment, methods and products to all potential Bidders.  The Bidder requesting and obtaining the approval of a substitute shall be responsible for disseminating information regarding the approval to any person or persons they wish to inform.

If the Contract Administrator approves a substitute as an “approved equal”, any Bidder may use the approved equal in place of the specified item.

If the Contract Administrator approves a substitute as an “approved alternative”, any Bidder bidding that approved alternative may base their Total Bid Price upon the specified item but may also indicate an alternative price based upon the approved alternative.  Such alternatives will be evaluated in accordance with B19.

No later claim by the Contractor for an addition to the Total Bid Price because of any other changes in the Work necessitated by the use of an approved equal or an approved alternative will be considered.

Bid Components

The Bid shall consist of the following components:

Form A: Bid/Proposal;

Form B: Prices;

Form G1: Bid Bond and Agreement to Bond.

SPEC NOTE: List any Bidder-supplied documents or samples to be submitted with their bid that are required to evaluate the Bid in B9.1(d) and provide a corresponding Bidding Procedure after B15, Evaluation criteria for any such additional information must be stipulated in B19.

^;

^.

All components of the Bid shall be fully completed or provided, and submitted by the Bidder no later than the Submission Deadline, with all required entries made clearly and completely.

The Bid shall be submitted electronically through MERX at www.merx.com.

Bids will only be accepted electronically through MERX.

Bidders are advised that inclusion of terms and conditions inconsistent with the Tender document, including the General Conditions, will be evaluated in accordance with B19.1(a).

Bid

The Bidder shall complete Form A: Bid/Proposal, making all required entries.

Paragraph 2 of Form A: Bid/Proposal shall be completed in accordance with the following requirements:

if the Bidder is a sole proprietor carrying on business in their own name, their name shall be inserted;

if the Bidder is a partnership, the full name of the partnership shall be inserted;

if the Bidder is a corporation, the full name of the corporation shall be inserted;

if the Bidder is carrying on business under a name other than their own, the business name and the name of every partner or corporation who is the owner of such business name shall be inserted.

If a Bid is submitted jointly by two or more persons, each and all such persons shall identify themselves in accordance with B10.2.

In Paragraph 3 of Form A: Bid/Proposal, the Bidder shall identify a contact person who is authorized to represent the Bidder for purposes of the Bid.

Paragraph 13 of Form A: Bid/Proposal shall be signed in accordance with the following requirements:

if the Bidder is a sole proprietor carrying on business in their own name, it shall be signed by the Bidder;

if the Bidder is a partnership, it shall be signed by the partner or partners who have authority to sign for the partnership;

if the Bidder is a corporation, it shall be signed by their duly authorized officer or officers;

if the Bidder is carrying on business under a name other than their own, it shall be signed by the registered owner of the business name, or by the registered owner's authorized officials if the owner is a partnership or a corporation.

The name and official capacity of all individuals signing Form A: Bid/Proposal should be entered below such signatures.

If a Bid is submitted jointly by two or more persons, the word "Bidder" shall mean each and all such persons, and the undertakings, covenants and obligations of such joint Bidders in the Bid and the Contract, when awarded, shall be both joint and several.

Prices

VERSION 1 - Use this version with VERSION 1 of Form B: Prices for unit price contracts. If there is more than one line item, it is a unit price contract, not a lump sum contract.

The Bidder shall state a price in Canadian funds for each item of the Work identified on Form B: Prices.

SPEC NOTE: Use B11.1.1 ONLY if the contract contains substantial mechanical or electrical work. If including B11.1.1, add a line item to Form B: Prices for the Bidder to insert the MRST/PST as a separate item.  If unsure, consult with the Contracts Officer.

Notwithstanding C12.2.3(c), prices on Form B: Prices shall not include the Manitoba Retail Sales Tax (MRST, also known as PST), which shall be extra where applicable.

SPEC NOTE: Delete B11.1.2 if 3rd Party Funding is confirmed

Prices stated on Form B: Prices shall not include any costs which may be incurred by the Contractor with respect to any applicable funding agreement obligations as outlined in C24.  Any such costs shall be determined in accordance with C24.

The quantities listed on Form B: Prices are to be considered approximate only.  The City will use said quantities for the purpose of comparing Bids.

The quantities for which payment will be made to the Contractor are to be determined by the Work actually performed and completed by the Contractor, to be measured as specified in the applicable Specifications.

Payments to Non-Resident Contractors are subject to Non-Resident Withholding Tax pursuant to the Income Tax Act (Canada).

The Bidder shall enter the Total Bid Price from Form B: Prices into the Total Bid Price field in MERX.

Bidders are advised that the calculation indicated in B19.5 will prevail over the Total Bid Price entered in MERX.

VERSION 2 - Use this version for lump sum contracts.  MERX has a field to input the Total Bid Price so a separate Form B: Prices form is not required for lump sum contracts. Also remove “Form B: Prices” from the table of contents and bid components clause B9.1(b).

    - The Bidder shall enter the lump sum price in Canadian funds for the Work in the Total Bid Price field in MERX.

SPEC NOTE: If you require a separate line item for MRST/PST you will need to use the Unit Prices Form B template.  Use B11.1.1 ONLY if the contract contains substantial mechanical or electrical work. If including B11.1.1, add a line item to Form B: Prices for the Bidder to insert the MRST/PST as a separate item, one for the Lump Sum Price and the 2nd for “Applicable MRST/PST.  If unsure, consult with the Contracts Officer.

          - Notwithstanding C12.2.3(c), prices shall not include the Manitoba Retail Sales Tax (MRST, also known as PST), which shall be extra where applicable.

SPEC NOTE: Delete B11.1.2 if 3rd Party Funding is confirmed

          - Prices stated shall not include any costs which may be incurred by the Contractor with respect to any applicable funding agreement obligations as outlined in C24.  Any such costs shall be determined in accordance with C24.

Payments to Non-Resident Contractors are subject to Non-Resident Withholding Tax pursuant to the Income Tax Act (Canada).

VERSION 3 - Use this version with VERSION 3 of Form B: Prices for lump sum price contracts with separate prices for adjustment.  Insert a concise description and specification reference for each item for which a separate price is required.

    - The Bidder shall state the lump sum price in Canadian funds for the Work on Form B: Prices.

SPEC NOTE: Use B11.1.1 ONLY if the contract contains substantial mechanical or electrical work. If including B11.1.1, revise the Form B: Prices table to include two line items above the Total Bid Price, one for the Lump Sum Price and the 2nd for “Applicable MRST/PST.  If unsure, consult with the Contracts Officer.

          - Notwithstanding C12.2.3(c), prices on Form B: Prices shall not include the Manitoba Retail Sales Tax (MRST, also known as PST), which shall be extra where applicable.

SPEC NOTE: Delete B11.1.2 if 3rd Party Funding is confirmed

          - Prices stated on Form B: Prices shall not include any costs which may be incurred by the Contractor with respect to any applicable funding agreement obligations as outlined in C24.  Any such costs shall be determined in accordance with C24.

SPEC NOTE: if including any of the deductions clauses, you must insert the clause “The funds available for this contract are $xxx.” under D2, Scope of Work

The Bidder shall state a separate price in Canadian funds for each of the following items of Work on Form B: Prices:

Separate Price - Item No. 1 shall be the amount to be deducted from the lump sum price if ^description is substituted for ^description in accordance with ^cross reference of the Specifications;

Separate Price - Item No. 2 shall be the amount to be deducted from the lump sum price if ^description is reduced in accordance with ^cross reference of the Specifications;

Separate Price - Item No. 3 shall be the amount to be deducted from the lump sum price if ^description is deleted in accordance with ^cross reference of the Specifications.

SPEC NOTE: Use B11.2.1 only if the contract includes taxable mechanical or electrical work.  B11.2.1 and Form B: Prices must be consistent.  Consult with the Contracts Officer.

Notwithstanding C12.2.3(c), prices on Form B: Prices shall not include the Manitoba Retail Sales Tax (MRST, also known as PST), which shall be extra where applicable.

Payments to Non-Resident Contractors are subject to Non-Resident Withholding Tax pursuant to the Income Tax Act (Canada).

The Bidder shall enter the Total Bid Price from Form B: Prices into the Total Bid Price field in MERX.

Bidders are advised that the calculation indicated in B19.5 will prevail over the Total Bid Price entered in MERX.

Disclosure

SPEC NOTE:   Do Not Delete.  If City staff or Consultants have discussed or obtained information/services from Persons, the name of that Person (company name preferred) and what information was discussed or obtained must be disclosed below. If you haven’t discussed with any Persons, state N/A.

    - Various Persons provided information or services with respect to this Work.  In the City’s opinion, this relationship or association does not create a conflict of interest because of this full disclosure.  Where applicable, additional material available as a result of contact with these Persons is listed below.

    - The Persons are:

      - ^

      - ^

- SPEC NOTE: Delete if not required.

    - Additional Material:

      - ^

^

Conflict of Interest and Good Faith

Further to C3.3, Bidders, by responding to this Tender, declare that no Conflict of Interest currently exists, or is reasonably expected to exist in the future.

Conflict of Interest means any situation or circumstance where a Bidder or employee of the Bidder proposed for the Work has:

other commitments;

relationships;

financial interests; or

involvement in ongoing litigation;

- that could or would be seen to:

exercise an improper influence over the objective, unbiased and impartial exercise of the independent judgment of the City with respect to the evaluation of Bids or award of the Contract; or

compromise, impair or be incompatible with the effective performance of a Bidder’s obligations under the Contract;

has contractual or other obligations to the City that could or would be seen to have been compromised or impaired as a result of their participation in the Tender process or the Work; or

has knowledge of confidential information (other than confidential information  disclosed by the City in the normal course of the Tender process) of strategic and/or material relevance to the Tender process or to the Work that is not available to other bidders and that could or would be seen to give that Bidder an unfair competitive advantage.

In connection with their Bid, each entity identified in B13.2 shall:

avoid any perceived, potential or actual Conflict of Interest in relation to the procurement process and the Work;

upon discovering any perceived, potential or actual Conflict of Interest at any time during the Tender process, promptly disclose a detailed description of the Conflict of Interest to the City in a written statement to the Contract Administrator; and

provide the City with the proposed means to avoid or mitigate, to the greatest extent practicable, any perceived, potential or actual Conflict of Interest and shall submit any additional information to the City that the City considers necessary to properly assess the perceived, potential or actual Conflict of Interest.

Without limiting B13.3, the City may, in their sole discretion, waive any and all perceived, potential or actual Conflicts of Interest. The City’s waiver may be based upon such terms and conditions as the City, in their sole discretion, requires to satisfy itself that the Conflict of Interest has been appropriately avoided or mitigated, including requiring the Bidder to put into place such policies, procedures, measures and other safeguards as may be required by and be acceptable to the City, in their sole discretion, to avoid or mitigate the impact of such Conflict of Interest.

Without limiting B13.3, and in addition to all contractual or other rights or rights at law or in equity or legislation that may be available to the City, the City may, in their sole discretion:

disqualify a Bidder that fails to disclose a perceived, potential or actual Conflict  of Interest of the Bidder or any of their employees proposed for the Work;

require the removal or replacement of any employees proposed for the Work that has a perceived, actual or potential Conflict of Interest that the City, in their sole discretion, determines cannot be avoided or mitigated;

disqualify a Bidder or employees proposed for the Work that fails to comply with any requirements prescribed by the City pursuant to B13.4 to avoid or mitigate  a Conflict of Interest; and

disqualify a Bidder if the Bidder, or one of their employees proposed for the Work, has a perceived, potential or actual Conflict of Interest that, in the City’s sole discretion, cannot be avoided or mitigated, or otherwise resolved.

The final determination of whether a perceived, potential or actual Conflict of Interest exists shall be made by the City, in their sole discretion.

Qualification

The Bidder shall:

undertake to be in good standing under The Corporations Act (Manitoba), or properly registered under The Business Names Registration Act (Manitoba), or otherwise properly registered, licensed or permitted by law to carry on business in Manitoba; and

be financially capable of carrying out the terms of the Contract; and

have all the necessary experience, capital, organization, and equipment to perform the Work in strict accordance with the terms and provisions of the Contract.

The Bidder and any proposed Subcontractor (for the portion of the Work proposed to be subcontracted to them) shall:

be responsible and not be suspended, debarred or in default of any obligations to the City.  A list of suspended or debarred individuals and companies is available on the Information Connection page at The City of Winnipeg, Corporate Finance, Purchasing Division website https://www.winnipeg.ca/matmgt/Templates/files/debar.pdf

The Bidder and/or any proposed Subcontractor (for the portion of the Work proposed to be subcontracted to them) shall:

have successfully carried out work similar in nature, scope and value to the Work; and

be fully capable of performing the Work required to be in strict accordance with the terms and provisions of the Contract; and

have a written workplace safety and health program if required pursuant to The Workplace Safety and Health Act (Manitoba);

have completed the Accessible Customer Service online training required by the Accessibility for Manitobans Act (AMA) (see B14.6 and C6.19).

^ SPEC NOTE Adjust open for acceptance dates in Form A clause 9.Time to allow sufficient time for clearances.  **for work within Winnipeg Police Services facilities, WPS requires a signed non-disclosure agreement signed by the successful Contractor.  upon request of the Contract Administrator, provide the Security Clearances in accordance with PART F -  ;

^SPEC NOTE: Identify any additional contract-specific qualification requirements for specialty contracts, e.g., a requirement that the bidder‘s proposed Supervisor have specific related experience.

The Bidder shall provide, in their Bid:

SPEC NOTE: Use B14.4 only if additional contract-specific submissions are required at the Submission Deadline to evaluate Bids and the inclusion of forms is not practical, e.g., audited financial statements.  Ensure that any and all such submissions are listed in B9.1 and must be evaluated.

^SPEC NOTE: Specify the form and content of the required submission(s) regarding qualifications, e.g., a résumé for the bidder’s proposed Supervisor.

^

SPEC NOTE: Use B14.5 for construction contracts estimated to exceed $100,000 in value or considered to be high risk.

Further to B14.3(c), the Bidder shall, within five (5) Business Days of a request by the Contract Administrator, provide proof satisfactory to the Contract Administrator that the Bidder/Subcontractor has a workplace safety and health program meeting the requirements of The Workplace Safety and Health Act (Manitoba), by providing:

Written confirmation of a safety and health certification meeting SAFE Work Manitoba’s SAFE Work Certified Standard (e.g., COR™ and SECOR™) in the form of:

a copy of their valid Manitoba COR certificate and Letter of Good Standing (or Manitoba equivalency) as issued under the Certificate of Recognition (COR) Program administered by the Construction Safety Association of Manitoba or by the Manitoba Heavy Construction Association’s WORKSAFELY™ COR™ Program; or

a copy of their valid Manitoba SECOR™ certificate and Letter of Good Standing (or Manitoba equivalency) as issued under the Small Employer Certificate of Recognition Program (SECOR™) administered by the Construction Safety Association of Manitoba or by the Manitoba Heavy Construction Association’s WORKSAFELY™ COR™ Program; or

a report or letter to that effect from an independent reviewer acceptable to the City.  A list of acceptable reviewers and the review template are available on the Information Connection page at The City of Winnipeg, Corporate Finance, Purchasing Division website at  http://www.winnipeg.ca/matmgt/Safety/default.stm.

Further to B14.3(d), the Bidder acknowledges that they and all Subcontractors have obtained training required by the Accessibility for Manitobans Act (AMA) available at https://accessibilitymb.ca/resources-events-and-training/online-training.html for anyone that may have any interaction with the public on behalf of the City of Winnipeg.

SPEC NOTE:  revise the number of days as required but be advised that the Contract Administrator MUST adhere to the number of days stated, without exception.

The Bidder shall submit, within three (3) Business Days of a request by the Contract Administrator, proof satisfactory to the Contract Administrator of the qualifications of the Bidder and of any proposed Subcontractor.

The Bidder shall provide, on the request of the Contract Administrator, full access to any of the Bidder's equipment and facilities to confirm, to the Contract Administrator’s satisfaction, that the Bidder's equipment and facilities are adequate to perform the Work.

Bid Security

The Bidder shall include in their Bid Submission bid security in the form of a digital bid bond, in the amount of at least ten percent (10%) of the Total Bid Price, and agreement to bond of a company registered to conduct the business of a surety in Manitoba, in Form G1: Bid Bond and Agreement to Bond, available at: https://www.winnipeg.ca/media/4929/

Bid security shall be submitted in a digital format meeting the following criteria:

The version submitted by the Bidder must have valid digital signatures and seals;

The version submitted by the Bidder must be verifiable by the City with respect to the totality and wholeness of the bond form, including: the content; all digital signatures and digital seals; with the surety company, or an approved verification service provider of the surety company.

The version submitted must be viewable, printable and storable in standard electronic file formats compatible with the City, and in a single file. Allowable formats include pdf.

The verification may be conducted by the City immediately or at any time during the life of the bond and at the discretion of the City with no requirement for passwords or fees.

The results of the verification must provide a clear, immediate and printable indication of pass or fail regarding B15.2(b).

Bonds failing the verification process will not be considered to be valid and the bid shall be determined to be non-responsive in accordance with B19.1(a).

Bonds passing the verification process will be treated as original and authentic.

If the Bidder submits alternative bids, the bid security shall be in the amount of the specified percentage of the highest Total Bid Price submitted.

The bid security of the successful Bidder and the next two lowest evaluated responsive and responsible Bidders will be released by the City when a Contract for the Work has been duly formed with the successful Bidder and the contract securities are furnished as provided herein.  The bid securities of all other Bidders will be released when a Contract is awarded.

The bid securities of all Bidders will be released by the City as soon as practicable following notification by the Contract Administrator to the Bidders that no award of Contract will be made pursuant to the Tender.

Opening of Bids and Release of Information

Bids will not be opened publicly.

Following the Submission Deadline, the names of the Bidders and their Total Bid Prices (unevaluated and pending review and verification of conformance with requirements) will be available on the MERX website at www.merx.com.

After award of Contract, the name(s) of the successful Bidder(s) and their Contract amount(s) will be available on the MERX website at www.merx.com.

The Bidder is advised that any information contained in any Bid may be released if required by The Freedom of Information and Protection of Privacy Act (Manitoba), by other authorities having jurisdiction, or by law or by City policy or procedures (which may include access by members of City Council).

To the extent permitted, the City shall treat as confidential information, those aspects of a Bid Submission identified by the Bidder as such in accordance with and by reference to Part 2, Section 17 or Section 18 or Section 26 of The Freedom of Information and Protection of Privacy Act (Manitoba), as amended.

Irrevocable Bid

The Bid(s) submitted by the Bidder shall be irrevocable for the time period specified in Paragraph 11 of Form A: Bid/Proposal.

The acceptance by the City of any Bid shall not release the Bids of the next two lowest evaluated responsive Bidders and these Bidders shall be bound by their Bids on such Work until a Contract for the Work has been duly formed and the contract securities have been furnished as herein provided, but any Bid shall be deemed to have lapsed unless accepted within the time period specified in Paragraph 11 of Form A: Bid/Proposal.

Withdrawal of Bids

A Bidder may withdraw their Bid without penalty at any time prior to the Submission Deadline.

Evaluation of Bids

Award of the Contract shall be based on the following bid evaluation criteria:

compliance by the Bidder with the requirements of the Tender, or acceptable deviation therefrom (pass/fail);

qualifications of the Bidder and the Subcontractors, if any, pursuant to B14 (pass/fail);

Total Bid Price;

economic analysis of any approved alternative pursuant to B8.

SPEC NOTE: Replace Total Bid Price with “evaluated Bid Price” where evaluation criteria will be used to add to or subtract from the Total Bid Price to reflect other costs.  Include any and all other criteria that will be used to evaluate Bids.

Further to B19.1(a), the Award Authority may reject a Bid as being non-responsive if the Bid is incomplete, obscure or conditional, or contains additions, deletions, alterations or other irregularities.  The Award Authority may reject all or any part of any Bid, or waive technical requirements or minor informalities or irregularities, if the interests of the City so require.

Further to B19.1(b), the Award Authority shall reject any Bid submitted by a Bidder who does not demonstrate, in their Bid or in other information required to be submitted, that they are qualified.

SPEC NOTE:  Delete B19.4 if NOT stating the available funds in Scope of Work D2.4.

Further to B19.1(c) the Award Authority may reject a Bid as being non-responsive if it exceeds the funds available as shown in D2.4.

VERSION 1 - Use this version with VERSION 1 of B11 and VERSION 1 of Form B: Prices for unit price contracts. If there is more than one line item, it is a unit price contract, not a lump sum contract.

Further to B19.1(c), the Total Bid Price shall be the sum of the quantities multiplied by the unit prices for each item shown on Form B: Prices.

Further to B19.1(a), in the event that a unit price is not provided on Form B: Prices, the City may determine the unit price by dividing the Amount (extended price) by the approximate quantity, for the purposes of evaluation and payment.

Where MRST is shown on Form B as a separate line item, if that Line item is not completed, the MRST shall be considered to be included in the Total Bid Price.

Bidders are advised that the calculation indicated in B19.5 will prevail over the Total Bid Price entered in MERX.

VERSION 2 - Use this version with VERSION 2 of B11 Lump Sum contract. If there is more than one line item or more than one quantity, it is a unit price contract, not a lump sum contract.

    - Further to B19.1(c), the Total Bid Price shall be the lump sum price entered into MERX.

VERSION 3 - Use this version with VERSION 3 of B11 and VERSION 3 of Form B: Prices for lump sum contracts with separate prices for adjustment purposes.  Revise B19.4(b) if using some criterion other than ”in the order listed in B11.2” to deduct separate prices.

SPEC NOTE: if including any of the deduction’s clauses, you must insert the clause “The funds available for this contract are $xxx.” under D2, Scope of Work

    - Further to B19.1(c), the Total Bid Price shall be the lump sum price shown on Form B: Prices adjusted, if necessary, as follows:

if the lowest evaluated responsive Bid submitted by a responsible and qualified Bidder is within the budgetary provision for the Work, no adjustment will be made to the lump sum price bid; or

if the lowest evaluated responsive Bid submitted by a responsible and qualified Bidder exceeds the budgetary provision for the Work, the lump sum prices of all responsive Bids submitted by responsible and qualified Bidders will be adjusted by progressively deducting separate prices in the order listed in B11.2 until a Total Bid Price within the budgetary provision is achieved, i.e., Total Bid Price = Lump Sum Price - Separate Price No. 1 - Separate Price No. 2 - ... - Separate Price No. ^last.

Bidders are advised that the Lump Sum Price indicated on Form B: Prices will prevail over the Total Bid Price entered in MERX.

VERSION 4 – Use this version with VERSION 1 of B11 and VERSION 1 of Form B:  Prices for unit price contracts.  This version allows for deductions until a Total Bid Price is within the budgetary provision.

SPEC NOTE: if including any of the deductions clauses, you must insert the clause “The funds available for this contract are $xxx.” under D2, Scope of Work

    - Further to B19.1(c), the Total Bid Price shall be the sum of the quantities multiplied by the unit prices for each item shown on Form B: Prices adjusted, if necessary, as follows:

if the lowest evaluated responsive Bid submitted by a responsible and qualified Bidder is within the budgetary provision for the Work, no adjustment will be made to the Total Bid Price; or

if the lowest evaluated responsive Bid submitted by a responsible and qualified Bidder exceeds the budgetary provision for the Work, the Total Bid Prices of all responsive Bids submitted by responsible and qualified Bidders will be adjusted by progressively deducting item(s) ^in numerals, ^ in numerals and ^ in numerals, in the order listed, until a Total Bid Price within the budgetary provision is achieved.

Further to B19.1(a), in the event that a unit price is not provided on Form B: Prices, the City may determine the unit price by dividing the Amount (extended price) by the approximate quantity, for the purposes of evaluation and payment.

Where MRST is shown on Form B as a separate line item, if that Line item is not completed, the MRST shall be considered to be included in the Total Bid Price.

Bidders are advised that the calculation indicated in B19.5 will prevail over the Total Bid Price entered in MERX.

SPEC NOTE: Use B19.5 only if there are alternatives identified in the Tender.  Identify alternatives on Form B: Prices and in the Specifications.  Evaluation criteria must be specified in B19.1.

The Contract may be awarded on the basis of:

Alternative 1 - ^description; or

Alternative 2 - ^description; or

Alternative 3 - ^description;

as identified on Form B: Prices.  Each alternative will be evaluated in accordance with the specified evaluation criteria.

Notwithstanding B11.1, the Bidder may, but is not required to, bid on all alternatives.

The City shall have the right to choose the alternative that is in their best interests.  If the Bidder has not bid on all alternatives, they shall have no claim against the City if their partial Bid is rejected in favour of an award of the Contract on the basis of an alternative upon which they have not bid.

Award of Contract

The City will give notice of the award of the Contract or will give notice that no award will be made.

The City will have no obligation to award a Contract to a Bidder, even though one or all of the Bidders are determined to be qualified, and the Bids are determined to be responsive.

Without limiting the generality of B20.2, the City will have no obligation to award a Contract where:

the prices exceed the available City funds for the Work;

the prices are materially in excess of the prices received for similar work in the past;

the prices are materially in excess of the City’s cost to perform the Work, or a significant portion thereof, with their own forces;

only one Bid is received; or

in the judgment of the Award Authority, the interests of the City would best be served by not awarding a Contract.

Spec Note: Delete B20.3 if not required or if fully funded under the Capital Budget.

The Work of this Contract is contingent upon Council approval of sufficient funding in the ^ Enter the Year    Capital Budget.  If the Capital Budget approved by Council does not include sufficient funding for the Work, the City will have no obligation to award a Contract.

SPEC NOTE: Delete B20.4 if 3rd Party Funding is confirmed.

If funding for the Work is provided to the City of Winnipeg by the Government of Manitoba and/or the Government of Canada, Bidders are advised that the terms of C24 shall immediately take effect upon confirmation of such funding, regardless of when funding is confirmed.

SPEC NOTE: B20.5 and B20.5.1 are the LAST two clauses in Award of Contract do NOT delete

Where an award of Contract is made by the City, the award shall be made to the qualified Bidder submitting the lowest evaluated responsive Bid, in accordance with B19.

Following the award of contract, a Bidder will be provided with information related to the evaluation of their Bid upon written request to the Contract Administrator.

SPEC NOTE: B20 Award of Contract must always be the last clause in the Bidding Procedures.

General Conditions

  - General Conditions

The General Conditions for Construction (Revision 2025 11 01) are applicable to the Work of the Contract.

The General Conditions for Construction are available on the Information Connection page at The City of Winnipeg, Corporate Finance, Purchasing Division website at http://www.winnipeg.ca/matmgt/gen_cond.stm

A reference in the Tender to a section, clause or subclause with the prefix “C” designates a section, clause or subclause in the General Conditions for Construction.

- Supplemental Conditions

General

General Conditions

In addition to the General Conditions for Construction, these Supplemental Conditions are applicable to the Work of the Contract.

Scope of Work

The Work to be done under the Contract shall consist of ^SPEC NOTE: Insert a concise description of the Work.

The major components of the Work are as follows:

SPEC NOTE: List the major components of the Work for the contract if they are not all evident from the description in D2.1.  Delete D2.2 if all major components of the Work are evident from the description.

^

^

- SPEC NOTE: Delete D2.3(a) if not required (buildings less than 500 sq. metres)

The following shall apply to the Services:

City of Winnipeg Green Building Policy: New City-Owned Buildings and major additions;

- http://clkapps.winnipeg.ca/DMIS/DocExt/ViewDoc.asp?DocumentTypeId=2&DocId=5989

Universal Design Policy

- http://clkapps.winnipeg.ca/DMIS/DocExt/ViewDoc.asp?DocumentTypeId=2&DocId=3604

SPEC NOTE: Delete D2.4 and  B19.4 if NOT stating the funds available or not utilizing the deduction clauses in B11.2 and B19. If available funds are NOT listed, a future non-award due to bids exceeding the available funds will violate the various trade agreements (undisclosed evaluation criteria) and the non-award must be approved by the CFO. Please make choice wisely.

    - The funds available for this contract are $^.

Definitions

SPEC NOTE: Include D3 only if it is necessary to define any words, phrases, acronyms or abbreviations used in the Tender with a meaning other than in common English usage or where the definition in C1.1 must be modified.

When used in this Tender:

SPEC NOTE: Define any words, phrases, acronyms or abbreviations used in the Tender with a meaning other than in common English usage and not defined in C1.1.

”^term” means ^definition;

”^term” means ^definition;

”^term” means ^definition.

Notwithstanding C1.1, when used in this Tender:

SPEC NOTE: Define any words, phrases, acronyms or abbreviations used in the Tender for which the meaning ascribed in C1.1 must be modified.

”^term” means ^definition;

”^term” means ^definition;

”^term” means ^definition;

”^term” means ^definition.

Contract Administrator

VERSION 1 - Use this version if the Contract Administrator is a company, e.g., consulting firm.  Insert the name of the company and the name, title, telephone number and email address of the individual representing the Contract Administrator.  The individual must be reasonably available throughout the bidding period.  Never name more than one person.

The Contract Administrator is ^company name, represented by:

^name

^title

Telephone No.	204 ^tel. no.

Email Address	^email address.

At the pre-construction meeting, ^name will identify additional personnel representing the Contract Administrator and their respective roles and responsibilities for the Work.

VERSION 2 - Use this version if the Contract administrator is an individual, e.g., City employee.  Insert name, title, department name, telephone number and email address of the City employee who is the Contract Administrator.  The Contract Administrator must be reasonably available throughout the bidding period.  Never name more than one person.

    - The Contract Administrator is:

^name

^title

Telephone No.	204 ^tel. no.

Email Address	^email address.

At the pre-construction meeting, the Contract Administrator will identify additional personnel representing the Contract Administrator and their respective roles and responsibilities for the Work.

Contractor's Supervisor

At the pre-construction meeting, the Contractor shall identify their designated supervisor and any additional personnel representing the Contractor and their respective roles and responsibilities for the Work.

Furnishing of Documents

Upon award of the Contract, the Contractor will be provided with ‘issued for construction’ Contract Documents electronically, including Drawings in PDF format only.

Submissions

Authority to Carry on Business

The Contractor shall be in good standing under The Corporations Act (Manitoba), or properly registered under The Business Names Registration Act (Manitoba), or otherwise properly registered, licensed or permitted by law to carry on business in Manitoba, or if the Contractor does not carry on business in Manitoba, in the jurisdiction where the Contractor does carry on business, throughout the term of the Contract, and shall provide the Contract Administrator with evidence thereof upon request.

Safe Work Plan

The Contractor shall provide the Contract Administrator with a Safe Work Plan at least five (5) Business Days prior to the commencement of any Work on the Site.

The Safe Work Plan should be prepared and submitted in the format shown in the City’s template which is available on the Information Connection page at The City of Winnipeg, Corporate Finance, Purchasing Division website at http://www.winnipeg.ca/matmgt/Safety/default.stm

SPEC NOTE: Delete D8.3 if deleting the COR requirements specified under B14 Qualifications.

Notwithstanding B14.5 at any time during the term of the Contract, the City may, at their sole discretion and acting reasonably, require an updated COR Certificate or Annual Letter of good Standing.  A Contractor, who fails to provide a satisfactory COR Certificate or Annual Letter of good Standing, will not be permitted to continue to perform any Work.

Insurance

SPEC NOTE:  Where 3rd Party Funding is confirmed, consult with the Insurance Branch at insurance@winnipeg.ca  for additional wording for wrap-up, builders’ risk etc. to be included in D9.

The Contractor shall provide and maintain the insurance coverage:

SPEC NOTE: Notwithstanding clauses will need to be added here. In consultation with the Insurance branch, increase the amount of liability coverage, if required for the Work.  Typically, $2,000,000 is adequate, however, on higher-risk contracts, a higher amount may be determined to be more appropriate by the Department.

commercial general liability insurance, in the amount of at least two million dollars ($2,000,000.00) inclusive, with The City of Winnipeg added as an additional insured, with a cross-liability clause, contractual liability, unlicensed motor vehicle liability (contractor’s equipment), non-owned automobile liability and products and completed operations endorsement, to remain in place at all times during the performance of the Work and throughout the Warranty period;

if applicable, Automobile Liability Insurance covering all motor vehicles, owned and operated and used or to be used by the Contractor directly or indirectly in the performance of the Work.  The Limit of Liability shall not be less than $2,000,000 inclusive for loss or damage including personal injuries and death resulting from any one accident or occurrence.

SPEC Note: Use D9.1(c) only for contracts which involve the construction of or renovations to a structure (building, bridge, etc.).

all risks course of construction insurance in the amount of one hundred percent (100%) of the total Contract Price, written in the name of the Contractor and The City of Winnipeg, at all times during the performance of the Work and until the date of Total Performance.

SPEC NOTE:  Complex projects and all projects over five million ($5,000,000) should be vetted through the Insurance Branch, as unique requirements or increased limits may be necessary and/or Owner Controlled Insurance (purchased by the City) may be warranted.  Example of possible additions:  Certificate to state “operations to include blasting/hazardous material handling/asbestos/mould removal/ etc”.

Deductibles shall be borne by the Contractor.

All policies shall be taken out with insurers licensed to carry on business in the Province of Manitoba.

The Contractor shall provide:

The certificate of insurance, in a form satisfactory to the Supervisor of Insurance, to:

- The City of Winnipeg

- Risk Management

- Insurance Section

- 185 King Street, 3rd Floor

- Winnipeg, MB R3B 1J1

The Contract Administrator with a copy of the certificate of insurance.

- At least two (2) Business Days of notification of the award of the Contract prior to the commencement of any Work on the Site.

The Contractor shall not cancel, materially alter, or cause each policy to lapse without providing at least thirty (30) Calendar Days prior written notice to the Supervisor of Insurance.

SPEC NOTE: On large projects, designated by the Insurance Branch, the City may elect to provide, or have the Contractor provide, Construction Wrap-Up Insurance for the Work.  In such cases, a statement to that effect shall replace these clauses.

Contract Security

The Contractor shall provide and maintain the performance bond and the labour and material payment bond until the expiration of the warranty period in the form of:

a performance bond of a company registered to conduct the business of a surety in Manitoba, in the amount of fifty percent (50%) of the Contract Price; and

labour and material payment bond of a company registered to conduct the business of a surety in Manitoba, in an amount equal to fifty percent (50%) of the Contract Price.

Bonds are available at:

Performance Bond https://www.winnipeg.ca//media/4928/

Performance Bond – Schedule A - Form of Notice https://www.winnipeg.ca/media/4831/

Performance Bond – Schedule B – Surety’s Acknowledgement  https://www.winnipeg.ca/media/4832/

Performance Bond – Schedule C – Surety’s Position https://www.winnipeg.ca/media/4833/

Labour & Material Payment Bond https://www.winnipeg.ca//media/4930/

L&M Bond – Schedule A – Notice of Claim

- https://www.winnipeg.ca/media/4834/

L&M Bond – Schedule B – Acknowledgement of a Notice

- https://www.winnipeg.ca/media/4835/

L&M Bond – Schedule C – Surety’s Position

- https://www.winnipeg.ca/media/4836/

Where the contract security is a performance bond, it may be submitted in hard copy or digital format.  If submitted in digital format the contract security must meet the following criteria:

      - the version submitted by the Contractor must have valid digital signatures and seals;

the version submitted by the Contractor must be verifiable by the City with respect to the totality and wholeness of the bond form, including: the content; all digital signatures and digital seals; with the surety company, or an approved verification service provider of the surety company.

the version submitted must be viewable, printable and storable in standard electronic file formats compatible with the City, and in a single file. Allowable formats include pdf.

the verification may be conducted by the City immediately or at any time during the life of the bond and at the discretion of the City with no requirement for passwords or fees.

the results of the verification must provide a clear, immediate and printable indication of pass or fail regarding D10.1(b).

Digital bonds failing the verification process will not be considered to be valid and may be determined to be an event of default in accordance with C18.1.  If a digital bond fails the verification process, the Contractor may provide a replacement bond (in hard copy or digital format) within seven (7) Calendar Days of the City’s request or within such greater period of time as the City in their discretion, exercised reasonably, allows.

Digital bonds passing the verification process will be treated as original and authentic.

The Contractor shall provide:

the required Contract Security to:

- The City of Winnipeg

- Legal Services Department

- 185 King Street, 3rd Floor

- Winnipeg, MB R3B 1J1

The Contract Administrator with copies of the required Contract Security.

- within seven (7) Calendar Days of notification of the award of the Contract and prior to the commencement of any Work on the Site.

The Contractor shall, as soon as practicable after entering into a contract with a Subcontractor:

give the Subcontractor written notice of the existence of the labour and material payment bond in D10.1(b); and

post a notice of the bond and/or a copy of that bond in a conspicuous location at the Site of the Work.

Detailed Prices

SPEC NOTE: Use D11 only where a detailed price breakdown is required for administrative purposes, e.g., progress payments, and Form I: Detailed Prices is included in the Tender.

The Contractor shall provide the Contract Administrator with a detailed price breakdown (Form I: Detailed Prices) at least two (2) Business Days prior to the commencement of any Work on the Site.

The Contractor shall state a price for each item or sub-item of the Work identified on Form I: Detailed Prices.  The detailed prices must be consistent with the price(s) provided in the Contractor’s Bid.

Subcontractor List

SPEC NOTE: Use D12 only if the names of Subcontractors are required for administrative purposes, e.g.,(a)	if Subcontractors for key portions of the Work were named in the Bid, to confirm that no unapproved substitutions have been made;

(b)	to confirm that no Subcontractors are suspended or debarred;

(c)	if the City is providing wrap-up insurance for the project, to provide the Insurance Branch with necessary information;

(d)	if persons other than the Contractor are responsible for security or access control for the Site, to identify who is authorized to access the Site.

Include Form J: Subcontractors List.

The Contractor shall provide the Contract Administrator with a complete list of the Subcontractors whom the Contractor proposes to engage (Form J: Subcontractor List) at least two (2) Business Days prior to the commencement of any Work on the Site.

Equipment List

SPEC NOTE: Use D13 only where an equipment list is required for administrative purposes and Form K: Equipment List is included in the Tender.

The Contractor shall provide the Contract Administrator with a complete list of the equipment which the Contractor proposes to utilize (Form K: Equipment List) at least two (2) Business Days prior to the commencement of any Work on the Site.

Detailed Work Schedule

SPEC NOTE: Use D14 only where a detailed work schedule is required for administrative purposes.

VERSION 1 - Use this version if Form L: Detailed Work Schedule is provided in the Tender. Form L must be consistent with D16, D19, D20, D21 & D22..

The Contractor shall provide the Contract Administrator with a detailed work schedule (Form L: Detailed Work Schedule) at least two (2) Business Days prior to the commencement of any Work on the Site.

VERSION 2 - Use this version if Form L: Detailed Work Schedule is not provided in the Tender.

    - The Contractor shall provide the Contract Administrator with a detailed work schedule at least two (2) Business Days prior to the commencement of any Work on the Site.

^SPEC NOTE: Identify any other conditions under which the Contractor will be permitted or required to adjust the schedule.

The detailed work schedule shall consist of the following:

SPEC NOTE: Specify the format for the detailed work schedule.

a critical path method (C.P.M.) schedule for the Work;

a Gantt chart for the Work based on the C.P.M. schedule;

a daily manpower schedule for the Work;

^;

all acceptable to the Contract Administrator.

Further to D14.2(a), the C.P.M. schedule shall clearly identify the start and completion dates of all of the following activities/tasks making up the Work as well as showing those activities/tasks on the critical path.

SPEC NOTE: Identify:

(a)	the minimum list of activities/tasks to be included in the, e.g., the commencement date, Substantial Performance and Total Performance dates, milestone dates for critical stages of the Work, interim milestone dates, etc.;

(b)	type(s) of schedule, e.g., C.P.M., Gantt, time-scaled-logic, etc.;

(c)	format, e.g., computer generated schedule type such as Prima Vera with a computer disk file copy provided to the Contract Administrator;

(d)	amount of detail, e.g., if the Contractor can only be able to reasonably provide a detailed schedule for first 1-3 months of the contract, ask for detailed information in first part of schedule and less detail for remainder, with further detail to follow within a specified time period.

Further to D14.2(b), the Gantt chart shall show the time on a weekly basis, required to carry out the Work of each trade, or specification division.  The time shall be on the horizontal axis, and the type of trade shall be on the vertical axis.

Further to D14.2(c), the daily manpower schedule shall list the daily number of individuals on the Site for each trade.

Requirement for Site Accessibility Plan

SPEC NOTE: Delete if not applicable to this Work.

The Contractor shall provide the Contract Administrator with an Accessibility Plan at least five (5) Business Days prior to the commencement of any Work on the Site.

The Accessibility Plan shall demonstrate how the Contractor will accommodate the safe passage of pedestrians and cyclists in accordance with the Manual of Temporary Traffic Control, the Contract Drawings, Staging Plans, and Streets By-Law No. 1481/77 at all times for the duration of the Construction. Unless noted in the Contract, the Accessibility Plan must include a written plan for the following:

      - How the Contractor will maintain at least one crossing in each direction for each intersection (one north/south crosswalk and one east/west crosswalk).

      - How the Contractor will maintain access to bus stops within the site.

      - How the Contractor will maintain access to pedestrian corridors and half signals.

      - How the Contractor will maintain cycling facilities.

      - How the Contractor will maintain access to residents and businesses unless otherwise noted in the Contract.

      - Any required detour signage at adjacent crossings to facilitate sidewalk or active transportation pathway closures.

The Accessibility Plan may also include figures, sketches, or drawings to demonstrate the proposed plan.

The Accessibility Plan shall include written details on how the Contractor intends to review, maintain, and document all items related to the Accessibility Plan on-site during Construction, including, but not limited to:

      - Signage

      - Temporary Ramping

      - Transit Stops

      - Detour Signage

At minimum, the Contractor shall review the site conditions on a daily basis to ensure that all features related to the Accessibility Plan are in place. The site review is intended to correct deficiencies as a result of unforeseen events such as wind, traffic, or the general public. Deficiencies that are direct result of the Contractors actions must be corrected immediately.

Any changes to the Accessibility Plan must be approved by the Contract Administrator.

Upon request from the Contract Administrator, the Contractor shall provide records demonstrating that the site has been maintained.

Deficiencies as a direct result of actions by the Contractor that are not immediately corrected and/or failure to produce records that demonstrate that the site was maintained in compliance with the Accessibility Plan may result in a pay adjustment via the monthly Progress Payment. The rate of pay adjustment will be as per the following schedule:

      - First Offence – A warning will be issued and documented in the weekly or bi-weekly site meeting.

      - Second Offence - A field instruction to immediately correct the site will be issued by the Contract Administrator.

Third and subsequent Offences – A pay reduction will be issued in the amount of $250.00 per instance and per day.

Schedule of Work

Commencement

The Contractor shall not commence any Work until they are in receipt of an award letter from the Award Authority authorizing the commencement of the Work.

SPEC NOTE: Delete any unnecessary items between D16.2(a)(ii) andD16.2(a)(ix).  Add any other submissions or documents required after award but before commencement of the Work on the Site.

The Contractor shall not commence any Work on the Site until:

the Contract Administrator has confirmed receipt and approval of:

evidence of authority to carry on business specified in D7;

evidence of the workers compensation coverage specified in C6.17;

the Safe Work Plan specified in D8;

evidence of the insurance specified in D9;

evidence of the contract security specified in D10;

the detailed prices specified in D11;

the Subcontractor list specified in D12;

the equipment list specified in D13;

the detailed work schedule specified in D14;

the Requirement for Site Accessibility Plan in D15; and

the direct deposit application form specified in C12.20

the Contractor has attended a pre-construction meeting with the Contract Administrator, or the Contract Administrator has waived the requirement for a pre-construction meeting.

^SPEC NOTE: Add any other conditions to be met by the Contractor after award but before commencement of the Work on the Site.

VERSION 1 - Use this version if the Contractor is required to commence the Work on the Site a specified number of days following award of the Contract.  Revise the number and type of days to suit the contract, e.g., allow fourteen (14) Business Days.

The Contractor shall commence the Work on the Site within seven (7) Working Days of receipt of the award letter.

VERSION 2 - Use this version where the Contractor is not allowed to commence the Work on the Site until a fixed date due to impediments such as weather conditions, inability to access the Site, etc.

    - The Contractor shall not commence the Work on the Site before ^month day, year.

SPEC NOTE:  Use D16.4 only if the Contractor is required to complete the Work on the Site by a specified date and the number of days for acceptance of the offer in Form A makes the time period for completion of the Work unreasonable.  E.g. if the Submission Deadline is April 15, the time period for acceptance is 60 Calendar Days, and the Work requires completion by June 17, the Contractor would technically have 3 Calendar Days to complete the project.

The City intends to award this Contract by ^month day, year.

SPEC NOTE: Delete the wording “Critical Stages” from D16.4.1 if not using D19 Critical Stages.

If the actual date of award is later than the intended date, the dates specified for Commencement, Critical Stages, Substantial Performance, and Total Performance will be adjusted by the difference between the aforementioned intended and actual dates.

Work By Others

SPEC NOTE:  Use D17 only if there is work to be done by others that is anticipated to be done concurrently with the Work of the Contract.  List known work to be done by others.  Consider utilities, other Civic Department, etc.  Ex. Manitoba Hydro installing temporary overhead street lighting, Manitoba Hydro Gas Div. lowering gas services or Geomatics doing monument referencing that is not arranged by the Contractor.  Include as much detail as is known, i.e. time frames, commencement/completion dates.  Work by others that must be completed prior to the Work or a portion of the Work of the Contract should be stated in D17.2.

Further to C6.26, the Contractor’s attention is directed to the fact that other Contractors, the personnel of Utilities and the staff of the City may be working within the project limit, approach roadway, adjacent roadways or right-of-way. The activities of these agencies may coincide with the Contractors execution of Work and it will be the Contractor’s responsibility to cooperate to the fullest extent with other personnel working in the area, and such cooperation is an obligation of the Contractor under the terms of Contract.

Work by others on or near the Site will include but not necessarily be limited to:

^;

^.

Further to D17.1 the Contractor shall cooperate and coordinate all activities with all parties performing required Work by Others identified in D17.1 and accommodate the necessary area on Site required for the Work by Others to complete the Work

Working Days

SPEC NOTE: Use D17 only if the Work Schedule is based on Working Days and there are two or more major classes of Work for which the definition of a Working Day may be applied differently.

Further to C1.1(xx), the Contract Administrator’s determination of whether or not atmospheric and Site conditions are such that a Working Day is deemed to have elapsed may be based at one time on one type of work while at another time a Working Day may be based on another type of work.  When more than one type of major work is involved, the quantity of equipment that must be able to work in order to meet the requirements of a Working Day may vary considerably from that specified in the General Conditions.

In the event that incidental work is behind schedule which, in the opinion of the Contract Administrator, should have been or could have been carried out by the Contractor in conjunction with or immediately following work of a major type, the City hereby reserves the right to charge Working Days on the incidental work until such time as it is up to schedule.

When the major type of work involves restoration of the site to the condition it was prior to rainfall, Working Days shall not be charged.

The Contract Administrator will furnish the Contractor with a daily record for each major type of work showing various information concerning the equipment, the time it worked, could have worked and Working Days charged.  This report is to be signed each day by an authorized representative of the Contractor.

Critical Stages

SPEC NOTE: Use D19 only if critical stages of the Work, other than Substantial Performance and/or Total Performance, must be achieved in accordance with a specified schedule.

The Contractor shall achieve critical stages of the Work in accordance with the following requirements:

^Specify the critical stages and the schedule required.

^

^

Substantial Performance

VERSION 1 - Use this version to specify the number of Working Days for Substantial Performance.  Insert the number of Working Days allowed.

The Contractor shall achieve Substantial Performance within ^number (^n) consecutive Working Days of the commencement of the Work as specified in D16.

When the Contractor considers the Work to be substantially performed, the Contractor shall arrange, attend and assist in the inspection of the Work with the Contract Administrator for purposes of verifying Substantial Performance.  Any defects or deficiencies in the Work noted during that inspection shall be remedied by the Contractor at the earliest possible instance and the Contract Administrator notified so that the Work can be reinspected.

The date on which the Work has been certified by the Contract Administrator as being substantially performed to the requirements of the Contract through the issue of a certificate of Substantial Performance is the date on which Substantial Performance has been achieved.

VERSION 2 - Use this version to specify a fixed date for Substantial Performance.  Insert the month, day and year.

    - The Contractor shall achieve Substantial Performance by ^month day, year.

When the Contractor considers the Work to be substantially performed, the Contractor shall arrange, attend and assist in the inspection of the Work with the Contract Administrator for purposes of verifying Substantial Performance.  Any defects or deficiencies in the Work noted during that inspection shall be remedied by the Contractor at the earliest possible instance and the Contract Administrator notified so that the Work can be reinspected.

The date on which the Work has been certified by the Contract Administrator as being substantially performed to the requirements of the Contract through the issue of a certificate of Substantial Performance is the date on which Substantial Performance has been achieved.

Total Performance

VERSION 1 - Use this version to specify the number of Working Days for Total Performance.  Insert the number of Working Days allowed.  The number of Working Days must be greater than the number of Working Days specified in Version 1 of  D20.1 for Substantial Performance.

The Contractor shall achieve Total Performance within ^number (^n) consecutive Working Days of the commencement of the Work as specified in D16.

When the Contractor or the Contract Administrator considers the Work to be totally performed, the Contractor shall arrange, attend and assist in the inspection of the Work with the Contract Administrator for purposes of verifying Total Performance.  Any defects or deficiencies in the Work noted during that inspection shall be remedied by the Contractor at the earliest possible instance and the Contract Administrator notified so that the Work can be reinspected.

The date on which the Work has been certified by the Contract Administrator as being totally performed to the requirements of the Contract through the issue of a certificate of Total Performance is the date on which Total Performance has been achieved.

VERSION 2 - Use this version to specify a fixed date for Total Performance.  Insert the month, day and year.  The date must be later than the date specified in Version 2 of D20.1 for Substantial Performance.

    - The Contractor shall achieve Total Performance by ^month day, year.

- SPEC NOTE: add the following to D21.1 if required or within ^ days if seasonal inclement weather does not allow permanent restorations to commence immediately after Substantial Performance, whichever comes first.  The Contract Administrator will advise the Contractor when seasonal conditions will allow permanent restorations to begin.  The Contractor will start final restorations no later than 14 (fourteen) Calendar Days after formal notification by the Contract Administrator

When the Contractor or the Contract Administrator considers the Work to be totally performed, the Contractor shall arrange, attend and assist in the inspection of the Work with the Contract Administrator for purposes of verifying Total Performance.  Any defects or deficiencies in the Work noted during that inspection shall be remedied by the Contractor at the earliest possible instance and the Contract Administrator notified so that the Work can be reinspected.

The date on which the Work has been certified by the Contract Administrator as being totally performed to the requirements of the Contract through the issue of a certificate of Total Performance is the date on which Total Performance has been achieved.

Liquidated Damages

VERSION 1 - Use this version if liquidated damages are to be assessed if the Contractor does not achieve Substantial Performance within the number of Working Days or by the fixed date specified in D20.  Insert the amount of Liquidated Damages in terms of dollars per Working Day (if D20 is based on Working Days) or Calendar Day (if D20 is based on a fixed date).  Ensure that a breakdown of the costs is prepared and available to substantiate the specified amount.  Liquidated damages may not be deleted unless approved in writing by the Manager of Purchasing.

If the Contractor fails to achieve Substantial Performance in accordance with the Contract by the day fixed herein for Substantial Performance, the Contractor shall pay the City ^amount dollars ($^n) per Working Day [Calendar Day] for each and every Working Day [Calendar Day] following the day fixed herein for Substantial Performance during which such failure continues.

The amount specified for liquidated damages in D22.1 is based on a genuine pre-estimate of the City's damages in the event that the Contractor does not achieve Substantial Performance by the day fixed herein for same.

The City may reduce any payment to the Contractor by the amount of any liquidated damages assessed.

VERSION 2 - Use this version if liquidated damages are to be assessed if the Contractor does not achieve Total Performance within the number of Working Days or by the fixed date specified in D21.  Insert the amount of Liquidated Damages in terms of dollars per Working Day (if D21 is based on Working Days) or Calendar Day (if D21 is based on a fixed date).  Ensure that a breakdown of the costs is prepared and available to substantiate the specified amount.  Liquidated damages may not be deleted unless approved in writing by the Manager of Purchasing.

    - If the Contractor fails to achieve Total Performance in accordance with the Contract by the day fixed herein for Total Performance, the Contractor shall pay the City ^amount dollars ($^n) per Working Day [Calendar Day] for each and every Working Day [Calendar Day] following the day fixed herein for Total Performance during which such failure continues.

The amount specified for liquidated damages in D22.1 is based on a genuine pre-estimate of the City's damages in the event that the Contractor does not achieve Total Performance by the day fixed herein for same.

The City may reduce any payment to the Contractor by the amount of any liquidated damages assessed.

VERSION 3 - Use this version if liquidated damages are to be assessed if the Contractor does not achieve critical stages, Substantial Performance or Total Performance within the number of Working Days or by the fixed dates specified in D19, D20, and D21 respectively.  Identify critical stages exactly as identified in D19.  Insert the amount of Liquidated Damages for each critical stage, Substantial Performance and Total Performance in terms of dollars per Working Day (if the schedule was based on Working Days) or Calendar Day (if the schedule was based on fixed dates).  Ensure that a breakdown of the costs is prepared and available to substantiate the specified amounts.  Liquidated damages may not be deleted unless approved in writing by the Manager of Purchasing.

    - If the Contractor fails to achieve Critical Stages, Substantial Performance or Total Performance in accordance with the Contract by the days fixed herein for same, the Contractor shall pay the City the following amounts per Working Day [Calendar Day] for each and every Working Day [Calendar Day] following the days fixed herein for same during which such failure continues:

^critical stage - ^amount dollars ($^n);

^critical stage - ^amount dollars ($^n);

^critical stage - ^amount dollars ($^n);

^critical stage - ^amount dollars ($^n);

Substantial Performance - ^amount dollars ($^n);

Total Performance - ^amount dollars ($^n).

The amounts specified for liquidated damages in D22.1 are based on a genuine pre-estimate of the City's losses in the event that the Contractor does not achieve critical stages, Substantial Performance or Total Performance by the days fixed herein for same.

The City may reduce any payment to the Contractor by the amount of any liquidated damages assessed.

Scheduled Maintenance

SPEC NOTE: Use D23 only if scheduled maintenance by the Contractor is required (e.g., watering, weed control and cutting of grass until established).  For each item of scheduled maintenance, provide a concise description (typically the specification clause heading) and a specification reference.

The Contractor shall perform the following scheduled maintenance in the manner and within the time periods required by the Specifications:

^description as specified in ^cross reference;

^description as specified in ^cross reference;

^description as specified in ^cross-reference.

Determination of Substantial Performance and Total Performance shall be exclusive of scheduled maintenance identified herein.  All scheduled maintenance shall be completed prior to the expiration of the warranty period.  Where the scheduled maintenance cannot be completed during the warranty period, the warranty period shall be extended for such period of time as it takes the Contractor to complete the scheduled maintenance.

Control of Work

Job Meetings

SPEC NOTE: Use D24 only if regular job meetings are required.  Change “weekly” to any suitable time interval.  Use the phrases ", one representative of the City" and “, the City” only where the Contract Administrator is not an employee of the City.

Regular weekly job meetings will be held at the Site.  These meetings shall be attended by a minimum of one representative of the Contract Administrator, one representative of the City and one representative of the Contractor.  Each representative shall be a responsible person capable of expressing the position of the Contract Administrator, the City and the Contractor respectively on any matter discussed at the meeting including the Work schedule and the need to make any revisions to the Work schedule.  The progress of the Work will be reviewed at each of these meetings.

The Contract Administrator reserves the right to cancel any job meeting or call additional job meetings whenever they deem it necessary.

Prime Contractor – The Workplace Safety and Health Act (Manitoba)

SPEC NOTE: Include D25 when there is a construction project site, the Contractor will be responsible for the project site, and more than one employer or self employed person may be involved in work at the project site at the same time.  Otherwise, the City, as owner of the project site, may have the duties of the prime contractor with respect to compliance with WSHA.  If the City is acting as the prime contractor for a project (very rare), do not include D25.

Further to C6.27, the Contractor shall be the Prime Contractor and shall serve as, and have the duties of the Prime Contractor in accordance with The Workplace Safety and Health Act (Manitoba).

The Workplace Safety and Health Act (Manitoba) – Qualifications

Further to B14.5, the Contractor/Subcontractor must, throughout the term of the Contract, have a Workplace Safety and Health Program meeting the requirements of The Workplace Safety and Health Act (Manitoba). At any time during the term of the Contract, the City may, at their sole discretion and acting reasonably, require updated proof of compliance, as set out in B14.5.

Responsibility for Plant and Materials

SPEC NOTE: Use D26 only where the City is prepared to assume risk and responsibility for Plant and/or Material.  Identify the appropriate condition which will terminate this responsibility, e.g., replace “until the Plant is removed from the Site” with “Substantial Performance” or “Total Performance”.

Further to C10, the City shall assume the risk of and responsibility for the following Plant from the time that the City delivers the Plant to the Site until the Plant is removed from the Site:

^SPEC NOTE: List Plant.

Further to C10, the City shall assume the risk of and responsibility for the following Material from the time that the City delivers the Material to the Site until the Material is incorporated in the Work or is removed from the Site:

^SPEC NOTE: List Material.

Payment

- SPEC NOTE: delete D28 if not including Cash Allowances

Payment

    - Further to E6, no payment will be made for Cash Allowances other than as set out in E6.4.

Payment Schedule

SPEC NOTE: Use D29 only if payment is not based on progress estimates pursuant to C12 or where the City is willing to pay for material (e.g., mechanical components, structural components, custom manufactured fabrications) before it is incorporated into the Work (e.g., 50% payment on manufacture and transfer of title to the City, 25% payment on delivery, 25% payment on Total Performance). Any Payment Schedule where funds are paid prior to total completion of Work shall be approved by the Chief Financial Officer PRIOR to the tender/rfp/rfq being issued.

Further to C12, payment shall be in accordance with the following payment schedule:

^SPEC NOTE: Provide payment schedule.

^

Warranty

Warranty

VERSION 1 – Use this version to accept the standard warranty clause listed in the General Conditions.

Warranty is as stated in C13.

VERSION 2 - Use this version only if the warranty period will commence upon the date of Total Performance but the warranty period is not one year.  Insert the appropriate time period, e.g., two (2) years for bridge contracts.

    - Notwithstanding C13.2, the warranty period shall begin on the date of Total Performance and shall expire two (2) years thereafter unless extended pursuant to C13.2.1 or C13.2.2, in which case it shall expire when provided for thereunder.

SPEC NOTE: Use D30.2 only if the warranty period will be permitted to commence prior to Total Performance where certain conditions are met.

Notwithstanding C13.2 or D30.1, the Contract Administrator may permit the warranty period for a portion or portions of the Work to begin prior to the date of Total Performance if:

a portion of the Work cannot be completed because of unseasonable weather or other conditions reasonably beyond the control of the Contractor but that portion does not prevent the balance of the Work from being put to its intended use.

SPEC NOTE: List the contract-specific conditions under which the Department will permit the warranty period to commence prior to Total Performance.

In such case, the date specified by the Contract Administrator for the warranty period to begin shall be substituted for the date specified in C13.2 for the warranty period to begin.

- SPEC NOTE: Specify any special warranties which will apply to specific items of Work (e.g., special manufacturer’s warranties on Material.

VERSION 3 - Use this version only if the warranty period will commence upon the date of Substantial Performance.  Increase the warranty period if necessary.

    - Notwithstanding C13.2, the warranty period shall begin on the date of Substantial Performance and shall expire one (1) year thereafter unless extended pursuant to C13.2.1 or C13.2.2, in which case it shall expire when provided for thereunder.

SPEC NOTE: Use D30.4 only if the warranty period will be permitted to commence prior to Substantial Performance where certain conditions are met.

Notwithstanding C13.2 or D30.3, the Contract Administrator may permit the warranty period for a portion or portions of the Work to begin prior to the date of Substantial Performance if:

a portion of the Work cannot be completed because of unseasonable weather or other conditions reasonably beyond the control of the Contractor but that portion does not prevent the balance of the Work from being put to its intended use.

SPEC NOTE: List the contract-specific conditions under which the Department will permit the warranty period to commence prior to Total Performance.

In such case, the date specified by the Contract Administrator for the warranty period to begin shall be substituted for the date specified in C13.2 for the warranty period to begin.

- SPEC NOTE: Specify any special warranties which will apply to specific items of Work (e.g., special manufacturer’s warranties on Material.

VERSION 4 - Use this version only if there is no change to the basic warranty but the warranty period will be permitted to commence prior to Total Performance where certain conditions are met.

Notwithstanding C13.2, the Contract Administrator may permit the warranty period for a portion or portions of the Work to begin prior to the date of Total Performance if:

a portion of the Work cannot be completed because of unseasonable weather or other conditions reasonably beyond the control of the Contractor but that portion does not prevent the balance of the Work from being put to its intended use.

- SPEC NOTE: List the contract-specific conditions under which the Department will permit the warranty period to commence prior to Total Performance.

In such case, the date specified by the Contract Administrator for the warranty period to begin shall be substituted for the date specified in C13.2 for the warranty period to begin.

- SPEC NOTE: Specify any special warranties which will apply to specific items of Work (e.g., special manufacturer’s warranties on Material.

VERSION 5 - Use this version only if there is no change to the basic warranty but longer warranties for some items are specified in the Specifications.

    - Notwithstanding C13.2, the warranty period shall begin on the date of Total Performance and shall expire one (1) year thereafter, except where longer warranty periods are specified in the respective Specification sections, unless extended pursuant to C13.2.1 or C13.2.2, in which case it shall expire when provided for thereunder.

For the purpose of contract security, the warranty period shall be one (1) year.

Notwithstanding C13.2, the Contract Administrator may permit the warranty period for a portion or portions of the Work to begin prior to the date of Total Performance if a portion of the Work cannot be completed because of unseasonable weather or other conditions reasonably beyond the control of the Contractor but that portion does not prevent the balance of the Work from being put to its intended use.

In such case, the date specified by the Contract Administrator for the warranty period to begin shall be substituted for the date specified in C13.2 for the warranty period to begin.

Indemnity

Indemnity

Indemnity shall be as stated in C17.

SPEC NOTE: Use Form I: Detailed Prices only if using D11.  Identify each item of the Work for which it is necessary to know detailed prices to control payments.

| Form I: Detailed Prices (See D11) Click or tap here to enter text. |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| ITEM NO. | DESCRIPTION | SPEC. REF. | UNIT | APPROX. QUANTITY | UNIT PRICE | AMOUNT |

SPEC NOTE: Use Form J: Subcontractors only if using D12.

Form J: Subcontractor List (See D12) Click or tap here to enter text.

Name Address ____________________________________________________________________________________ ____________________________________________________________________________________ ____________________________________________________________________________________ ____________________________________________________________________________________ ____________________________________________________________________________________ ____________________________________________________________________________________ ____________________________________________________________________________________ ____________________________________________________________________________________ ____________________________________________________________________________________ ____________________________________________________________________________________ ____________________________________________________________________________________ ____________________________________________________________________________________ ____________________________________________________________________________________ ____________________________________________________________________________________ ____________________________________________________________________________________ ____________________________________________________________________________________ ____________________________________________________________________________________ ____________________________________________________________________________________ ____________________________________________________________________________________ ____________________________________________________________________________________ ____________________________________________________________________________________ ____________________________________________________________________________________ ____________________________________________________________________________________

SPEC NOTE: Use Form K: Equipment List only if using D13.  Identify each key category or type of equipment for which it is necessary to have information to control the Work.  Modify the form to obtain the information required for each category or type of equipment.  Copy sufficient lines for the Contractor to enter information for the required number of pieces.

Form K: Equipment (See D13) Click or tap here to enter text.

- Category/type: SPEC NOTE: Identify category or type of equipment. Make/Model/Year: _____________________________________ Serial No.: ___________________________ Registered owner: _________________________________________________________________________ Make/Model/Year: _____________________________________ Serial No.: ___________________________ Registered owner: _________________________________________________________________________ Make/Model/Year: _____________________________________ Serial No.: ___________________________ Registered owner: _________________________________________________________________________

- Category/type: SPEC NOTE: Identify category or type of equipment. Make/Model/Year: _____________________________________ Serial No.: ___________________________ Registered owner: _________________________________________________________________________ Make/Model/Year: _____________________________________ Serial No.: ___________________________ Registered owner: _________________________________________________________________________ Make/Model/Year: _____________________________________ Serial No.: ___________________________ Registered owner: _________________________________________________________________________

- Category/type: SPEC NOTE: Identify category or type of equipment. Make/Model/Year: _____________________________________ Serial No.: ___________________________ Registered owner: _________________________________________________________________________ Make/Model/Year: _____________________________________ Serial No.: ___________________________ Registered owner: _________________________________________________________________________ Make/Model/Year: _____________________________________ Serial No.: ___________________________ Registered owner: _________________________________________________________________________

- Category/type: SPEC NOTE: Identify category or type of equipment. Make/Model/Year: _____________________________________ Serial No.: ___________________________ Registered owner: _________________________________________________________________________ Make/Model/Year: _____________________________________ Serial No.: ___________________________ Registered owner: _________________________________________________________________________ Make/Model/Year: _____________________________________ Serial No.: ___________________________ Registered owner: _________________________________________________________________________

- Category/type: SPEC NOTE: Identify category or type of equipment. Make/Model/Year: _____________________________________ Serial No.: ___________________________ Registered owner: _________________________________________________________________________ Make/Model/Year: _____________________________________ Serial No.: ___________________________ Registered owner: _________________________________________________________________________ Make/Model/Year: _____________________________________ Serial No.: ___________________________ Registered owner: _________________________________________________________________________

- Category/type: SPEC NOTE: Identify category or type of equipment. Make/Model/Year: _____________________________________ Serial No.: ___________________________ Registered owner: _________________________________________________________________________ Make/Model/Year: _____________________________________ Serial No.: ___________________________ Registered owner: _________________________________________________________________________ Make/Model/Year: _____________________________________ Serial No.: ___________________________ Registered owner: _________________________________________________________________________

SPEC NOTE: Use Form L: Detailed Work Schedule only if using D14.  Identify each key item of Work for which it is necessary to know the schedule to control the Work.

VERSION 1 - Use this version where the work schedule is based on Working Days.

| Form L: Detailed Work Schedule (See D14) Click or tap here to enter text. |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| For each item of Work, indicate the cumulative percentage proposed to be completed by the end of each time period until 100% completion is achieved. |  |  |  |  |  |  |
| Items of Work | Time Period in Working Days |  |  |  |  |  |
|  | 0 | 10 | 20 | 30 | 40 | 50 |
| SPEC NOTE: Identify items of Work. |  |  |  |  |  |  |

VERSION 2 - Use this version where the work schedule is based on fixed dates.

| Form L: Detailed Work Schedule (See D14) Click or tap here to enter text. |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| For each item of Work, indicate the proposed date that each cumulative percentage to be completed will be achieved. |  |  |  |  |  |
| Items of Work | Percentage of Work Completed |  |  |  |  |
|  | Start | 25% | 50% | 75% | 100% |
| SPEC NOTE: Identify items of Work. |  |  |  |  |  |

Specifications

General

Applicable Specifications and Drawings

These Specifications shall apply to the Work.

SPEC NOTE: Use E1.2 only if some or all of the Standard Construction Specifications apply.

The City of Winnipeg Standard Construction Specifications in their entirety, whether or not specifically listed on Form B: Prices, shall apply to the Work.

The City of Winnipeg Standard Construction Specifications is available on the Information Connection page at The City of Winnipeg, Corporate Finance, Purchasing Division website at http://www.winnipeg.ca/matmgt/Spec/Default.stm .

The version in effect three (3) Business Days before the Submission Deadline shall apply.

Further to C2.4(d), Specifications included in the Tender shall govern over The City of Winnipeg Standard Construction Specifications.

SPEC NOTE: All specified proprietary goods/services (mfr, brand, model) must be approved as a single source prior to posting, unless requests for substitutes will be considered in accordance with B8”

A link to the manufacturer’s specifications or a copy of the manufacturer’s specifications must be provided in the Tender document

Bidders are reminded that requests for approval of substitutes as an approved equal or an approved alternative shall be made in accordance with B8. In every instance where a brand name or design specification is used, the City will also consider approved equals and/or approved alternatives in accordance with B8.

The following are applicable to the Work:

SPEC NOTE: List all specifications, provided as separate documents, which apply.  Do not list the Standard Construction Specifications (already listed above).  Do not list specifications included within this document.

| Specification No. | Specification Title |  |
| --- | --- | --- |
|  | Table of Contents All pages, including Table of Contents or Index (if provided) must be listed. A Table of Contents or Index does not require a Specification No. |  |
| NMS Specifications |  |  |
| Division 01 – |  | General Requirements |
| 0103300 |  | Procedures |
| 014500 |  | Quality Control |
| Division 02 – |  | Existing Conditions |
| 022800 |  | Asbestos Abatement |
| Division 03 – |  | Concrete |
| Division 04 – |  | Masonry |
| 040499 |  | Masonry for Minor Works |
| Division 05 – |  | Metals |

SPEC NOTE: List all drawings which apply.

| Drawing No. | Drawing Name/Title |
| --- | --- |
|  | Cover Sheet All drawings, including cover sheets must be listed. Cover sheets do not have to be numbered. |

Soils Investigation Report

SPEC NOTE: Use E2 only if soils investigation information exists.  Disclose and include all geotechnical reports in this clause.

Further to C3.1,

General Requirements

Office Facilities

SPEC NOTE: Use E3 only if the Contractor is required to supply office facilities at the job site and/or at any location where material requiring inspection is being manufactured.  Requirements should include only basic office space, furnishings and services such as desks, chairs, tables, file cabinets, light, heat, water and telephone.  Requirements should not include consumable supplies, computers, facsimile machines or cellular telephones.

The Contractor shall supply office facilities meeting the following requirements:

^SPEC NOTE: Identify the requirements for each facility.

Hazardous Materials

SPEC NOTE: If using E3 Hazardous Materials, ensure that the proper insurance coverage clauses are in place in D9   The Contract Administrator must get the proper insurance requirements from the City/Contracts Officer and impose that on the Contractor/subcontractor.

If asbestos or other hazardous materials are encountered during the Work of the Contract, the Contractor shall stop all work and notify the Contract Administrator immediately.  Removal of hazardous materials shall be dealt with by the City and the Contractor shall await further instruction by the Contract Administrator.

Mobilization and Demobilization Payment

SPEC NOTE: Use E5 in combination with the line item in Form B: Prices. If not using E5, delete the line item in the Form B and vice-versa. This clause is meant to cover fixed expenses per contract such as bonding and insurance. Consult with City Project Manager for further direction on their use.

Description

This Specification shall govern mobilization and demobilization from site.

SPEC NOTE: reminder to add Mobilization and Demobilization to your Form B Prices if applicable

    - Measurement and Payment

Mobilization and Demobilization

      - Mobilization and demobilization will be measured on a lump sum basis and paid for at the Contract Lump Sum Price for “Mobilization and Demobilization”. Payment for Mobilization and demobilization shall include all costs associated with mobilization and demobilization, site set up, and cleanup. Payment will be made on the following schedule:

      - 25% payment of the Mobilization and Demobilization lump sum price will be paid once sewer cleaning and preparation crews arrive on site and commence with cleaning and sewer preparation works.

      - 50% payment of the Mobilization and Demobilization lump sum price will be paid once lining crews arrive on site and commence CIPP liner installations.

      - 100% of the Mobilization and Demobilization lump sum price will be paid subsequent to completion of the liner installation, liner repairs (if necessary), and site cleanup.

Cash Allowance for Additional Work

SPEC NOTE: delete if Cash Allowance is not applicable or modify as needed

    - Additional Work may be necessitated due to unforeseen circumstances that may arise during the course of the project due to:

      - Additions to the scope of Work by the Contract Administrator, beyond that defined herein.

    - A cash allowance has been included on Form B: Prices. SPEC NOTE: Reminder to include a Cash Allowance line item on Form B: Prices

    - The City reserves the right to delete any or all of the Cash Allowance from the Contract if the Work intended to be covered by the Cash Allowance is not required, or if the Works intended are found to be more extensive than the provisional Cash Allowance.

    - Cost of additional work shall be evaluated by the methods outlined in C7.4, and a Change Order prepared by the Contract Administrator. Cost of the Change Order will be paid on the Progress Estimate and deducted from the Cash Allowance. If the valuation of the authorized work exceeds the Value of the Cash Allowance, the Contract Value will be adjusted by the shortfall.

    - Additional services and/or Work will not be initiated for:

      - Reasons of lack of performance or errors in execution.

      - Scheduling changes initiated by the City, where at least 24 hours’ notice is given prior to the Contractors schedule time to be on Site.

    - Should it be determined that additional material or services are required, the Contract Administrator shall approve the Work, prior to commencement of the additional Work.

    - Material Mark-Up Factors in accordance with C7:

      - The base cost is to be the wholesale cost of the material, regardless of the Contractor or Subcontractor supplying the material.

      - In general, the party (Contractor or Subcontractor) supplying the material is the party that purchases the material from a supplier who does not perform any work on Site, unless otherwise determined by the Contract Administrator.

      - Where the Contractor is supplying the material, the mark-up on the material is limited to fifteen percent (15%).

      - Where the Contractor’s immediate Subcontractor is supplying the material the total mark-up on the material including all Subcontractors and the Contractor is limited to twenty-five percent (25%)

        - The Subcontractor’s mark-up on the material is limited to fifteen percent (15%);

        - The Contractor’s mark-up on the material is limited to ten percent (10%).

      - A Third-Level Subcontractor is a Subcontractor of a Subcontractor of the Contractor.

        - No Third-Level Subcontractors on this project are approved for additional mark-up.

In the event that a Third-Level Subcontractor is utilized, that is not approved for additional mark-up, the Contractor is responsible for coordinating the split of the maximum approved mark-up between the Contractor and Subcontractors.

Traffic Control

- E7.1	In accordance with the Manual of Temporary Traffic Control on City Streets (MTTC), the Contract Administrator shall make arrangements with the Traffic Services Branch of the City of Winnipeg to place, maintain, and remove all regulatory signs and traffic control devices authorized and/or required by the Traffic Management Branch in the following situations:

      - Parking restrictions,

      - Stopping restrictions,

      - Turn restrictions,

      - Diamond lane removal,

      - Full or directional closures on a Regional Street,

      - Traffic routed across a median,

      - Full or directional closure of a non-regional street where there is a requirement for regulatory signs (turn restrictions, bus stop relocations, etc.) to implement the closure.

      - Approved Designated Construction Zones with a temporary posted speed limit reduction. Traffic Services will be responsible for placing all of the advance signs and 'Construction Ends' (TC-4) signs. The Contractor is still responsible for all other temporary traffic control including but not limited to barricades, barrels and tall cones.

- E7.2	Further to (c), the Contractor shall make arrangement with the Traffic Services Branch of the City of Winnipeg to supply regulatory signs as required.

- E7.3	Upon request from the Contract Administrator, the Contractor shall provide records demonstrating that the Site has been maintained.

- E7.4	Further to E7(c) and E7(d) the Contractor shall make arrangements with the Traffic Services Branch of the City of Winnipeg to reinstall the permanent regulatory signs after the Contract Work is complete. At this time the Contractor shall make arrangements to drop off the stockpiled materials to Traffic Services at 495 Archibald Street.

- E7.5	Any changes to the approved traffic management plan must be submitted to the Contract Administrator a minimum of (five) 5 Working Days prior to the required change for approval.

If the Contract Administrator determines that the Contractor is not performing Traffic Control in accordance with this specification, Traffic Services Branch may be engaged to perform the Traffic Control. In this event the Contractor shall bear the costs associated charged to the project by the Traffic Services Branch of the City of Winnipeg in connection with the required Works undertaken by the Contractor.

^

^

Security Clearance

Security Clearance

SPEC NOTE: Use 1 only if necessary, e.g., work in security area, work requires interaction with public.

DO NOT USE P-608 form for version 1.  Form P-608 to be used only for version 2 and for work within Winnipeg Police Service facilities.

VERSION 1 - Use this version for locations other than Winnipeg Police Stations or Service Centres.  Adjust bid validity dates in Form A to allow sufficient time for clearances.  Walk-ins to the Winnipeg Police Service currently requires 6 -8 weeks for processing and then mails the certificate  For 2017 online Police Information Check is available and may take approx. one week.

Version 1.1 – Use this version of F1.1 if all individuals performing any work under the contract must obtain a security clearance.

Each individual proposed to perform Work under the Contract shall be required to obtain a Police Information Check from the police service having jurisdiction at their place of residence.  This can be obtained from one of the following;

police service having jurisdiction at their place of residence; or

Sterling BackCheck – for existing account holders, log into your account to send individual invitations to employees requiring security clearance.  For those that do not have an account, click on the following link to open an account:  https://forms.sterlingbackcheck.com/partners/platform2-en.php?&partner=winnipegcity ; or

Commissionaires (Manitoba Division), forms to be completed can be found on the website at: https://www.commissionaires.ca/en/manitoba/home ; or

Fastcheck Criminal Record & Fingerprint Specialists, forms to be completed can be found on the website at: https://myfastcheck.com

SPEC NOTE: Use F1.2  and F1.2.1 only if the work reasonably requires contact with vulnerable persons (under 18 years of age and/or due to age, disability or other circumstances, dependent on others or at a greater risk of harm than the general population from a person in a position of authority or trust).

The Vulnerable Sector screening can ONLY be obtained from the police service having jurisdiction at their place of residence.  Sterling BackCheck, Core of Commissionaires and FASTCHECK do not perform Vulnerable Sector searches.

The following is a link to information for obtaining the Police Information Check including the Vulnerable Sector screening from the City of Winnipeg Police Service.  http://winnipeg.ca/police/pr/PIC.stm

The Police Information Check shall include a Vulnerable Sector Screening.  This can be obtained by following the link below http://winnipeg.ca/police/pr/PIC.stm    .

Individuals will need to state in the form, that they may be working in City of Winnipeg pools, libraries and community centres;

The original Police Information Check (Form P–612) will be provided by the Winnipeg Police Service to the individual applicant.  The original has a validation sticker from the Winnipeg Police Service in the top right hand corner.  The applicant shall:

Provide the original Police Information Check (Form P–612) to the Contract Administrator.

SPEC NOTE:   The Contract Administrator must take a photocopy of the original Police Information Check and sign it as a true copy and then return the original to the individual.

Prior to the award of Contact, and during the term of the Contract if additional or replacement individuals are proposed to perform Work, the Bidder/Contractor shall supply the Contract Administrator with a Police Information Check obtained not earlier than one (1) year prior to the Submission Deadline, or a certified true copy thereof, for each individual proposed to perform the Work.

Any individual for whom a Police Information Check is not provided, or for whom a Police Information Check indicates any convictions or pending charges related to property offences or crimes against another person will not be permitted to perform any Work.

Any Police Information Check obtained thereby will be deemed valid for the duration of the Contract subject to a repeated records search as hereinafter specified.

Notwithstanding the foregoing, at any time during the term of the Contract, the City may, at their sole discretion and acting reasonably, require an updated Police Information Check.  Any individual who fails to provide a satisfactory Police Information Check as a result of a repeated Police Information Check will not be permitted to continue to perform any Work.

Version 1.2 – Use this version of F1.1 if only individuals performing work in certain locations or under certain conditions, or performing certain tasks, must obtain a security clearance.

    - Each individual proposed to perform the following portions of the Work:

SPEC NOTE: Add or delete locations, conditions, tasks and/or exceptions thereto, e.g., consider deleting F1.1(b)(ii) for a contract involving work in a playground in use.

      - any Work on private property;

any Work within City facilities other than:

an underground structure such as a manhole;

in areas and at times normally open to the public;

^;

communicating with residents and homeowners in person or by telephone;

^;

^;

Each Individual shall be required to obtain a Police Information Check from the police service having jurisdiction at their place of residence. Or

Sterling BackCheck – for existing account holders, log into your account to send individual invitations to employees requiring security clearance.  For those that do not have an account, click on the following link to open an account:  https://forms.sterlingbackcheck.com/partners/platform2-en.php?&partner=winnipegcity; or

Commissionaires (Manitoba Division), forms to be completed can be found on the website at: https://www.commissionaires.ca/en/manitoba/home; or

FASTCHECK Criminal Record & Fingerprint Specialists, forms to be completed can be found on the website at: https://myfastcheck.com

SPEC NOTE: Use 1.2 and 1.2.1 only if the work reasonably requires contact with vulnerable persons (under 18 years of age and/or due to age, disability or other circumstances, dependent on others or at a greater risk of harm than the general population from a person in a position of authority or trust).

The Vulnerable Sector screening can ONLY be obtained from the police service having jurisdiction at their place of residence.  Sterling BackCheck, Core of Commissionaires and FASTCHECK do not perform Vulnerable Sector searches.

The following is a link to information for obtaining the Police Information Check from the City of Winnipeg Police Service.  http://winnipeg.ca/police/pr/PIC.stm

The Police Information Check shall include a Vulnerable Sector Screening.  This can be obtained by following the link below  http://winnipeg.ca/police/pr/PIC.stm

Individuals will need to state in the form, that they may be working in City of Winnipeg pools, libraries and community centres;

The original Police Information Check (Form P–612) will be provided by the Winnipeg Police Service to the individual applicant.  The original has a validation sticker from the Winnipeg Police Service in the top right hand corner.  The applicant shall:

Provide the original Police Information Check (Form P–612) to the Contract Administrator.

SPEC NOTE:   The Contract Administrator must take a photocopy of the original Police Information Check and sign it as a true copy and then return the original to the individual.

Prior to the award of Contact, and during the term of the Contract if additional or replacement individuals are proposed to perform Work, the Bidder/Contractor shall supply the Contract Administrator with a Police Information Check obtained not earlier than one (1) year prior to the Submission Deadline, or a certified true copy thereof, for each individual proposed to perform such Work.

Any individual for whom a Police Information Check is not provided, or for whom a Police Information Check indicates any convictions or pending charges related to property offences or crimes against another person will not be permitted to perform any Work specified in F1.1.

Any Police Information Check obtained thereby will be deemed valid for the duration of the Contract subject to a repeated records search as hereinafter specified.

Notwithstanding the foregoing, at any time during the term of the Contract, the City may, at their sole discretion and acting reasonably, require an updated Police Information Check.  Any individual who fails to provide a satisfactory Police Information Check as a result of a repeated Police Information Check will not be permitted to continue to perform any Work specified in F1.1.

SPEC NOTE: Use 1.8 to 1.12 only if the work reasonably requires contact with children.  Use F1.1 above.

Each individual proposed to perform the following portions of the Work:

SPEC NOTE: Identify locations or conditions of Work, and/or specific tasks.

      - ^;

^;

^;

shall be required to obtain a Child Abuse Registry check from the Manitoba Child Abuse Registry.

Prior to the award of Contact, and during the term of the Contract if additional or replacement individuals are proposed to perform Work, the Bidder/Contractor shall supply the Contract Administrator with a satisfactory Child Abuse Registry Self-Check – Information and Results obtained not earlier than one (1) year prior to the Submission Deadline, or a certified true copy thereof, for each individual proposed to perform such Work.

Any individual for whom a Child Abuse Registry result is not provided, or for whom a Child Abuse Registry result indicates the subject is listed on the Manitoba Child Abuse Registry, will not be permitted to perform any Work specified in F1.1.

Any Child Abuse Registry result obtained thereby will be deemed valid for the duration of the Contract subject to a repeated Child Abuse Registry check as hereinafter specified.

    - Notwithstanding the foregoing, at any time during the term of the Contract, the City may, at their sole discretion and acting reasonably, require an updated Child Abuse Registry check.  Any individual who fails to provide a satisfactory Child Abuse Registry result as a result of a repeated Child Abuse Registry check will not be permitted to continue to perform any Work specified in F1.1.

Version 1.3 – Use this version of F.1.1 if only individuals performing work in certain locations or under certain conditions, or performing certain tasks, must obtain a Police Information Check and a Safety Verification Check.

SPEC NOTE: For Water and Waste Department Use ONLY Any work within facilities associated with the water supply, treatment and distribution system including the Shoal Lake Intake Facility, Shoal Lake Aqueduct, Deacon Reservoir, Water Treatment Plant, Regional Pumping Stations, and Booster Pumping Stations requires an Additional Security Check = The Safety Verification Check.  This is to be obtained through BackCheck.  Add as an (i) Contact Ron Risley at 204-986-3758 if you have any questions regarding the Safety Verification.

SPEC NOTE:  Sterling Talent Solutions provide the BackCheck Service for the Police Information Check/ Criminal Record Check and/or the Global Sanctions & PEP Checks.

    - Each individual proposed to perform Work under this Contract within facilities associated with the water supply, treatment and distribution system including the Shoal Lake Intake Facility, Shoal Lake Aqueduct, Deacon Reservoir, Water Treatment Plant, Regional Pumping Stations, and Booster Pumping Stations shall be required to obtain a Global Sanctions & PEP Check and a Police Information Check as detailed below.

          - The Global Sanctions & PEP Check must be obtained through Sterling BackCheck.

            - A Sterling BackCheck account must be setup 72 hours prior to individual security clearances to allow sufficient time for activation of the contracting company’s account.  If the contracting company has an existing City of Winnipeg Sterling Backcheck vendor account, they may skip to (d) below.

            - An authorized individual of the contracting company must complete the Sterling Backcheck Setup Form. There is no cost to the organization to set up the account. Click on the link below, complete the form, and hit submit. **(This form is to be completed by the company, not by the employee requiring the security clearances).  https://forms.sterlingbackcheck.com/partners/platform2-en.php?&partner=winnipegcity

            - Within 48 hours of completing the Sterling Backcheck Setup Form, the authorized individual of the contracting company will receive a Username and Password for Sterling Backcheck. It will appear in their inbox as a “Welcome to Sterling Backcheck” email. Upon receipt, the authorized individual of the contracting company will be asked to login to the Sterling Backcheck website to set their security questions and password. Once completed, individual security clearance requests can be submitted.

            - In order to run a Global Sanctions & PEP Check and/or a Police Information Check, follow the steps below:

              - Click on the sub-tab labelled “Order eConsent”.

              - Fill out the required information about the employee proposed to perform Work under this Contract within City facilities (the person that requires the security clearances).

              - Select your location under the “Order Information” section and enter the organization’s phone number, if required.

              - Select the required individual service(s) in the dropdown menu under the “Select Services” section. If both the Global Sanctions & PEP Check and the Police Information Check are required, select the Sterling Backcheck Package One (with electronic identity verification). Once selected, both the Global Sanctions & PEP Check and the Police Information Check should have a grey check mark beside them.

              - Scroll down to the bottom and click the blue “Submit” button. The employee proposed to perform Work under this Contract within City facilities will be invited to complete their security clearance.

              - The employee will receive the invitation and must click on the link and complete their Global Sanctions & PEP Check and/or Police Information Check.

              - The results of the Global Sanctions & PEP Check and/or Police Information Check will go directly to the City of Winnipeg and to the authorized individual of the contracting company within 24 hours.

            - Any questions related to the Sterling BackCheck process can be directed to Linda Ferens at 204-999-0912 or by email at: linda.ferens@sterlingcheck.com OR managedsupport@sterlingcheck.com

          - The Police Information Check must be obtained from one of the following:

            - Sterling BackCheck;

              - See F1.1.1(a) thru (e) for instructions on how to set up an account and submit individuals for security checks; or

            - A police service having jurisdiction at their place of residence;

              - The original Police Information Check (Form P–612) will be provided by the Winnipeg Police Service to the individual applicant.  The original has a validation sticker from the Winnipeg Police Service in the top right hand corner.

              - The applicant shall provide the original Police Information Check (Form P–612) to the Contract Administrator; or

            - Commissionaires (Manitoba Division);

              - Forms to be completed can be found on the website at: https://www.commissionaires.ca/en/manitoba/home

              - The applicant shall provide the original Police Information Check to the Contract Administrator; or

            - FASTCHECK Criminal Record & Fingerprint Specialists;

              - Forms to be completed can be found on the website at: https://myfastcheck.com

              - The applicant shall provide the original Police Information Check to the Contract Administrator.

SPEC NOTE:   The Contract Administrator must take a photocopy of the original Police Information Check and sign it as a true copy and then return the original to the individual.

Any individual for whom a Global Sanctions & PEP Check and/or a Police Information Check is not provided will not be permitted to perform any Work.

Individuals for whom a Global Sanctions & PEP Check indicates “CLEAR” and a Police Information Check demonstrates no previous convictions or pending charges will be permitted to perform Work as specified in F1.1.

Individuals for whom a Global Sanctions & PEP Check does not indicate “CLEAR” and/or a Police Information Check demonstrates previous convictions or pending charges may not be permitted to perform any Work as specified in F1.1.

Previous convictions or pending charges may be investigated and a determination will be made by the City as to whether the individual will be permitted to perform any Work.

Convictions or pending charges that may preclude an individual from performing any Work include but are not limited to:

convictions or pending charges related to property offences; and/or

convictions or pending charges related to crimes against another person.

Where additional investigation related to a Global Sanctions & PEP Check or a Police Information Check is required by the City, no extension to critical stages, Substantial Performance, or Total Performance, as applicable, will be provided.

Additional investigation by the City may take upwards of six weeks.

Prior to the award of Contract, and during the term of the Contract, if additional or replacement individuals are proposed to perform Work within City facilities, the Bidder/Contractor shall supply the Contract Administrator with a Global Sanctions & PEP Check and a Police Information Check satisfactory to the City obtained not earlier than one (1) year prior to the Submission Deadline, or a certified true copy thereof, for each individual proposed to perform the Work.

Any Global Sanctions & PEP Check and Police Information Check determined to be satisfactory to the City will be deemed valid for the duration of the Contract subject to a repeated records search as hereinafter specified.

Notwithstanding the foregoing, at any time during the term of the Contract, the City may, at their sole discretion and acting reasonably, require an updated Global Sanctions & PEP Check and/or a Police Information Check.  Any individual F1.1 who fails to provide a Global Sanctions & PEP Check and/or a Police Information Check satisfactory to the City as a result of a repeated records search will not be permitted to continue to perform any Work as specified in F1.1.

VERSION 2 - Use this version for ANY Work to be performed at Winnipeg Police Service Buildings or Stations. If you have any questions or concerns regarding Police security clauses, contact the Manager of Services, Abdul Aziz at AAziz@winnipeg.ca.

VERSION 2.1 - Use Level One security for Site Investigations only at any Winnipeg Police Service Building or Stations (to be used in combination with version 2.2. If a site investigation is not required, delete version 2.1.

Security Clearance for Site Investigations at Winnipeg Police Service Buildings or Stations

    - The City will conduct a Level One Security Clearance Check for:

      - owner(s), members of the Board of Directors and persons with controlling interest in the company; and

      - any individual proposed to perform Work under the Contract for the Winnipeg Police Service.

    - Each individual listed in F1.1 shall submit the required information and form to the Winnipeg Police Service Division 30 Security Section Supervisor at Main Floor, 245 Smith Street;

      - A completed Form P-608: Security Clearance Check authorization form available at https://www.winnipeg.ca/matmgt/templates/information.stm#securitycheck.  Form P-608 must be signed and dated. (only page 1 of P-608 required for Level One)

    - Any company for whom a satisfactory Level One Security Clearance is not obtained for any individual proposed to do the Work, all owner(s), member(s) of the Board of Directors, and persons with controlling interest in the company will not be allowed to attend the Site Investigation and will not be qualified for award of Contract.

Any satisfactory Security Clearance obtained thereby will be deemed valid for one (1) year from the date of clearance.

      - Each individual attending the Site Investigation for Winnipeg Police Service Buildings or Stations shall provide photo identification upon entry, in order that their Level One security clearance can be verified.

    - If a person fails a Winnipeg Police Service security clearance check at any level, they will not be able to apply for another clearance for 2 years.

VERSION 2.2 Use Level Two security for ANY Work being performed for Winnipeg Police Service Buildings or Stations. (if a site investigation is not required delete version 2.1 above

Security Clearance for Work at Winnipeg Police Service Buildings or Stations

    - The City will conduct a Level Two Security Clearance Check for:

      - owner(s), members of the Board of Directors and persons with controlling interest in the company; and

      - any individual proposed to perform Work under the Contract for the Winnipeg Police Service.

    - The Bidder/Contractor shall provide the Contract Administrator with:

      - a list of individuals identified in F1.1:

        - in the case of additional or replacement individuals during the term of the Contract, at least thirty (30) Calendar Days before they assume their controlling role within the company or are proposed to commence Work for the Winnipeg Police Service.

      - A completed Form P-608: Security Clearance Check authorization form available at https://www.winnipeg.ca/matmgt/templates/information.stm#securitycheck .  Form P-608 must be signed and dated.

        - Signature of Witness shall be signed by the contact person stated on Paragraph 3 of Form A: Bid/Proposal.

Each individual shall submit the required information and form to the Winnipeg Police Service Division 30 Security Section Supervisor at Main Floor, 245 Smith Street:

      - in the case of an additional or replacement individual during the term of the Contract, at least thirty (30) Calendar Days before they assume their controlling role within the company or are proposed to commence Work for the Winnipeg Police Service.

Any company for whom a satisfactory Level Two Security Clearance is not obtained for all owner(s), member(s) of the Board of Directors; and persons with controlling interests in the company will not be qualified for award of Contract.

Any individual proposed to do the Work for whom a satisfactory Level Two Security Clearance is not obtained will not be permitted to perform any Work for Winnipeg Police Service.

Any satisfactory Security Clearance obtained thereby will be deemed valid for one (1) year from the date of clearance, subject to a repeated Security Clearance Check as hereinafter specified.

Each individual doing Work in a Winnipeg Police Service Facility shall provide photo identification upon entry, in order that their Level Two security clearance can be verified.

    - Notwithstanding the foregoing, at any time during the term of the Contract, the City may, at their sole discretion and acting reasonably, require a further Security Clearance Check.

          - The Contract will be terminated with any Contractor should any owner(s), member(s) of the Board of Directors; or persons with controlling interest in the company fail to obtain a satisfactory Security Clearance Check as a result of a repeated Security Clearance Check.

          - Any individual who fails to obtain a satisfactory Security Clearance Check as a result of a repeated Security Clearance Check will not be permitted to continue to perform Work under the Contract for the Winnipeg Police Service.

    - If a person fails a Winnipeg Police Service security clearance check at any level, they will not be able to apply for another clearance for 2 years.