THE CITY OF WINNIPEG

TENDER

TENDER NO. Click or tap here to enter text.

Click or tap here to enter text.

Contract Title (maximum 80 characters & although appears in uppercase only the first letter of each word should be typed uppercase & subsequent letters of each word in lowercase)

DO NOT USE TRACK CHANGES OR MARKUP.

IT WILL OVER RIDE THE FORMATTING AND YOUR DOCUMENT WILL BE UNUSABLE

SPEC NOTE: Replace the ^ between the bookmark brackets [ ] with; a) the Tender No. ( nnnn-yyyy for PurTrac numbers) and b) the Contract Title.  Then update fields (click Print Preview) to update all references to the Tender No. and Contract Title.

SPEC NOTE: Do not use hard returns ( ¶ ) within the Contract Title.

Sample Contract Titles: Regional > Plessis Road – Dugald Road to PTH #1, Asphalt Overlay and Sidewalk Construction.

Residential > Residential Streets Renewal Program, Magnus Avenue, Sinclair Street, and various other locations (list first two locations or the two most significant locations)

Residential with Provincial funding > Province of Manitoba/City of Winnipeg 2004 Residential Street Renewals, Part 1 – Enfield Crescent and Various Other Locations, Part 2 – Harrowby Avenue and Various Other Locations (list first two locations or the two most significant locations)

SPEC NOTE: All clauses included in this template are mandatory and may not be deleted or modified unless approved in writing by the Manager of Purchasing.

SPEC NOTE: Where a Spec Note is provided, modifications may only be made in accordance with the Spec Note, unless approved in writing by the Manager of Purchasing.

*** SPEC NOTE: If there are any funding agreements related to a Tender, then the Contract Administrator should review the funding agreement to ensure that the General Conditions include clauses to ensure compliance with the funding agreement, particularly in the areas of Insurance, Indemnity, Document Retention and Third Party Contract requirements.  The Contract Administrator should consult with Legal Services, to ensure the General Conditions wording aligns with the applicable funding agreement and the potential for a new Supplemental Conditions by submitting a Legal Service Request to Legal Service Request Form with the proposed wording included.

Version 2025 11 01- Const Road Works

TABLE OF CONTENTS

SPEC NOTE: The Table of Contents is automatically generated.  When the template is first opened, page numbers may be incorrect.  To update, right click anywhere in the field (shaded area) and select Update Field, Update entire table.  Prior to printing, select > File > Print Preview, to update all field codes, bookmarks and cross-references.

PART A - BID SUBMISSION

Form A: Bid/Proposal

Form B: Prices

Form G1: Bid Bond and Agreement to Bond

PART B - BIDDING PROCEDURES

B1.	Contract Title	1

B2.	Submission Deadline	1

B3.	Site Investigation	1

B4.	Enquiries	1

B5.	Confidentiality	2

B6.	Addenda	2

B7.	Substitutes	2

B8.	Bid Components	3

B9.	Bid	4

B10.	Prices	4

B11.	Disclosure	5

B12.	Conflict of Interest and Good Faith	5

B13.	Qualification	6

B14.	Bid Security	7

B15.	Opening of Bids and Release of Information	8

B16.	Irrevocable Bid	8

B17.	Withdrawal of Bids	9

B18.	Evaluation of Bids	9

B19.	Award of Contract	10

PART C - General Conditions

C0.	General Conditions	1

PART D - SUPPLEMENTAL CONDITIONS

General

D1.	General Conditions	1

D2.	Scope of Work	1

D3.	Definitions	2

D4.	Contract Administrator	2

D5.	Contractor's Supervisor	2

D6.	Furnishing of Documents	3

Submissions

D7.	Authority to Carry on Business	3

D8.	Safe Work Plan	3

D9.	Insurance	3

D10.	Contract Security	4

D11.	Subcontractor List	5

D12.	Equipment List	5

D13.	Detailed Work Schedule	5

D14.	Requirements for Site Accessibility Plan	6

Schedule of Work

D15.	Commencement	7

D16.	Working Days	8

D17.	Restricted Work Hours	8

D18.	Work By Others	8

D19.	Sequence of Work	9

D20.	Critical Stages	10

D21.	Substantial Performance	10

D22.	Total Performance	11

D23.	Liquidated Damages	11

D24.	Scheduled Maintenance	12

Control of Work

D25.	Job Meetings	12

D26.	Prime Contractor – The Workplace Safety and Health Act (Manitoba)	12

D27.	The Workplace Safety and Health Act (Manitoba) – Qualifications	13

Payment

D28.	Payment	13

D29.	Payment Schedule	13

D30.	Fuel Price Adjustment	13

Warranty

D31.	Warranty	14

Indemnity

D32.	Indemnity	14

Form J: Subcontractor List	15

Form K: Equipment	16

Form L: Detailed Work Schedule	18

Form L: Detailed Work Schedule	19

Form L: Detailed Work Schedule	20

PART E - SPECIFICATIONS

General

E1.	Applicable Specifications and Drawings	1

E2.	Mobilization and Demobilization Payment	2

E3.	Cash Allowance for Additional Work	3

E4.	Geotechnical Report	4

E5.	Office Facilities	4

E6.	Protection Of Existing Trees	4

E7.	Traffic Control	5

E8.	Traffic Management	6

E9.	Refuse and Recycling Collection	7

E10.	Pedestrian Safety	7

E11.	Water Obtained From the City	8

E12.	Surface Restorations	8

E13.	Infrastructure Signs	8

E14.	Patching of Existing Pavement	8

E15.	Supply and Installation of Pavement Repair Fabric	9

E16.	Partial Depth Patching of Existing Joints	10

E17.	Salt Tolerant Grass Seeding	11

E18.	Portland Cement Concrete Sidewalk With Block Outs For Indicator Surfaces	12

E19.	Paving Stones for Indicator Surfaces	13

E20.	Supply and Install Watermain and Water Service Insulation	14

E21.	Mix Design Proportion	15

E22.	^	16

- BIDDING PROCEDURES

Contract Title

Click or tap here to enter text.

SPEC NOTE: The Contract Title will reflect the bookmark entry made on the cover page after a field update.

DO NOT USE TRACK CHANGES OR MARKUP.  IT WILL OVER RIDE THE FORMATTING AND YOUR DOCUMENT WILL BE UNUSABLE

Submission Deadline

The Submission Deadline is 12:00 noon Winnipeg time, ^month day, year.

SPEC NOTE: Insert month, day and year of Submission Deadline scheduled by the Purchasing Division.

The Contract Administrator or the Manager of Purchasing may extend the Submission Deadline by issuing an addendum at any time prior to the time and date specified in B2.1.

Site Investigation

SPEC NOTE: Use B3 only if the Bidder must be advised of restrictions on or special reasons for investigating the Site.

SPEC NOTE: VERSION 1 - Use this version when the Site is accessible without the Contract Administrator being in attendance, and there are restrictions on or special reasons for investigating the Site.

    - Further to C3.1, the Bidder may view the Site without making an appointment.

The Bidder is advised that ^SPEC NOTE: Identify the reason(s) the Bidder should view the site, e.g., existing snow cover, etc., or any restrictions on access such as days.  Do not paraphrase C3.1.

The Bidder is responsible for inspecting the Site, the nature of the Work to be done and all conditions that might affect their Bid or their performance of the Work, and shall assume all risk for conditions existing or arising in the course of the Work which have been or could have been determined through such inspection.

SPEC NOTE: VERSION 2 - Use this version when providing a limited number of opportunities to view the Site is reasonable and the Contract Administrator should be in attendance, e.g., soil test holes to be drilled.  Insert times, month(s), day(s) and year when the Site will be attended by the Contract Administrator.  Advise the Purchasing Division of the requirement to ensure that it is included in the advertisement of the Tender.

    - Further to C3.1, the Contract Administrator or an authorized representative will be available at the Site at ^start time on ^month day, year to provide Bidders access to the Site.

The Bidder is advised that ^SPEC NOTE: Identify any special reason(s) the Bidder should view the site, e.g., demonstration of operations, test borings, etc.  Delete B3.2 if there are no such reasons.

The Bidder shall not be entitled to rely on any information or interpretation received at the Site investigation unless that information or interpretation is the Bidder’s direct observation, or is provided by the Contract Administrator in writing.

The Bidder is responsible for inspecting the Site, the nature of the Work to be done and all conditions that might affect their Bid or their performance of the Work, and shall assume all risk for conditions existing or arising in the course of the Work which have been or could have been determined through such inspection.

VERSION 3 - Use this version when only one opportunity to view the Site is reasonable, and the Contract Administrator should be in attendance, e.g., soil test holes to be drilled etc,.  Insert time, month, day and year when the Site will be attended by the Contract Administrator.  Advise the Purchasing Division of the requirement to ensure that it is included in the advertisement of the Tender.

    - Further to C3.1, a Site meeting will be held at start  time on ^month day, year to provide Bidders access to the Site.

The Bidder is advised that ^SPEC NOTE: Identify any reason(s) the Bidder should view the site, e.g., demonstration of operations, test borings, etc.  Delete B3.2 if there are no such reasons.

The Bidder shall not be entitled to rely on any information or interpretation received at the Site investigation unless that information or interpretation is the Bidder’s direct observation, or is provided by the Contract Administrator in writing.

The Bidder is responsible for inspecting the Site, the nature of the Work to be done and all conditions that might affect their Bid or their performance of the Work, and shall assume all risk for conditions existing or arising in the course of the Work which have been or could have been determined through such inspection.

Enquiries

All enquiries shall be directed to the Contract Administrator identified in D4.1.

If the Bidder finds errors, discrepancies or omissions in the Tender, or is unsure of the meaning or intent of any provision therein, the Bidder shall notify the Contract Administrator of the error, discrepancy or omission, or request a clarification as to the meaning or intent of the provision at least five (5) Business Days prior to the Submission Deadline.

Responses to enquiries which, in the sole judgment of the Contract Administrator, require a correction to or a clarification of the Tender will be provided by the Contract Administrator to all Bidders by issuing an addendum.

Responses to enquiries which, in the sole judgment of the Contract Administrator, do not require a correction to or a clarification of the Tender will be provided by the Contract Administrator only to the Bidder who made the enquiry.

The Bidder shall not be entitled to rely on any response or interpretation received pursuant to B4 unless that response or interpretation is provided by the Contract Administrator in writing.

Any enquiries concerning submitting through MERX should be addressed to:

MERX Customer Support

Phone: 1-800-964-6379

Email: merx@merx.com

Confidentiality

Information provided to a Bidder by the City or acquired by a Bidder by way of further enquiries or through investigation is confidential. Such information shall not be used or disclosed in any way without the prior written authorization of the Contract Administrator.  The use and disclosure of the confidential information shall not apply to information which:

was known to the Bidder before receipt hereof; or

becomes publicly known other than through the Bidder; or

is disclosed pursuant to the requirements of a governmental authority or judicial order.

The Bidder shall not make any statement of fact or opinion regarding any aspect of the Tender to the media or any member of the public without the prior written authorization of the Contract Administrator.

Addenda

The Contract Administrator may, at any time prior to the Submission deadline, issue addenda correcting errors, discrepancies or omissions in the Tender, or clarifying the meaning or intent of any provision therein.

The Contract Administrator will issue each addendum at least two (2) Business Days prior to the Submission Deadline, or provide at least two (2) Business Days by extending the Submission Deadline.

Addenda will be available on the MERX website at www.merx.com.

The Bidder is responsible for ensuring that they have received all addenda and is advised to check the MERX website for addenda regularly and shortly before the Submission Deadline, as may be amended by addendum.

The Bidder shall acknowledge receipt of each addendum in Paragraph 10 of Form A: Bid/Proposal.  Failure to acknowledge receipt of an addendum may render a Bid non-responsive.

Notwithstanding B4, enquiries related to an Addendum may be directed to the Contract Administrator indicated in D4.

Substitutes

The Work is based on the Plant, Materials and methods specified in the Tender.

Substitutions shall not be allowed unless application has been made to and prior approval has been granted by the Contract Administrator in writing.

SPEC NOTE: Increase or decrease the five (5) Business Days depending on the complexity of the Work.  Four (4) Business Days is the minimum feasible.

Requests for approval of a substitute will not be considered unless received in writing by the Contract Administrator at least five (5) Business Days prior to the Submission Deadline.

The Bidder shall ensure that any and all requests for approval of a substitute:

provide sufficient information and details to enable the Contract Administrator to determine the acceptability of the Plant, Material or method as either an approved equal or alternative;

identify any and all changes required in the applicable Work, and all changes to any other Work, which would become necessary to accommodate the substitute;

identify any anticipated cost or time savings that may be associated with the substitute;

certify that, in the case of a request for approval as an approved equal, the substitute will fully perform the functions called for by the general design, be of equal or superior substance to that specified, is suited to the same use and capable of performing the same function as that specified and can be incorporated into the Work, strictly in accordance with the proposed work schedule and the dates specified in the Supplemental Conditions for Substantial Performance and Total Performance;

certify that, in the case of a request for approval as an approved alternative, the substitute will adequately perform the functions called for by the general design, be similar in substance to that specified, is suited to the same use and capable of performing the same function as that specified and can be incorporated into the Work, strictly in accordance with the proposed work schedule and the dates specified in the Supplemental Conditions for Substantial Performance and Total Performance.

The Contract Administrator, after assessing the request for approval of a substitute, may in their sole discretion grant approval for the use of a substitute as an “approved equal” or as an “approved alternative”, or may refuse to grant approval of the substitute.

The Contract Administrator will provide a response in writing, at least two (2) Business Days prior to the Submission Deadline, to the Bidder who requested approval of the substitute.

The Contract Administrator will issue an Addendum, disclosing the approved materials, equipment, methods and products to all potential Bidders.  The Bidder requesting and obtaining the approval of a substitute shall be responsible for disseminating information regarding the approval to any person or persons they wish to inform.

If the Contract Administrator approves a substitute as an “approved equal”, any Bidder may use the approved equal in place of the specified item.

If the Contract Administrator approves a substitute as an “approved alternative”, any Bidder bidding that approved alternative may base their Total Bid Price upon the specified item but may also indicate an alternative price based upon the approved alternative.  Such alternatives will be evaluated in accordance with B18.

No later claim by the Contractor for an addition to the Total Bid Price because of any other changes in the Work necessitated by the use of an approved equal or an approved alternative will be considered.

Bid Components

The Bid shall consist of the following components:

Form A:	Bid;

Form B:	Prices;

Form G1: Bid Bond and Agreement to Bond.

SPEC NOTE:  List any Bidder-supplied documents or samples to be submitted with their bid that are required to evaluate the Bid and provide a corresponding Bidding Procedure after B14, Evaluation criteria for any such additional information must be stipulated in B18.

All components of the Bid shall be fully completed or provided, and submitted by the Bidder no later than the Submission Deadline, with all required entries made clearly and completely.

The Bid shall be submitted electronically through MERX at www.merx.com.

Bids will only be accepted electronically through MERX.

Bidders are advised that inclusion of terms and conditions inconsistent with the Tender document, including the General Conditions, will be evaluated in accordance with B18.1(a).

Bid

The Bidder shall complete Form A: Bid/Proposal, making all required entries.

Paragraph 2 of Form A: Bid/Proposal shall be completed in accordance with the following requirements:

if the Bidder is a sole proprietor carrying on business in their own name, their name shall be inserted;

if the Bidder is a partnership, the full name of the partnership shall be inserted;

if the Bidder is a corporation, the full name of the corporation shall be inserted;

if the Bidder is carrying on business under a name other than their own, the business name and the name of every partner or corporation who is the owner of such business name shall be inserted.

If a Bid is submitted jointly by two or more persons, each and all such persons shall identify themselves in accordance with B9.2.

In Paragraph 3 of Form A: Bid/Proposal, the Bidder shall identify a contact person who is authorized to represent the Bidder for purposes of the Bid.

Paragraph 13 of Form A: Bid/Proposal shall be signed in accordance with the following requirements:

if the Bidder is a sole proprietor carrying on business in their own name, it shall be signed by the Bidder;

if the Bidder is a partnership, it shall be signed by the partner or partners who have authority to sign for the partnership;

if the Bidder is a corporation, it shall be signed by their duly authorized officer or officers;

if the Bidder is carrying on business under a name other than their own, it shall be signed by the registered owner of the business name, or by the registered owner's authorized officials if the owner is a partnership or a corporation.

The name and official capacity of all individuals signing Form A: Bid/Proposal should be entered below such signatures.

If a Bid is submitted jointly by two or more persons, the word "Bidder" shall mean each and all such persons, and the undertakings, covenants and obligations of such joint Bidders in the Bid and the Contract, when awarded, shall be both joint and several.

Prices

VERSION 1 - Use this version with VERSION 1 of Form B: Prices for unit price contracts.

The Bidder shall state a price in Canadian funds for each item of the Work identified on Form B: Prices.

SPEC NOTE: Delete B10.1.1 if 3rd Party Funding is confirmed

Prices stated on Form B: Prices shall not include any costs which may be incurred by the Contractor with respect to any applicable funding agreement obligations as outlined in C24.  Any such costs shall be determined in accordance with C24.

The quantities listed on Form B: Prices are to be considered approximate only.  The City will use said quantities for the purpose of comparing Bids.

The quantities for which payment will be made to the Contractor are to be determined by the Work actually performed and completed by the Contractor, to be measured as specified in the applicable Specifications.

Payments to Non-Resident Contractors are subject to Non-Resident Withholding Tax pursuant to the Income Tax Act (Canada).

The Bidder shall enter the Total Bid Price from Form B: Prices into the Total Bid Price field in MERX.

Bidders are advised that the calculation indicated in B18.5 will prevail over the Total Bid Price entered in MERX.

Spec Note: Delete B10.6 in its entirety if none of the Work is being funded by another source (Province) or if the funds from the other source have been secured.  Form B: Prices and D2 must be formatted into two parts.  The Work being funded by the City must be identified as Part 1 and the Work funded by other sources (Province) must be identified as Part 2.  Form B: Prices must include a summary sheet with a total price for each Part, and the Total Bid Price.

Form B: Prices is organized into Parts: Part 1 of the Work and Part 2 of the Work.  Bidders shall provide a total price for each Part and, on the summary sheet, a Total Bid Price consisting of the sum of prices for Part 1 and Part 2.

Disclosure

SPEC NOTE:  Do Not Delete.  If City staff or Consultants have discussed or obtained information/services from Persons, the name of that Person (company name preferred) and what information was discussed or obtained must be disclosed below.  If you haven’t discussed with any Persons, state N/A.

Various Persons provided information or services with respect to this Work.  In the City’s opinion, this relationship or association does not create a conflict of interest because of this full disclosure.  Where applicable, additional material available as a result of contact with these Persons is listed below.

The Persons are:

^

^

SPEC NOTE: Delete if not required.

Additional Material:

^

^

Conflict of Interest and Good Faith

Further to C3.3, Bidders, by responding to this Tender, declare that no Conflict of Interest currently exists, or is reasonably expected to exist in the future.

Conflict of Interest means any situation or circumstance where a Bidder or employee of the Bidder proposed for the Work has:

other commitments;

relationships;

financial interests; or

involvement in ongoing litigation;

- that could or would be seen to:

exercise an improper influence over the objective, unbiased and impartial exercise of the independent judgment of the City with respect to the evaluation of Bids or award of the Contract; or

compromise, impair or be incompatible with the effective performance of a Bidder’s obligations under the Contract;

has contractual or other obligations to the City that could or would be seen to have been compromised or impaired as a result of their participation in the Tender process or the Work; or

has knowledge of confidential information (other than confidential information  disclosed by the City in the normal course of the Tender process) of strategic and/or material relevance to the Tender process or to the Work that is not available to other bidders and that could or would be seen to give that Bidder an unfair competitive advantage.

In connection with their Bid, each entity identified in B12.2 shall:

avoid any perceived, potential or actual Conflict of Interest in relation to the procurement process and the Work;

upon discovering any perceived, potential or actual Conflict of Interest at any time during the Tender process, promptly disclose a detailed description of the Conflict of Interest to the City in a written statement to the Contract Administrator; and

provide the City with the proposed means to avoid or mitigate, to the greatest extent practicable, any perceived, potential or actual Conflict of Interest and shall submit any additional information to the City that the City considers necessary to properly assess the perceived, potential or actual Conflict of Interest.

Without limiting B12.3, the City may, in their sole discretion, waive any and all perceived, potential or actual Conflicts of Interest. The City’s waiver may be based upon such terms and conditions as the City, in their sole discretion, requires to satisfy itself that the Conflict of Interest has been appropriately avoided or mitigated, including requiring the Bidder to put into place such policies, procedures, measures and other safeguards as may be required by and be acceptable to the City, in their sole discretion, to avoid or mitigate the impact of such Conflict of Interest.

Without limiting B12.3, and in addition to all contractual or other rights or rights at law or in equity or legislation that may be available to the City, the City may, in their sole discretion:

disqualify a Bidder that fails to disclose a perceived, potential or actual Conflict  of Interest of the Bidder or any of their employees proposed for the Work;

require the removal or replacement of any employees proposed for the Work that has a perceived, actual or potential Conflict of Interest that the City, in their sole discretion, determines cannot be avoided or mitigated;

disqualify a Bidder or employees proposed for the Work that fails to comply with any requirements prescribed by the City pursuant to B12.4 to avoid or mitigate  a Conflict of Interest; and

disqualify a Bidder if the Bidder, or one of their employees proposed for the Work, has a perceived, potential or actual Conflict of Interest that, in the City’s sole discretion, cannot be avoided or mitigated, or otherwise resolved.

The final determination of whether a perceived, potential or actual Conflict of Interest exists shall be made by the City, in their sole discretion.

Qualification

The Bidder shall:

undertake to be in good standing under The Corporations Act (Manitoba), or properly registered under The Business Names Registration Act (Manitoba), or otherwise properly registered, licensed or permitted by law to carry on business in Manitoba; and

be financially capable of carrying out the terms of the Contract; and

have all the necessary experience, capital, organization, and equipment to perform the Work in strict accordance with the terms and provisions of the Contract.

The Bidder and any proposed Subcontractor (for the portion of the Work proposed to be subcontracted to them) shall:

be responsible and not be suspended, debarred or in default of any obligations to the City.  A list of suspended or debarred individuals and companies is available on the Information Connection page at The City of Winnipeg, Corporate Finance, Purchasing Division website at https://www.winnipeg.ca/matmgt/Templates/files/debar.pdf

The Bidder and/or any proposed Subcontractor (for the portion of the Work proposed to be subcontracted to them) shall:

have successfully carried out work similar in nature, scope and value to the Work; and

be fully capable of performing the Work required to be in strict accordance with the terms and provisions of the Contract; and

have a written workplace safety and health program if required pursuant to The Workplace Safety and Health Act (Manitoba);

have completed the Accessible Customer Service online training required by the Accessibility for Manitobans Act (AMA) (see B13.5 and C6.19)

SPEC NOTE: Identify any additional contract-specific qualification requirements for specialty contracts, e.g., a requirement that the bidder‘s proposed Supervisor have specific related experience.

SPEC NOTE: Use B13.4 for contracts estimated to exceed $100,000 in value or considered to be high risk.  Examples of high risk work would include confined space entry, excavation, work at heights, overhead craning, use of explosives, work near high energy power lines, work that involves the use of large (reportable under TDG) amounts of hazardous chemicals, e.g., propane, chlorine, acids, sand blasting media, solvent-based paints.

Further to B13.3(c), the Bidder shall, within five (5) Business Days of a request by the Contract Administrator, provide proof satisfactory to the Contract Administrator that the Bidder/Subcontractor has a workplace safety and health program meeting the requirements of The Workplace Safety and Health Act (Manitoba), by providing:

Written confirmation of a safety and health certification meeting SAFE Work Manitoba’s SAFE Work Certified Standard (e.g., COR™ and SECOR™) in the form of:

a copy of their valid Manitoba COR certificate and Letter of Good Standing (or Manitoba equivalency) as issued under the Certificate of Recognition (COR) Program administered by the Construction Safety Association of Manitoba or by the Manitoba Heavy Construction Association’s WORKSAFELY™ COR™ Program; or

a copy of their valid Manitoba SECOR™ certificate and Letter of Good Standing (or Manitoba equivalency) as issued under the Small Employer Certificate of Recognition Program (SECOR™) administered by the Construction Safety Association of Manitoba or by the Manitoba Heavy Construction Association’s WORKSAFELY™ COR™ Program; or

a report or letter to that effect from an independent reviewer acceptable to the City.  A list of acceptable reviewers and the review template are available at https://www.winnipeg.ca/matmgt/Safety/safety_consultant.stm.

Further to B13.3(d), the Bidder acknowledges that they and all Subcontractors have obtained training required by the Accessibility for Manitobans Act (AMA) available at https://accessibilitymb.ca/resources-events-and-training/online-training.html for anyone that may have any interaction with the public on behalf of the City of Winnipeg.

SPEC NOTE:  revise the number of days as required but be advised that the Contract Administrator MUST adhere to the number of days stated, without exception.

The Bidder shall submit, within three (3) Business Days of a request by the Contract Administrator, proof satisfactory to the Contract Administrator of the qualifications of the Bidder and of any proposed Subcontractor.

The Bidder shall provide, on the request of the Contract Administrator, full access to any of the Bidder's equipment and facilities to confirm, to the Contract Administrator’s satisfaction, that the Bidder's equipment and facilities are adequate to perform the Work.

Bid Security

The Bidder shall include in their Bid Submission bid security in the form of a digital bid bond, in the amount of at least ten percent (10%) of the Total Bid Price, and agreement to bond of a company registered to conduct the business of a surety in Manitoba, in Form G1: Bid Bond and Agreement to Bond, available at: https://www.winnipeg.ca/media/4929/.

Bid security shall be submitted in a digital format meeting the following criteria:

The version submitted by the Bidder must have valid digital signatures and seals;

The version submitted by the Bidder must be verifiable by the City with respect to the totality and wholeness of the bond form, including: the content; all digital signatures and digital seals; with the surety company, or an approved verification service provider of the surety company.

The version submitted must be viewable, printable and storable in standard electronic file formats compatible with the City, and in a single file. Allowable formats include pdf.

The verification may be conducted by the City immediately or at any time during the life of the bond and at the discretion of the City with no requirement for passwords or fees.

The results of the verification must provide a clear, immediate and printable indication of pass or fail regarding B14.2(a).

Bonds failing the verification process will not be considered to be valid and the bid shall be determined to be non-responsive in accordance with B18.1(a).

Bonds passing the verification process will be treated as original and authentic.

If the Bidder submits alternative bids, the bid security shall be in the amount of the specified percentage of the highest Total Bid Price submitted.

The bid security of the successful Bidder and the next two lowest evaluated responsive and responsible Bidders will be released by the City when a Contract for the Work has been duly formed with the successful Bidder and the contract securities are furnished as provided herein.  The bid securities of all other Bidders will be released when a Contract is awarded.

The bid securities of all Bidders will be released by the City as soon as practicable following notification by the Contract Administrator to the Bidders that no award of Contract will be made pursuant to the Tender.

Opening of Bids and Release of Information

Bids will not be opened publicly.

Following the submission deadline, the names of the Bidders and their Total Bid Prices (unevaluated, and pending review and verification of conformance with requirements) will be available on the MERX website at www.merx.com.

After award of Contract, the name(s) of the successful Bidder(s) and their Contract amount(s) will be available on the MERX website at www.merx.com.

The Bidder is advised that any information contained in any Bid may be released if required by The Freedom of Information and Protection of Privacy Act (Manitoba), by other authorities having jurisdiction, or by law or by City policy or procedures (which may include access by members of City Council).

To the extent permitted, the City shall treat as confidential information, those aspects of a Bid Submission identified by the Bidder as such in accordance with and by reference to Part 2, Section 17 or Section 18 or Section 26 of The Freedom of Information and Protection of Privacy Act (Manitoba), as amended.

Irrevocable Bid

The Bid(s) submitted by the Bidder shall be irrevocable for the time period specified in Paragraph 11 of Form A: Bid/Proposal.

The acceptance by the City of any Bid shall not release the Bids of the next two lowest evaluated responsive Bidders and these Bidders shall be bound by their Bids on such Work until a Contract for the Work has been duly formed and the contract securities have been furnished as herein provided, but any Bid shall be deemed to have lapsed unless accepted within the time period specified in Paragraph 11 of Form A: Bid/Proposal.

Withdrawal of Bids

A Bidder may withdraw their Bid without penalty prior to the Submission Deadline.

Evaluation of Bids

Award of the Contract shall be based on the following bid evaluation criteria:

compliance by the Bidder with the requirements of the Tender, or acceptable deviation therefrom (pass/fail);

qualifications of the Bidder and the Subcontractors, if any, pursuant to B13 (pass/fail);

Total Bid Price;

economic analysis of any approved alternative pursuant to B7.

SPEC NOTE: Replace Total Bid Price with “evaluated Bid Price” where evaluation criteria will be used to add to or subtract from the Total Bid Price to reflect other costs.  Include any and all other criteria that will be used to evaluate Bids.

Further to B18.1(a), the Award Authority may reject a Bid as being non-responsive if the Bid is incomplete, obscure or conditional, or contains additions, deletions, alterations or other irregularities.  The Award Authority may reject all or any part of any Bid, or waive technical requirements or minor informalities or irregularities, if the interests of the City so require.

Spec Note: Delete B18.2.1 if none of the Work is being funded by another source (Province) or if the funds from the other source have been secured.  Form B: Prices and D2 must be formatted into two parts.  The Work being funded by the City must be identified as Part 1 and the Work funded by other sources (Province) must be identified as Part 2.

Any bid with an apparent imbalance between the unit prices in Part 1 and Part 2 may be determined to be non-responsive and rejected by the Award Authority in their sole discretion, acting reasonably.

Further to B18.1(b), the Award Authority shall reject any Bid submitted by a Bidder who does not demonstrate, in their Bid or in other information required to be submitted, that they are qualified.

SPEC NOTE:  Delete B18.4 if NOT stating the available funds in Scope of Work D2.1.

Further to B18.1(c) the Award Authority may reject a Bid as being non-responsive if it exceeds the funds available as shown in D2.1.

SPEC NOTE: VERSION 1 - Use this version with VERSION 1 of B10 and VERSION 1 of Form B: Prices for unit price contracts.

Further to B18.1(c), the Total Bid Price shall be the sum of the quantities multiplied by the unit prices for each item shown on Form B: Prices.

Further to B18.1(a), in the event that a unit price is not provided on Form B: Prices, the City may determine the unit price by dividing the Amount (extended price) by the approximate quantity, for the purposes of evaluation and payment.

Where MRST is shown on Form B as a separate line item, if that Line item is not completed, the MRST shall be considered to be included in the Total Bid Price.

Bidders are advised that the calculation indicated in B18.5 will prevail over the Total Bid Price entered in MERX.

VERSION 2 – Use this version with VERSION 1 of B10 and VERSION 1 of Form B:  Prices for unit price contracts.  This version allows for deductions until a Total Bid Price is within the budgetary provision.

    - Further to B18.1(c), the Total Bid Price shall be the sum of the quantities multiplied by the unit prices for each item shown on Form B: Prices adjusted, if necessary, as follows:

if the lowest evaluated responsive Bid submitted by a responsible and qualified Bidder is within the budgetary provision for the Work, no adjustment will be made to the Total Bid Price; or

if the lowest evaluated responsive Bid submitted by a responsible and qualified Bidder exceeds the budgetary provision for the Work, the Total Bid Prices of all responsive Bids submitted by responsible and qualified Bidders will be adjusted by progressively deducting item(s) ^in numerals, ^ in numerals and ^ in numerals in the order listed until a Total Bid Price within the budgetary provision is achieved.

Further to B18.1(a), in the event that a unit price is not provided on Form B: Prices, the City may determine the unit price by dividing the Amount (extended price) by the approximate quantity, for the purposes of evaluation and payment.

Where MRST is shown on Form B as a separate line item, if that Line item is not completed, the MRST shall be considered to be included in the Total Bid Price.

Bidders are advised that the calculation indicated in B18.5  will prevail over the Total Bid Price entered in MERX.

SPEC NOTE: Use B18.6 only if there are alternatives identified in the Tender that have been reviewed and approved by the Streets Project Engineer/Coordinator.  Identify alternatives on Form B: Prices and in the Specifications.  Evaluation criteria must be specified in B18.1.

The Contract may be awarded on the basis of:

Alternative 1 - ^description; or

Alternative 2 - ^description; or

Alternative 3 - ^description;

as identified on Form B: Prices.  Each alternative will be evaluated in accordance with the specified evaluation criteria.

Notwithstanding B10, the Bidder may, but is not required to, bid on all alternatives.

The City shall have the right to choose the alternative that is in their best interests.  If the Bidder has not bid on all alternatives, they shall have no claim against the City if their partial Bid is rejected in favour of an award of the Contract on the basis of an alternative upon which they have not bid.

Award of Contract

The City will give notice of the award of the Contract or will give notice that no award will be made.

The City will have no obligation to award a Contract to a Bidder, even though one or all of the Bidders are determined to be qualified, and the Bids are determined to be responsive.

Without limiting the generality of B19.2, the City will have no obligation to award a Contract where:

the prices exceed the available City funds for the Work;

the prices are materially in excess of the prices received for similar work in the past;

the prices are materially in excess of the City’s cost to perform the Work, or a significant portion thereof, with their own forces;

only one Bid is received; or

in the judgment of the Award Authority, the interests of the City would best be served by not awarding a Contract.

Spec Note: Delete B19.3 if not required or if fully funded under the Capital Budget.

The Work of this Contract is contingent upon Council approval of sufficient funding in the ^ Enter the Year    Capital Budget.  If the Capital Budget approved by Council does not include sufficient funding for the Work, the City will have no obligation to award a Contract.

SPEC NOTE: Delete B19.4 if 3rd Party Funding is confirmed.

If funding for the Work is provided to the City of Winnipeg by the Government of Manitoba and/or the Government of Canada, Bidders are advised that the terms of C24 shall immediately take effect upon confirmation of such funding, regardless of when funding is confirmed.

Where an award of Contract is made by the City, the award shall be made to the qualified Bidder submitting the lowest evaluated responsive Bid, in accordance with B18.

Following the award of contract, a Bidder will be provided with information related to the evaluation of their Bid upon written request to the Contract Administrator.

SPEC NOTE: Delete B19.6 if none of the Work is being funded by another source (Province) or if the funds from the other source have been secured.  Form B: Prices and D2 must be formatted into two parts.  The Work being funded by the City must be identified as Part 1 and the Work funded by other sources (Province) must be identified as Part 2.

As noted in D2 and identified in Form B: Prices, the Work of Part 2 will be contingent upon the Province approving funding for the Work. If sufficient funding for Part 2 Work is not approved by the Province the City shall have the right to eliminate all or any portion of Part 2 Work in accordance with D2.

SPEC NOTE: B19 Award of Contract must always be the last clause in the Bidding Procedures.

General Conditions

  - General Conditions

The General Conditions for Construction (Revision 2025-11-01) are applicable to the Work of the Contract.

The General Conditions for Construction are available on the Information Connection page at The City of Winnipeg, Corporate Finance, Purchasing Division website at http://www.winnipeg.ca/matmgt/gen_cond.stm

A reference in the Tender to a section, clause or subclause with the prefix “C” designates a section, clause or subclause in the General Conditions for Construction.

- SUPPLEMENTAL CONDITIONS

General

General Conditions

In addition to the General Conditions for Construction, these Supplemental Conditions are applicable to the Work of the Contract.

Scope of Work

- SPEC NOTE: Insert the type(s) of Work and a concise description of the applicable location(s).  Where practical group the locations as clause sublist items (i, ii, iii…) under the various types of renewals listed as clauselist items (a, b, c…).  See examples for Regional & Residential Streets at the end of this clause section.

- SPEC NOTE: VERSION 1: For contracts with all funding from a single source (City) or where funding from other source (Province) have been secured.

The Work to be done under the Contract shall consist of:

^ Type of Work (e.g., Pavement Reconstruction, Crack & Seating, Pavement Rehabilitation, Watermain Renewal.  Repeat for each type of Work.

^ Location (e.g., Mighton Avenue from Henderson Highway to Brazier Street.)

^ Location (e.g., St. Mary’s Road from Dunkirk to Fermor, West Side)

^

^

^

- SPEC NOTE: VERSION 2: For contracts with a funding component from another source (Province) and the funds have not been secured; separate the Work funded by the City into Part1 and the Work funded by the other source (Province) into Part 2.

    - The Work to be done under the Contract shall consist of two parts:

Part 1 – City Funded Work

Part 2 – Provincially Funded Work.

Part 1 – City Funded Work

Part 1 – City Funded Work shall consist of:

^ Type of Work (e.g., Pavement Reconstruction, Crack & Seating, Pavement Rehabilitation, Watermain Renewal.  Repeat for each type of Work.

^ Location (e.g., Mighton Avenue from Henderson Highway to Brazier Street.)

^ Location (e.g., St. Mary’s Road from Dunkirk to Fermor, West Side)

^

^

^

Part 2 – Provincially Funded Work

Part 2 – Provincially Funded Work shall consist of:

^ Type of Work (e.g., Pavement Reconstruction, Crack & Seating, Pavement Rehabilitation, Watermain Renewal.  Repeat for each type of Work.

^ Location (e.g., Dudley Avenue from Lilac Street to Arbuthnot Street)

^ Location (e.g., Melrose Avenue W from Winona Street to Bond Street)

^

^

^

The City currently has no approved funding in the Capital Budget for Part 2 of the Work, but is anticipating receiving notification about funding from the Province of Manitoba by late May.  Part 2 of the Work is contingent upon the Province approving sufficient funding.

Further to C7.1, if notice of sufficient funding is not received, the City shall have the right to eliminate all or any portion of Part 2, and the Contract Price will be reduced accordingly.

Further to C7.5, C7.5.1, and C7.6, a reduction in the Contract Price pursuant to D2.4.1 shall not be considered in calculating the aggregate reduction in the Contract Price for purposes of C7.5.

If all or any portion of Part 2 is eliminated pursuant to D2.4.1, the time periods stipulated in D21 for Substantial Performance of the Work and in D22 for Total Performance of the Work will be reduced proportionally by the Contract Administrator acting reasonably.

SPEC NOTE: List the type(s) of Work identified in D2.1.  Under each type, list the associated major components in logical order, especially components that are typically sub-contracted.

Where a component is applicable to only some of the locations identified under the type of Work, list the applicable location(s) in brackets following the component  e.g.:

(iv)	 Construction of 150mm Concrete Pavement (reinforced) with slip-form paving equipment (Mighton Ave. & Smith St.)

Use of Slip Form Paving Equipment

- Concrete Pavements

- Consider slip-from paving equipment for the placement of concrete pavement to maximize quality of the finished surface and/or to reduce the construction period.  Review and finalize with the PW Streets Project Engineer/Co-ordinator.  If slip form paving is specified (see CW3240 –R9,  3.3.15 & CW3310-R14, 8.2), increase the limits of the excavation from 450mm to 750 mm (see CW3110-R15, 3.2.5) and where applicable indicate on the drawings.

- Curbs, Curb & Gutter Sections and Splash Strips

- Specify slip-form paving equipment for new construction, reconstructions, for complete curb renewals when all curbs are being replaced or when the length being replaced is over 250 metres.  Include breaks for approaches, isolations or fixed obstacles such as light standards or poles in determining the length

- Asphalt Overlays

Where a component is “Placement of Asphalt Overlay”, specify the average new asphalt overlay thickness for each location to allow the Contractor to estimate the actual average curb height that he will be installing.  Note: The curb height specified in the applicable pay items on Form “B” is the reveal or finished curb height at completion of asphalt work. e.g.:

- Placement of Asphalt Overlay

  - thickness 100mm (Mighton Ave. & Smith St.)

  - thickness 140mm (Waterloo St.)

The major components of the Work are as follows:

^ 1st type of Work (from D2.1)

^ Component

^ Component

^ Component

^ 2nd type of Work (from D2.1)

^ Component

^ Component

^ Component

SPEC NOTE: Example of scope of work for the regional streets renewal program (with funding secured).

  - Scope of Work

The Work to be done under the Contract shall consist of:

Asphalt Resurfacing and Related Works

St. Mary’s Road from Dunkirk Drive to Fermor Avenue

The major components of the Work are as follows:

Asphalt Resurfacing and Related Works

Planing of asphalt overlay

Full depth concrete repairs of existing slabs and joints

Installation of catchbasins and connection pipe

Adjustment of drainage inlets, water valves and manholes

Complete renewal of existing curbs in gutter lanes utilizing slip-form paving equipment

Construct splash strip in median lanes utilizing slip-form paving equipment

Construct monolithic median slab

Complete curb renewal at intersections

Placement asphalt overlay (average thickness –100mm)

Renewal of existing miscellaneous concrete slabs

Boulevard restoration

- Spec Note: example of scope of work for the residential streets renewal program (with funding secured)

  - Scope of Work

- Pavement Reconstruction

- (Rosseau Avenue average thickness –90mm)

- (Ashland Avenue and Aurora Street average thickness –80mm)

- (Kate Street average thickness –90mm)

_________________________________________________________________________________

FUNDS AVAILABLE

SPEC NOTE: Delete D2.1 and B18.4 if NOT stating the funds available or not utilizing the deduction clauses in B18. If available funds are NOT listed, a future non-award due to bids exceeding the available funds will violate the various trade agreements (undisclosed evaluation criteria) and the non-award must be approved by the CFO. Please make choice wisely.

    - The funds available for this contract are $^.

Definitions

SPEC NOTE: Include D3 only if it is necessary to define any words, phrases, acronyms or abbreviations used in the Tender with a meaning other than in common English usage and not defined in C1.1.  Include terms introduced in the Supplemental Conditions.  Note:  terms introduced in the Specifications should be defined in that Specification.

When used in this Tender:

”^term” means ^definition;

”^term” means ^definition;

”^term” means ^definition.

Contract Administrator

SPEC NOTE: VERSION 1 – IN-HOUSE Bid Opportunities only.  Use this version if the Contract Administrator is an individual, e.g., City employee.  Insert name, title, department name, telephone number and email address of the City employee who is the Contract Administrator.  The Contract Administrator must be reasonably available throughout the bidding period.  Never name more than one person.

The Contract Administrator is:

^name

^title

Telephone No.	204 ^tel. no.

Email Address	^email address.

At the pre-construction meeting, the Contract Administrator will identify additional personnel representing the Contract Administrator and their respective roles and responsibilities for the Work.

SPEC NOTE: VERSION 2 Use this version if the Contract Administrator is a company, e.g., consulting firm.  Insert the name of the company and the name, title, telephone number and facsimile number of the individual representing the Contract Administrator.  The individual must be reasonably available throughout the bidding period.  Never name more than one person

    - The Contract Administrator is ^company name, represented by:

^  insert name between bookmark brackets for reference in D4.2.

^title

Telephone No.	204 ^tel. no.

Email Address	^email address.

At the pre-construction meeting,  ^  will identify additional personnel representing the Contract Administrator and their respective roles and responsibilities for the Work.

Contractor's Supervisor

At the pre-construction meeting, the Contractor shall identify their designated supervisor and any additional personnel representing the Contractor and their respective roles and responsibilities for the Work.

SPEC NOTE:  Contract Administrator to forward Emergency Contact number to Emergency Services @ 986-2511.

At least two (2) Business Days prior to the commencement of any Work on the site, the Contractor shall provide the Contract Administrator with a phone number where the supervisor identified in D5.1 or an alternate can be contacted twenty-four (24) hours a day to respond to an emergency.

Furnishing of Documents

Upon award of the Contract, the Contractor will be provided with ‘issued for construction’ Contract Documents electronically, including Drawings in PDF format only.

Submissions

Authority to Carry on Business

The Contractor shall be in good standing under The Corporations Act (Manitoba), or properly registered under The Business Names Registration Act (Manitoba), or otherwise properly registered, licensed or permitted by law to carry on business in Manitoba, or if the Contractor does not carry on business in Manitoba, in the jurisdiction where the Contractor does carry on business, throughout the term of the Contract, and shall provide the Contract Administrator with evidence thereof upon request.

Safe Work Plan

The Contractor shall provide the Contract Administrator with a Safe Work Plan at least five (5) Business Days prior to the commencement of any Work on the Site.

The Safe Work Plan shall be prepared and submitted in the format shown in the City’s template which is available on the Information Connection page at The City of Winnipeg, Corporate Finance, Purchasing Division website at http://www.winnipeg.ca/matmgt/safety/default.stm

SPEC NOTE: Delete D8.3 if deleting the COR requirements specified under B13 Qualifications.

Notwithstanding B13.4 at any time during the term of the Contract, the City may, at their sole discretion and acting reasonably, require an updated COR Certificate or Annual Letter of good Standing.  A Contractor, who fails to provide a satisfactory COR Certificate or Annual Letter of good Standing, will not be permitted to continue to perform any Work.

Insurance

SPEC NOTE:  Where 3rd Party Funding is confirmed, consult with the Insurance Branch insurance@winnipeg.ca for additional wording for wrap-up, builders’ risk etc. to be included in D9.

The Contractor shall provide and maintain the insurance coverage:

SPEC NOTE: Notwithstanding clauses will need to be added here. Increase the amount of liability coverage if required for the Work.  Typically, $2,000,000 is adequate, however, on higher-risk contracts, a higher amount may be determined to be more appropriate by the Department in consultation with the Insurance Branch insurance@winnipeg.ca .

commercial general liability insurance, in the amount of at least two million dollars ($2,000,000.00) inclusive, with The City of Winnipeg added as an additional insured, with a cross-liability clause, contractual liability, unlicensed motor vehicle liability (contractor’s equipment), non-owned automobile liability and products and completed operations endorsement, to remain in place at all times during the performance of the Work and throughout the Warranty period;

if applicable, Automobile Liability Insurance covering all motor vehicles, owned and operated and used or to be used by the Contractor directly or indirectly in the performance of the Work.  The Limit of Liability shall not be less than $2,000,000 inclusive for loss or damage including personal injuries and death resulting from any one accident or occurrence;

all risks Installation Floater carrying adequate limits to cover all machinery, equipment, supplies and/or materials intended to enter into and form part of any installation.

SPEC NOTE:  Complex projects and all projects over five million ($5,000,000) should be vetted through the Insurance Branch, as unique requirements or increased limits may be necessary and/or Owner Controlled Insurance (purchased by the City) may be warranted.  Example of possible additions:  Certificate to state “operations to include blasting/hazardous material handling/asbestos/mould removal/ etc”.

    - Deductibles shall be borne by the Contractor.

    - All policies shall be taken out with insurers licensed to carry on business in the Province of Manitoba.

SPEC NOTE: For contracts that include some form of demolition of a structure (building, bridge, etc.) copy and paste the “Insurance” subclause with reference to “demolition work” from the Demolition template.

    - The Contractor shall provide:

      - The certificate of insurance, in a form satisfactory to the Supervisor of Insurance, to:

- The City of Winnipeg

- Risk Management

- Insurance Section

- 185 King Street, 3rd Floor

- Winnipeg, MB R3B 1J1

      - The Contract Administrator with a copy of the certificate of insurance.

- At least two (2) Business Days of notification of the award of the Contract prior to the commencement of any Work on the Site.

    - The Contractor shall not cancel, materially alter, or cause each policy to lapse without providing at least thirty (30) Calendar Days prior written notice to the Supervisor of Insurance.

Contract Security

The Contractor shall provide and maintain the performance bond and the labour and material payment bond until the expiration of the warranty period in the form of:

      - a performance bond of a company registered to conduct the business of a surety in Manitoba, in the amount of fifty percent (50%) of the Contract Price; and

      - labour and material payment bond of a company registered to conduct the business of a surety in Manitoba, in an amount equal to fifty percent (50%) of the Contract Price.

Bonds are available at:

            - Performance Bond https://www.winnipeg.ca//media/4928/

              - Performance Bond – Schedule A - Form of Notice https://www.winnipeg.ca/media/4831/

              - Performance Bond – Schedule B – Surety’s Acknowledgement  https://www.winnipeg.ca/media/4832/

              - Performance Bond – Schedule C – Surety’s Position https://www.winnipeg.ca/media/4833/

            - Labour & Material Payment Bond https://www.winnipeg.ca//media/4930/

              - L&M Bond – Schedule A – Notice of Claim

- https://www.winnipeg.ca/media/4834/

              - L&M Bond – Schedule B – Acknowledgement of a Notice https://www.winnipeg.ca/media/4835/

              - L&M Bond – Schedule C – Surety’s Position

- https://www.winnipeg.ca/media/4836/

          - Where the contract security is a performance bond, it may be submitted in hard copy or digital format.  If submitted in digital format the contract security must meet the following criteria:

      - the version submitted by the Contractor must have valid digital signatures and seals;

      - the version submitted by the Contractor must be verifiable by the City with respect to the totality and wholeness of the bond form, including: the content; all digital signatures and digital seals; with the surety company, or an approved verification service provider of the surety company.

      - the version submitted must be viewable, printable and storable in standard electronic file formats compatible with the City, and in a single file. Allowable formats include pdf.

      - the verification may be conducted by the City immediately or at any time during the life of the bond and at the discretion of the City with no requirement for passwords or fees.

      - the results of the verification must provide a clear, immediate and printable indication of pass or fail regarding D10.1(b).

          - Digital bonds failing the verification process will not be considered to be valid and may be determined to be an event of default in accordance with C18.1.  If a digital bond fails the verification process, the Contractor may provide a replacement bond (in hard copy or digital format) within seven (7) Calendar Days of the City’s request or within such greater period of time as the City in their discretion, exercised reasonably, allows.

Digital bonds passing the verification process will be treated as original and authentic.

The Contractor shall provide the required Contract Security to the Contract Administrator with copies of the required Contract Security within seven (7) Calendar Days of notification of the award of the Contract and prior to the commencement of any Work on the Site.

The Contractor shall, as soon as practicable after entering into a contract with a Subcontractor:

give the Subcontractor written notice of the existence of the labour and material payment bond in D10.1(b); and

post a notice of the bond and/or a copy of that bond in a conspicuous location at the Site of the Work.

Subcontractor List

SPEC NOTE: Use D11 only if a complete list of the names of Subcontractors (including materials suppliers) is required for administrative purposes, e.g.,

(a)	if Subcontractors for key portions of the Work were named in the Bid,

(b)	to confirm that no unapproved substitutions have been made (see C6.32);

(c)	to confirm that no Subcontractors are suspended or debarred;

(d)	if the City is providing wrap-up insurance for the project, to provide the Insurance Branch with necessary information;

(e)	if persons other than the Contractor are responsible for security or access control for the Site, to identify who is authorized to access the Site.

(f)	to restrict the Contractor from replacing a subcontractor without the Contract Administrator’s approval, in accordance with C6.29.2.

Include Form J: Subcontractors List.

The Contractor shall provide the Contract Administrator with a complete list of the Subcontractors whom the Contractor proposes to engage (Form J: Subcontractor List) at or prior to a pre-construction meeting, or at least two (2) Business Days prior to the commencement of any Work on the Site.

Equipment List

SPEC NOTE: Use D12 only where an equipment list is required for administrative purposes and Form K: Equipment List is included in the Tender.

The Contractor shall provide the Contract Administrator with a complete list of the equipment which the Contractor proposes to utilize (Form K: Equipment List) at or prior to a pre-construction meeting, or at least two (2) Business Days prior to the commencement of any Work on the Site.

Detailed Work Schedule

SPEC NOTE: Use D13 only where a detailed work schedule is required for administrative purposes.

SPEC NOTE: VERSION 1 - Use this version if Form L: Detailed Work Schedule is provided in the Tender.  Form L must be consistent with D15, D17 D18.1 D20, D21, D22.

The Contractor shall provide the Contract Administrator with a detailed work schedule (Form L: Detailed Work Schedule) at least two (2) Business Days prior to the commencement of any Work on the Site.

SPEC NOTE: Delete D13.2 & D13.3 if none of the Work is being funded by another source (Province) or if the funds from the other source have been secured.  Insert the time period that the contract will be reduced by should Part 2 be eliminated.  Note: Clauses and Form L: formatting provided for Working Day contracts only, if your contract is Calendar Day based you will need to revise the effected clauses/forms similarly.  Form B: Prices and D2 must be formatted into two parts.  The Work being funded by the City must be identified as Part 1 and the Work funded by other sources (Province) must be identified as Part 2.

If, prior to submitting the Detailed Work Schedule, the Contractor does not receive notification pursuant to D15.4 that all or some portion of Part 2 of the Work may be commenced, they shall complete Form L: Detailed Work Schedule for only Part 1 of the Work assuming that, if all of Part 2 is eliminated, the time periods stipulated in D21 for Substantial Performance of the Work and in D22 for Total Performance of the Work will be reduced by ^number (^n)  Working Days.

If, after submitting the Detailed Work Schedule, the Contractor receives notification that all or any portion of Part 2 of the Work may be commenced, they shall submit a revised Detailed Work Schedule no later than two (2) Business Days from receipt of the notification.

SPEC NOTE: VERSION 2 - Use this version if Form L: Detailed Work Schedule is not provided in the Tender.

    - The Contractor shall provide the Contract Administrator with a detailed work schedule at least two (2) Business Days prior to the commencement of any Work on the Site.

SPEC NOTE: Delete D13.2 &  D13.3 if none of the Work is being funded by another source (Province) or if the funds from the other source have been secured.  Insert the time period that the contract will be reduced by should Part 2 be eliminated.  Note: Clause formatting provided for Working Day contracts only, if your contract is Calendar day based you will need to revise the effected clauses similarly.  Form B: Prices and D2 must be formatted into two parts.  The Work being funded by the City must be identified as Part 1 and the Work funded by other sources (Province) must be identified as Part 2.

If, prior to submitting the Detailed Work Schedule, the Contractor does not receive notification pursuant to D15.4 that all or some portion of Part 2 of the Work may be commenced, they shall complete the Detailed Work Schedule for only Part 1 of the Work assuming that, if all of Part 2 is eliminated, the time periods stipulated in D21 for Substantial Performance of the Work and in D22 for Total Performance of the Work will be reduced by ^number (^n)  Working Days

If, after submitting the Detailed Work Schedule, the Contractor receives notification that all or any portion of Part 2 of the Work may be commenced, they shall submit a revised Detailed Work Schedule no later than two (2) Business Days from receipt of the notification.

The detailed work schedule shall consist of the following:

SPEC NOTE: Specify the format for the detailed work schedule.  Delete any unnecessary items.

a critical path method (C.P.M.) schedule for the Work;

a Gantt chart for the Work based on the C.P.M. schedule; SPEC NOTE:- Delete reference to C.P.M. if (a) is not included and

a daily manpower schedule for the Work

^

all acceptable to the Contract Administrator.

Further to D13.4(a), the C.P.M. schedule shall clearly identify the start and completion dates of all of the following activities/tasks making up the Work as well as showing those activities/tasks on the critical path:

SPEC NOTE: Identify:

(a)	the minimum list of activities/tasks to be included in the, e.g., the commencement date, Substantial Performance and Total Performance dates, milestone dates for critical stages of the Work, interim milestone dates, etc.;

(b)	type(s) of schedule, e.g., C.P.M., Gantt, time-scaled-logic, etc.;

(c)	format, e.g., computer generated schedule type such as Prima Vera with a computer disk file copy provided to the Contract Administrator;

(d)	amount of detail, e.g., if the Contractor can only be able to reasonably provide a detailed schedule for first 1-3 months of the contract, ask for detailed information in first part of schedule and less detail for remainder, with further detail to follow within a specified time period.

Further to D13.4(b), the Gantt chart shall show the time on a weekly basis, required to carry out the Work of each trade, or specification division.  The time shall be on the horizontal axis, and the type of trade shall be on the vertical axis.

SPEC NOTE:  Modify the clause for multiple location contracts and be prepared to supply the Contractor with the vertical axis detail required on the Gantt chart.

Further to D13.4(c), the daily manpower schedule shall list the daily number of individuals on the Site for each trade.

Requirements for Site Accessibility Plan

SPEC NOTE: Delete if not applicable to this Work.

The Contractor shall provide the Contract Administrator with an Accessibility Plan at least five (5) Business Days prior to the commencement of any Work on the Site.

The Accessibility Plan shall demonstrate how the Contractor will accommodate the safe passage of pedestrians and cyclists in accordance with the Manual of Temporary Traffic Control, the Contract Drawings, Staging Plans, and Streets By-Law No. 1481/77 at all times for the duration of the Construction. Unless noted in the Contract, the Accessibility Plan must include a written plan for the following:

How the Contractor will maintain at least one crossing in each direction for each intersection (one north/south crosswalk and one east/west crosswalk).

How the Contractor will maintain access to bus stops within the site.

How the Contractor will maintain access to pedestrian corridors and half signals.

How the Contractor will maintain cycling facilities.

How the Contractor will maintain access to residents and businesses unless otherwise noted in the Contract.

Any required detour signage at adjacent crossings to facilitate sidewalk or active transportation pathway closures.

The Accessibility Plan may also include figures, sketches, or drawings to demonstrate the proposed plan.

The Accessibility Plan shall include written details on how the Contractor intends to review, maintain, and document all items related to the Accessibility Plan on-site during Construction, including, but not limited to:

Signage

Temporary Ramping

Transit Stops

Detour Signage

At minimum, the Contractor shall review the site conditions on a daily basis to ensure that all features related to the Accessibility Plan are in place. The site review is intended to correct deficiencies as a result of unforeseen events such as wind, traffic, or the general public. Deficiencies that are direct result of the Contractors actions must be corrected immediately.

Any changes to the Accessibility Plan must be approved by the Contract Administrator.

Upon request from the Contract Administrator, the Contractor shall provide records demonstrating that the site has been maintained.

SPEC NOTE: Revise as required

Deficiencies as a direct result of actions by the Contractor that are not immediately corrected and/or failure to produce records that demonstrate that the site was maintained in compliance with the Accessibility Plan may result in a pay adjustment via the monthly Progress Payment. The rate of pay adjustment will be as per the following schedule:

First Offence – A warning will be issued and documented in the weekly or bi-weekly site meeting.

Second Offence – A field instruction to immediately correct the site will be issued by the Contract Administrator.

Third and subsequent Offences – A pay reduction will be issued in the amount of $250.00 per instance and per day.

Schedule of Work

Commencement

The Contractor shall not commence any Work until they are in receipt of an award letter from the Award Authority authorizing the commencement of the Work.

SPEC NOTE: Delete any unnecessary between items D15.2(a)(ii) and D15.2(a)(ix).  Add any other submissions or documents required after award but before commencement of the Work on the Site

The Contractor shall not commence any Work on the Site until:

the Contract Administrator has confirmed receipt and approval of:

evidence of authority to carry on business specified in D7;

evidence of the workers compensation coverage specified in C6.17;

the twenty-four (24) hour emergency response phone number specified in D5.2.

the Safe Work Plan specified in D8;

evidence of the insurance specified in D9;

evidence of the contract security specified in D10;

the subcontractor list specified in D11;

the equipment list specified in D12;

the detailed work schedule specified in D13;

the Requirements for Site Accessibility Plan specified in D14; and

the direct deposit application form specified in C12.20.

the Contractor has attended a pre-construction meeting with the Contract Administrator, or the Contract Administrator has waived the requirement for a pre-construction meeting.

^SPEC NOTE: Add any other conditions to be met by the Contractor after award but before commencement of the Work on the Site.

SPEC NOTE: VERSION 1 - Use this version if the Contractor is required to commence the Work on the Site a specified number of days following award of the Contract.  Revise the number of days to suit the contract,

The Contractor shall commence the Work on the Site within seven (7) Working Days of receipt of the award letter.

SPEC NOTE: VERSION 2 - Use this version where the Contractor is not allowed to commence the Work on the Site until a fixed date due to impediments such as weather conditions, inability to access the Site, etc.

    - The Contractor shall not commence the Work on the Site before ^month day, year.

SPEC NOTE: VERSION 3 Use this version where the Contractor is to commence the Work on the Site within a fixed window.  E.g. where the Tender will be awarded before the weather is permissible for construction. The latest start date specified must be at least 7 days later than the award lapse date.  This will ensure that the latest specified commencement date is achievable and will provide the Contractor with seven days to obtain and submit their contract security and other required submissions.

    - The Contractor shall not commence the Work on the Site before ^month day, year, and shall commence the Work on Site no later than ^month day, year, as directed by the Contract Administrator and weather permitting.

SPEC NOTE: Delete D15.4 if none of the Work is being funded by another source (Province) or if the funds from the other source have been secured.  Form B: Prices and D2 must be formatted into two parts.  The Work being funded by the City must be identified as Part 1 and the Work funded by other sources (Province) must be identified as Part 2.

The Contractor shall not commence Part 2 of the Work as described in D2 and identified in Form B: Prices, unless prior to ^ (specify the latest date by which the City expects to receive funds as provided by Streets Project Engineer/Coordinator, typically July 31, yyyy), they have received notification from the Contract Administrator that the City has received notice of sufficient funding from the Province.

SPEC NOTE:  Use D15.5 only if the Contractor is required to complete the Work on the Site by a specified date and the number of days for acceptance of the offer in Form A makes the time period for completion of the Work unreasonable.  E.g. if the Submission Deadline is April 15, the time period for acceptance is 60 Calendar Days, and the Work requires completion by June 17, the Contractor would technically have 3 Calendar Days to complete the project.

The City intends to award this Contract by ^month day, year.

SPEC NOTE: Delete the wording “Critical Stages” from D15.5.1 if not using D20 Critical Stages.

If the actual date of award is later than the intended date, the dates specified for Critical Stages, Substantial Performance, and Total Performance will be adjusted by the difference between the aforementioned intended and actual dates.

Working Days

SPEC NOTE: Use D16 only if the Work Schedule is based on Working Days

Further to C1.1(xx);

The Contract Administrator will determine daily if a Working Day has elapsed and will record their assessment.  On a weekly basis the Contract Administrator will provide the Contractor with a record of the Working Days assessed for the preceding week.  The Contractor shall sign each report signifying that they agree with the Contract Administrator’s determination of the Working Days assessed for the report period.

Work done to restore the Site to a condition suitable for Work, shall not be considered “work” as defined in the definition of a Working Day.

SPEC NOTE: Use D16.1.3 only if the Work Schedule is based on Working Days and there are two or more major classes of Work for which the definition of a Working Day may be applied differently, e.g., the classes of Work might include Work that is weather dependent such as surface work or underground installations by open trench and Work that is not weather dependent such as sewer lining or machine bored tunnelling.

When the Work includes two or more major types of Work that can be performed under different atmospheric conditions, the Contract Administrator shall consider all major types of Work in determining whether the Contractor was able to work in assessing Working Days.

Restricted Work Hours

SPEC NOTE:  Use  D17 only if there is a need to further restrict the Contractor’s hours of operations.  Modify the hours/days as necessary.

Further to 3.10 of CW 1130, the Contractor shall require written permission forty-eight (48) hours in advance from the Contract Administrator for any work to be performed between 2000 hours and 0700 hours, or on Saturdays, Sundays, Statutory Holidays and or Civic Holidays.

SPEC NOTE: Include other restrictions such as known peak hour traffic restrictions in D17.2.

The following work hour restrictions shall also apply:

^;

^.

Work By Others

SPEC NOTE:  Use D18 only if there is work to be done by others that is anticipated to be done concurrently with the Work of the Contract.  List known work to be done by others.  Consider utilities, other Civic Department, etc.  Ex. Manitoba Hydro installing temporary overhead street lighting, Manitoba Hydro Gas Div. lowering gas services or Geomatics doing monument referencing that is not arranged by the Contractor.  Include as much detail as is known, i.e. time frames, commencement/completion dates.  Work by others that must be completed prior to the Work or a portion of the Work of the Contract should be stated in D19.1.4.

Further to C6.26, the Contractor’s attention is directed to the fact that other Contractors, the personnel of Utilities and the staff of the City may be working within the project limit, approach roadway, adjacent roadways or right-of-way. The activities of these agencies may coincide with the Contractors execution of work and it will be the Contractor’s responsibility to cooperate to the fullest extent with other personnel working in the area, and such cooperation is an obligation of the Contractor under the terms of Contract.

Work by others on or near the Site will include but not necessarily be limited to:

^;

^.

Further to D18.1 the Contractor shall cooperate and coordinate all activities with all parties performing required Work by Others. The Contractor must include and accommodate Work by Others identified in D18.2 or additional parties, in their construction schedule as per D13 and accommodate the necessary area on Site required for the Work by Others to complete the Work.

Sequence of Work

SPEC NOTE:  Use D19 if there is a need to control the sequencing/order of the work.

SPEC NOTE:  REGIONAL STREETS VERSION 1:  Sample clauses for work to be done in phases/stages.

Further to C6.1, the sequence of work shall be as follows:

The Work shall be divided into ^ [number of Phases. If no phases specify number of stages and amend as necessary].  Each Phase shall be subdivided into stages.  Stages are further subdivided into major items of work.

Phase I - ^ Description [Describe the limits of Phase I if the Work is divided into Phases.  Repeat for each Phase]

Stage I –	^ Description, e.g., South Curb Lane and Boulevard.  Repeat for each stage. [List the major components of the Work in the order they must occur, e.g.:]

Planing of asphalt and concrete where required;

Concrete pavement slab and joint work and adjustments to pavement structures and appurtenances;

Curb renewals, concrete boulevard works and sidewalk reconstruction;

Joint and crack maintenance;

Placing topsoil and finish grading;

Placing of scratch course of asphalt; and

Laying of sod.

[ and/or state restrictions affecting the order of construction of the major components of the work, e.g.:]

Placing the topsoil and finished grading of all boulevard and median areas shall be completed prior to commencing construction of the asphaltic concrete overlay, including the scratch course.

Stage II – ^ Description, e.g., Final Layer of Asphalt; All Lanes

All asphaltic concrete work shall be performed using a lane-at-a-time method (see E7.1 for minimum requirements of traffic lanes to be left open at various times).

At the end of any day, there shall be no drop-off along any longitudinal joint, excepting the longitudinal joint between the gutter and approaches.

Immediately following the completion of the asphaltic concrete works of Phase I, the Contractor shall clean up the Site and remove all plant, surplus material, waste and debris, other than that left by the City or other Contractors.

Phase II - ^ Description

[Describe the limits of Phase I if the Work is divided into Phases.  Repeat for each Phase]

Stage I –	^ Description, e.g., South Curb Lane and Boulevard.  Repeat for each stage.

[List the major components of the Work in the order they must occur, e.g.:]

^ ;

^.; and

^ .

SPEC NOTE:  REGIONAL STREETS VERSION 2 Without phases/stages, specify curb lane, median lane etc.

    - Further to C6.1, the sequence of work shall be as follows:

Construction activity is to be limited to the ^ [specify lane(s)] of the roadway at a time.  No construction shall commence on the subsequent ^ [specify lane(s)] until all work is completed on the ^ [specify lane(s)].

Initial planing operations are to be limited to the ^ [specify lane(s)] of the roadway.  Planing of the ^ [specify lane(s)] of the roadway ^ (is/are) not be commence until the Contract Administrator has approved the opening of the ^ [specify lane(s)] to traffic.

The Contractor shall delay placing the final lift of asphalt on the ^ [specify lane(s)] of the roadway, so that the final lift of all lanes is placed in one operation.

Construction activity on ^ [location] shall not commence until construction of a ^ [description], by others, is completed.  This Work is expected to be completed by ^ [date].

SPEC NOTE - Be sure that the assumed completion date for work by others is considered when establishing the Contract time. (i.e. enough days are allotted in the Contract time to permit the completion of the portion of the Work that is contingent to the completion of the work by others.)  Should the work at the identified location not be completed by the assumed date indicated, an adjustment to the Contract time and/or price should be considered. A delay to the completion of the prerequisite work should also be discussed in the “Detailed Work Schedule “ Supplemental Condition D13.

SPEC NOTE: RESIDENTIAL STREETS VERSION:  Sample clause for Residential Projects with Multiple locations:  Verify that the time allotted for the Contract is sufficient to complete the Work while complying with the restrictions.

    - Further to C6.1, the sequence of work shall comply with the following:

Providing that the Work on each street is completed in a similar order to the order that the Work was commenced in, the Contractor will be permitted to have a maximum of three (3) streets under construction at any one time.  Completion of a street means that all of the necessary concrete, asphalt including approaches and landscaping Work is completed to the satisfaction of the Contract Administrator.

Where the Contractor utilizes two (2) or more crews that work independently on the same major component of the Work as identified inD2, the Contract Administrator may approve an increase to the maximum number of streets under construction at any time.

Placing the topsoil and finished grading of all boulevard and median areas shall be completed prior to commencing construction of asphaltic concrete overlays, including scratch courses.

Critical Stages

SPEC NOTE: Use D20 only if critical stages of the Work, other than Substantial Performance and/or Total Performance, must be achieved in accordance with a specified schedule.  Specify the critical stages and the schedule required.  If Form L:- Detailed Work Schedule is used, ensure that the descriptions match exactly.  Maybe used for two year contracts, make work required to be completed in the first year a critical stage.  Consider using this clause on Residential Streets contracts to ensure that the Work is kept on schedule. i.e. you could make the first five streets of a ten street contract a critical stage or specify a critical stage completion date for a location(s) that must be completed by an earlier date than the others because of, for example a school opening.  Be careful when specifying a location subject to Provincial funding as a Critical Stage as the commencement of such work is conditional to the Contractor receiving notification in accordance with D15.4.  Critical Stages must be reviewed with and approved by the Streets Project Engineer/Coordinator.

The Contractor shall achieve critical stages of the Work in accordance with the following requirements:

^Specify the critical stages and the schedule required.

^

^

SPEC NOTE: Use D20.2 and D20.3 where it is necessary to clearly specify when a critical stage will be considered completed.

When the Contractor considers the Work associated with ^ [insert critical stage] to be completed, the Contractor shall arrange, attend and assist in the inspection of the Work with the Contract Administrator for purposes of verifying Completion.  Any defects or deficiencies in the Work noted during that inspection shall be remedied by the Contractor at the earliest possible instance and the Contract Administrator notified so that the Work can be re-inspected.

The date on which the ^ [insert critical stage] Work has been accepted by the Contract Administrator as being completed to the requirements of the Contract is the date on which completion of ^ [insert critical stage] has been achieved.

Substantial Performance

SPEC NOTE:  If part of the Work is being funded by another source (Province) and if the funds from the other source have not been secured it is recommended that the contract be Working Day based to allow for the unpredictable date of when funds from the other source will be secured.

SPEC NOTE: VERSION 1 - Use this version to specify the number of Working Days for Substantial Performance.  Insert the number of Working Days allowed.

The Contractor shall achieve Substantial Performance within ^number (^n) consecutive Working Days of the commencement of the Work as specified in D15.

When the Contractor considers the Work to be substantially performed, the Contractor shall arrange, attend and assist in the inspection of the Work with the Contract Administrator for purposes of verifying Substantial Performance.  Any defects or deficiencies in the Work noted during that inspection shall be remedied by the Contractor at the earliest possible instance and the Contract Administrator notified so that the Work can be re-inspected.

The date on which the Work has been certified by the Contract Administrator as being substantially performed to the requirements of the Contract through the issue of a certificate of Substantial Performance is the date on which Substantial Performance has been achieved.

SPEC NOTE: VERSION 2 - Use this version to specify a fixed date for Substantial Performance.  Insert the month, day and year.

    - The Contractor shall achieve Substantial Performance by ^month day, year.

When the Contractor considers the Work to be substantially performed, the Contractor shall arrange, attend and assist in the inspection of the Work with the Contract Administrator for purposes of verifying Substantial Performance.  Any defects or deficiencies in the Work noted during that inspection shall be remedied by the Contractor at the earliest possible instance and the Contract Administrator notified so that the Work can be re-inspected.

The date on which the Work has been certified by the Contract Administrator as being substantially performed to the requirements of the Contract through the issue of a certificate of Substantial Performance is the date on which Substantial Performance has been achieved.

Total Performance

SPEC NOTE:  If part of the Work is being funded by another source (Province) and if the funds from the other source have not been secured it is recommended that the contract be Working Day based to allow for the unpredictable date of when funds from the other source will be secured.

SPEC NOTE: VERSION 1 - Use this version if using version 1 of D21, to specify the number of Working Days for Total Performance.  Insert the number of Working Days allowed.  The number of Working Days must be greater than the number of Working Days specified in D21.1 for Substantial Performance

The Contractor shall achieve Total Performance within ^number (^n) consecutive Working Days of the commencement of the Work as specified in D15.

When the Contractor or the Contract Administrator considers the Work to be totally performed, the Contractor shall arrange, attend and assist in the inspection of the Work with the Contract Administrator for purposes of verifying Total Performance.  Any defects or deficiencies in the Work noted during that inspection shall be remedied by the Contractor at the earliest possible instance and the Contract Administrator notified so that the Work can be re-inspected.

The date on which the Work has been certified by the Contract Administrator as being totally performed to the requirements of the Contract through the issue of a certificate of Total Performance is the date on which Total Performance has been achieved.

SPEC NOTE: VERSION 2 - Use this version if using version 2 of D21, to specify a Fixed Date for Total Performance.  Insert the month, day and year.  The date must be later than the date specified in D21.1 for Substantial Performance.

    - The Contractor shall achieve Total Performance by ^month day, year.

- SPEC NOTE: add the following to D22.1, if required or within ^ days if seasonal inclement weather does not allow permanent restorations to commence immediately after Substantial Performance, whichever comes first.  The Contract Administrator will advise the Contractor when seasonal conditions will allow permanent restorations to begin.  The Contractor will start final restorations no later than 14 (fourteen) Calendar Days after formal notification by the Contract Administrator

When the Contractor or the Contract Administrator considers the Work to be totally performed, the Contractor shall arrange, attend and assist in the inspection of the Work with the Contract Administrator for purposes of verifying Total Performance.  Any defects or deficiencies in the Work noted during that inspection shall be remedied by the Contractor at the earliest possible instance and the Contract Administrator notified so that the Work can be re-inspected.

The date on which the Work has been certified by the Contract Administrator as being totally performed to the requirements of the Contract through the issue of a certificate of Total Performance is the date on which Total Performance has been achieved.

Liquidated Damages

SPEC NOTE:  While it is possible to assess liquidated damages for failure to achieve Substantial and/or Total Performance by a specified date(s), when only using one date, it is recommended that you use Total Performance as this provides additional motivation for the Contractor to complete all of the Work.  Liquidated damages may not be deleted unless approved in writing by the Manager of Purchasing.

SPEC NOTE: VERSION 1 - Use this version if liquidated damages are to be assessed if the Contractor does not achieve Substantial Performance within the number of Working Days or by the fixed date specified in D21.  Insert the amount of Liquidated Damages in terms of dollars per Working Day (if D21 is based on Working Days) or Calendar Day (if D21 is based on a fixed date).  Ensure that a breakdown of the costs is prepared and available to substantiate the specified amount.

If the Contractor fails to achieve Substantial Performance in accordance with the Contract by the day fixed herein for Substantial Performance, the Contractor shall pay the City ^amount dollars ($^n) per ^[Working Day/Calendar Day] for each and every ^[Working Day/Calendar Day] following the day fixed herein for Substantial Performance during which such failure continues.

The amount specified for liquidated damages in D23.1 is based on a genuine pre-estimate of the City's damages in the event that the Contractor does not achieve Substantial Performance by the day fixed herein for same.

The City may reduce any payment to the Contractor by the amount of any liquidated damages assessed.

SPEC NOTE: VERSION 2 - Use this version if liquidated damages are to be assessed if the Contractor does not achieve Total Performance within the number of Working Days or by the fixed date specified in D22.  Insert the amount of Liquidated Damages in terms of dollars per Working Day (if D22 is based on Working Days) or Calendar Day (if D22 is based on a fixed date).  Ensure that a breakdown of the costs is prepared and available to substantiate the specified amount.

    - If the Contractor fails to achieve Total Performance in accordance with the Contract by the day fixed herein for Total Performance, the Contractor shall pay the City ^amount dollars ($^n) per ^[Working Day/Calendar Day] for each and every ^[Working Day/Calendar Day] following the day fixed herein for Total Performance during which such failure continues.

The amount specified for liquidated damages in D23.1 is based on a genuine pre-estimate of the City's damages in the event that the Contractor does not achieve Total Performance by the day fixed herein for same.

The City may reduce any payment to the Contractor by the amount of any liquidated damages assessed.

SPEC NOTE: VERSION 3 - Use this version if liquidated damages are to be assessed if the Contractor does not achieve critical stages, Substantial Performance or Total Performance within the number of Working Days or by the fixed dates specified in D20, D21, and D22 respectively.  Identify critical stages exactly as identified in D20.  Insert the amount of Liquidated Damages for each critical stage, Substantial Performance and Total Performance in terms of dollars per Working Day (if the schedule was based on Working Days) or Calendar Day (if the schedule was based on fixed dates).  Ensure that a breakdown of the costs is prepared and available to substantiate the specified amounts.

    - If the Contractor fails to achieve Critical Stages, Substantial Performance or Total Performance in accordance with the Contract by the days fixed herein for same, the Contractor shall pay the City the following amounts per ^[Working Day/Calendar Day] for each and every ^[Working Day/Calendar Day] following the days fixed herein for same during which such failure continues:

^critical stage - ^amount dollars ($^n);

^critical stage - ^amount dollars ($^n);

^critical stage - ^amount dollars ($^n);

^critical stage - ^amount dollars ($^n);

Substantial Performance - ^amount dollars ($^n);

Total Performance - ^amount dollars ($^n).

The amounts specified for liquidated damages in D23.1 are based on a genuine pre-estimate of the City's losses in the event that the Contractor does not achieve critical stages, Substantial Performance or Total Performance by the days fixed herein for same.

The City may reduce any payment to the Contractor by the amount of any liquidated damages assessed.

Scheduled Maintenance

SPEC NOTE: Use D24 only if scheduled maintenance by the Contractor is required (e.g. sodding, landscape, and reflective crack sealing).  For each item of scheduled maintenance, provide a concise description (typically the specification clause heading) and a specification reference.

The Contractor shall perform the following scheduled maintenance in the manner and within the time periods required by the Specifications:

^description as specified in ^cross reference;

^description as specified in ^cross reference;

^description as specified in ^cross-reference.

Determination of Substantial Performance and Total Performance shall be exclusive of scheduled maintenance identified herein.  All scheduled maintenance shall be completed prior to the expiration of the warranty period.  Where the scheduled maintenance cannot be completed during the warranty period, the warranty period shall be extended for such period of time as it takes the Contractor to complete the scheduled maintenance.

Control of Work

Job Meetings

SPEC NOTE: Use only if regular job meetings are required.  Change “weekly” to any suitable time interval.  Use the phrases, "one representative of the City" and “the City” only where the Contract Administrator is not an employee of the City.  Do not limit the CA to providing 24 hours notice for cancelling or calling an additional meeting.

Regular weekly job meetings will be held at ^[at the Site or specify location].  These meetings shall be attended by a minimum of one representative of the Contract Administrator, ^ [one representative of the City] and one representative of the Contractor.  Each representative shall be a responsible person capable of expressing the position of the Contract Administrator, ^ [the City] and the Contractor respectively on any matter discussed at the meeting including the Work schedule and the need to make any revisions to the Work schedule.  The progress of the Work will be reviewed at each of these meetings.

The Contract Administrator reserves the right to cancel any job meeting or call additional job meetings whenever they deem it necessary.

Prime Contractor – The Workplace Safety and Health Act (Manitoba)

SPEC NOTE: Include D26 when there is a construction project site, the Contractor will be responsible for the project site, and more than one employer or self employed person may be involved in work at the project site at the same time. Otherwise, the City, as owner of the project site, may have the duties of the prime contractor with respect to compliance with WSHA. 	(i.e., if the City is acting as the prime contractor for a project (very rare), do not include D26.)

Further to C6.27, the Contractor shall be the Prime Contractor and shall serve as, and have the duties of the Prime Contractor in accordance with The Workplace Safety and Health Act (Manitoba).

SPEC NOTE: To comply with the WSHA only one Contractor should be designated the Prime Contractor at a site at a time.  Where the possibility exists that 2 or more Contractors (i.e. separate contracts) will occupy the same, or parts of the same construction project site, at the same time, consider dividing the construction project site into logical phases/stages and use milestone dates (e.g., date specified for completion of critical stage(s), Substantial Performance, Total Performance) to specify when each Contractor is the Prime Contractor.  Be sure to coordinate the clause with a similar clause in the other Tender(ies).  Contact the Streets Project Coordinator/Engineer to assist in drafting the clause.

The following is sample clause wording:

(For Other Contract (e.g., Water and Waste Contract) –

For the purpose of determining Prime Contractor, Phase I shall be the Construction Project Site from Maryland to Furby and Phase II shall be the Construction Project Site from Furby to Isabel.

Further to C6.26, the Contractor shall be the Prime Contractor and shall serve as, and have the duties of the Prime Contractor in accordance with The Workplace Safety and Health Act (Manitoba), as follows:

For the Construction Project Site Phase I from commencement of Work until notified in writing by the Contract Administrator that the contractor for Tender #____, (add in description of Public Works Work), commences Work on Phase I, at which time the Tender #_____ contractor will become the Prime Contractor; and

For the Construction Project Site Phase II from commencement of Work until Total Performance of the Contract, as notified in writing by the Contract Administrator.

(For Public Works Contract) -

    - For the purpose of determining Prime Contractor, Phase I shall be the Construction Project Site from Arlington to Furby and Phase II shall be the Construction Project Site from Furby to Isabel.

Further to C6.26, the Contractor shall be the Prime Contractor and shall serve as, and have the duties of the Prime Contractor in accordance with The Workplace Safety and Health Act (Manitoba), as follows:

For the Construction Project Site Phase I upon commencement of the Contract; and

For the Construction Project Site Phase II upon Total Performance of Tender #________, (add in description of Water and Waste Work), as notified in writing by the Contract Administrator.

The Workplace Safety and Health Act (Manitoba) – Qualifications

Further to B13.4, the Contractor/Subcontractor must, throughout the term of the Contract, have a Workplace Safety and Health Program meeting the requirements of The Workplace Safety and Health Act (Manitoba). At any time during the term of the Contract, the City may, at their sole discretion and acting reasonably, require updated proof of compliance, as set out in B13.4.

Payment

Payment

- SPEC NOTE: delete D28 if not including Cash Allowances

    - Further to E3, no payment will be made for Cash Allowances other than as set out in E3.4.

Payment Schedule

SPEC NOTE: Use D29 only if payment is not based on progress estimates pursuant to C12 or where the City is willing to pay for material (e.g., mechanical components, structural components, custom manufactured fabrications) before it is incorporated into the Work (e.g., 50% payment on manufacture and transfer of title to the City, 25% payment on delivery, 25% payment on Total Performance). Any Payment Schedule where funds are paid prior to total completion of Work shall be approved by the Chief Financial Officer PRIOR to the tender/rfp/rfq being issued.

Further to C12, payment shall be in accordance with the following payment schedule:

^SPEC NOTE: Provide payment schedule.

^

Fuel Price Adjustment

- SPEC NOTE: Use only if Fuel Price Adjustment applies to the Contract.

The Contract is subject to a fuel price adjustment which will be calculated monthly based on eligible Work completed utilizing the following mathematical formulas;

where the price of fuel has increased - ((CFI/BFI)-1.15) x Q x FF; and

where the price of fuel has decreased - ((CFI/BFI)-0.85) x Q x FF; where

BFI = base fuel index

CFI = current fuel index

FF = fuel factor

Q = monetary value of Work applied in the calculation.

Eligible Work will be determined in accordance with D30.5.

The base fuel index (BFI) will be the retail price of fuel identified on the Submission Deadline based on latest published “Monthly average retail prices for gasoline and fuel by geography” for Winnipeg, published by Statistics Canada, Table 18-10-0001-01.  The BFI is a blended rate based on 15% regular unleaded gasoline at self-service filling stations and 85% diesel fuel at self-service filling stations.

The current fuel index (CFI) based on the above blended rate will be determined for each monthly progress estimate and applied on the following progress estimate as a change order once rates are published by Statistics Canada.

A Fuel Factor (FF) rate of the monetary value of all eligible Work completed that month based on the Contract unit prices will be used to calculate the assumed apportioned cost of fuel.

Fuel cost adjustments may result in additional payment to the Contractor or credit to the City within the Contract by way of a monthly change order.

The fuel escalation or de-escalation adjustment will not be applied if the CFI is within ±15% of the BFI.

Fuel escalation adjustments will not be considered beyond the Substantial Performance/Critical Stages except where those dates/Working Days are adjusted by change order.   Fuel de-escalation adjustments will apply for Work that extends beyond the dates/Working Days specified for Substantial Performance/Critical Stages.

The Fuel Factor (FF) rates will be set as follows:

- SPEC NOTE: The Fuel Factor rate may be adjusted in consultation with the Manager of Engineering

The Fuel Factor rate shall be set at 2.7% of the monetary value of all Work based on unit prices except for the portions of the Contract identified below;

- SPEC NOTE: Delete (b) if there is no bridge and structure Work in the Contract

The Fuel Factor rate will be set at 1.9% of the monetary value for ^ specify part or item numbers identified on Form B: Prices related to bridges and structures Work.

- SPEC NOTE: Delete (c) if there are no Water and Waste funded watermain or sewer renewals. This would not apply to land drainage repairs etc. within the road renewal portion of the Contract

The Fuel Factor will not apply to ^ specify part or item numbers identified on Form B: Prices related to Water & Waste Work.

Warranty

Warranty

SPEC NOTE: Use D31 only if modifying the standard warranty or warranty period.  Which is stated in C13.2 as one year from Total Performance.  Where a portion of Version 1 and/or Version 2 and/or Version 3 apply, combine the applicable portions into one clause.

SPEC NOTE: VERSION 1 - Use this version only if the warranty period will commence upon the date of Total Performance but the warranty period is not one year.  Insert the appropriate time period, e.g., two (2) years for road reconstructions contracts.

Notwithstanding C13.2, the warranty period shall begin on the date of Total Performance and shall expire two (2) years thereafter unless extended pursuant to C13.2.1 or C13.2.2, in which case it shall expire when provided for thereunder.

SPEC NOTE: VERSION 2 - Use this version only if the warranty period for all of the Work will commence upon the date of Substantial Performance.  Increase the warranty period if necessary. Caution note: commencing the warranty period on Total Performance (in accordance with D31.1(Version 1) may provide additional motivation to the Contractor in getting the Work totally completed, especially when liquidated damages are only conditional to Substantial Performance.

Notwithstanding C13.2, the warranty period shall begin on the date of Substantial Performance and shall expire one (1) year thereafter unless extended pursuant to C13.2.1 or C13.2.2, in which case it shall expire when provided for thereunder.

SPEC NOTE: VERSION 3 - Use this version for multiple location contracts where the warranty period is one year for some locations and two years for others (e.g. pavement reconstructions).

    - Notwithstanding C13.2, the warranty period shall begin on the date of ^ [Substantial / Total] Performance and shall expire one (1) years thereafter for ^ [describe works other than reconstructions], and two (2) years thereafter for pavement reconstruction works, unless extended pursuant to C13.2.1 or C13.2.2, in which case it shall expire when provided for thereunder.

SPEC NOTE:  Use D31.2 with Versions 1 to 3 or independently, only if the warranty period for a portion(s) of the Work will be permitted to commence prior to [Substantial/Total] Performance (as specified in D31.1), where certain conditions are met. Delete reference to prior D31.1 where not applicable (i.e.  there is no change to the basic warranty).  List contract-specific conditions under which the Department will permit the warranty period to commence prior to Substantial/Total Performance.  Example (a) could apply to landscaping.

Notwithstanding C13.2[ or D31.1], the Contract Administrator may permit the warranty period for a portion or portions of the Work to begin prior to the date of ^ [Substantial / Total] Performance if:

a portion of the Work cannot be completed because of unseasonable weather or other conditions reasonably beyond the control of the Contractor but that portion does not prevent the balance of the Work from being put to its intended use.

- SPEC NOTE: List any other contract-specific conditions under which the Department will permit the warranty period to commence prior to Total Performance.

In such case the date specified by the Contract Administrator for the warranty period to begin shall be substituted for the date specified in C13.2 for the warranty period to begin.

^ SPEC NOTE: Specify any special warranties which will apply to specific items of Work (e.g., special manufacturer’s warranties on Material.

VERSION 4 - Use this version only if there is no change to the basic warranty but longer warranties for some items are specified in the Specifications.

    - Notwithstanding C13.2, the warranty period shall begin on the date of Total Performance and shall expire one (1) year thereafter, except where longer warranty periods are specified in the respective Specification sections, unless extended pursuant to C13.2.1 or C13.2.2, in which case it shall expire when provided for thereunder.

For the purpose of contract security, the warranty period shall be one (1) year.

Notwithstanding C13.2, the Contract Administrator may permit the warranty period for a portion or portions of the Work to begin prior to the date of Total Performance if a portion of the Work cannot be completed because of unseasonable weather or other conditions reasonably beyond the control of the Contractor but that portion does not prevent the balance of the Work from being put to its intended use.

In such case, the date specified by the Contract Administrator for the warranty period to begin shall be substituted for the date specified in C13.2 for the warranty period to begin.

Indemnity

  - Indemnity

    - Indemnity shall be as stated in C17.

SPEC NOTE: Use Form J: Subcontractors only if using D11.

Form J: Subcontractor List (See D11) Click or tap here to enter text.

Portion of the Work Name Address

SURFACE WORKS:

Supply of Materials:

Concrete

Asphalt

Base Course & Sub-Base

Sod

Installation/Placement:

Concrete

Asphalt

Base

UNDERGROUND WORKS:

Supply of Materials:

Installation/Placement:

OTHERS:

SPEC NOTE: Use Form K: Equipment List only if using D12.  Identify each key category or type of equipment for which it is necessary to have information to control the Work.  Modify the form to obtain the information required for each category or type of equipment.  Copy sufficient lines for the Contractor to enter information for the required number of pieces.

Form K: Equipment (See D12) Click or tap here to enter text.

- Category/type: SPEC NOTE: Identify category or type of equipment. Make/Model/Year: _____________________________________ Serial No.: ___________________________ Registered owner: _________________________________________________________________________ Make/Model/Year: _____________________________________ Serial No.: ___________________________ Registered owner: _________________________________________________________________________ Make/Model/Year: _____________________________________ Serial No.: ___________________________ Registered owner: _________________________________________________________________________

- Category/type: SPEC NOTE: Identify category or type of equipment. Make/Model/Year: _____________________________________ Serial No.: ___________________________ Registered owner: _________________________________________________________________________ Make/Model/Year: _____________________________________ Serial No.: ___________________________ Registered owner: _________________________________________________________________________ Make/Model/Year: _____________________________________ Serial No.: ___________________________ Registered owner: _________________________________________________________________________

- Category/type: SPEC NOTE: Identify category or type of equipment. Make/Model/Year: _____________________________________ Serial No.: ___________________________ Registered owner: _________________________________________________________________________ Make/Model/Year: _____________________________________ Serial No.: ___________________________ Registered owner: _________________________________________________________________________ Make/Model/Year: _____________________________________ Serial No.: ___________________________ Registered owner: _________________________________________________________________________

- Category/type: SPEC NOTE: Identify category or type of equipment. Make/Model/Year: _____________________________________ Serial No.: ___________________________ Registered owner: _________________________________________________________________________ Make/Model/Year: _____________________________________ Serial No.: ___________________________ Registered owner: _________________________________________________________________________ Make/Model/Year: _____________________________________ Serial No.: ___________________________ Registered owner: _________________________________________________________________________

- Category/type: SPEC NOTE: Identify category or type of equipment. Make/Model/Year: _____________________________________ Serial No.: ___________________________ Registered owner: _________________________________________________________________________ Make/Model/Year: _____________________________________ Serial No.: ___________________________ Registered owner: _________________________________________________________________________ Make/Model/Year: _____________________________________ Serial No.: ___________________________ Registered owner: _________________________________________________________________________

- Category/type: SPEC NOTE: Identify category or type of equipment. Make/Model/Year: _____________________________________ Serial No.: ___________________________ Registered owner: _________________________________________________________________________ Make/Model/Year: _____________________________________ Serial No.: ___________________________ Registered owner: _________________________________________________________________________ Make/Model/Year: _____________________________________ Serial No.: ___________________________ Registered owner: _________________________________________________________________________

SPEC NOTE: Use Form L: Detailed Work Schedule only if using D13. Version 1.  Identify each key item of Work for which it is necessary to know the schedule to control the Work.

SPEC NOTE: VERSION 1A - Use this version where the work schedule is based on Working Days and  D13 does not include the unsecured  funding clauses (D13.2 & D13.3).  Insert time period intervals (^) ending with the total number of Contract Working Days.

| Form L: Detailed Work Schedule (See D13) Click or tap here to enter text. |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| For each item of Work, indicate the cumulative percentage proposed to be completed by the end of each time period until 100% completion is achieved. |  |  |  |  |  |  |
| Items of Work | Time Period in Working Days |  |  |  |  |  |
|  | ^ | ^ | ^ | ^ | ^ | ^ |
| SPEC NOTE: Identify items of Work. |  |  |  |  |  |  |

SPEC NOTE: VERSION 1B  For Residential Projects subject to unsecured (Provincial) funding.  Use this version where the work schedule is based on Working Days  Insert time period intervals (^) ending with the total number of Contract Working Days. One of the intermediate intervals must match the reduced time period for Total Performance of the Work as specified in D13.2 if Part 2 is eliminated.

| Form L: Detailed Work Schedule (See D13) Click or tap here to enter text. |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| For each item of Work, indicate the cumulative percentage proposed to be completed by the end of each time period until 100% completion is achieved. |  |  |  |  |  |  |
| Items of Work | Time Period in Working Days |  |  |  |  |  |
|  | ^ | ^ | ^ | ^ | ^ | ^ |
| PART 1 CITY FUNDED WORK |  |  |  |  |  |  |
| SPEC NOTE: Identify items of Work. |  |  |  |  |  |  |
| PART 2 PROVINCIALLY FUNDED WORK |  |  |  |  |  |  |
| SPEC NOTE: Identify items of Work. |  |  |  |  |  |  |

SPEC NOTE: VERSION 2 - Use this version where the work schedule is based on fixed dates.

| Form L: Detailed Work Schedule (See D13) Click or tap here to enter text. |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| For each item of Work, indicate the proposed date that each cumulative percentage to be completed will be achieved. |  |  |  |  |  |
| Items of Work | Percentage of Work Completed |  |  |  |  |
|  | Start | 25% | 50% | 75% | 100% |
| SPEC NOTE: Identify items of Work. |  |  |  |  |  |

SPECIFICATIONS

General

  - Applicable Specifications and Drawings

    - These Specifications shall apply to the Work.

SPEC NOTE: Include this clause unless none of the Standard Construction Specifications (including the general requirements) apply.

The City of Winnipeg Standard Construction Specifications in their entirety, whether or not specifically listed on Form B: Prices, shall apply to the Work.

The City of Winnipeg Standard Construction Specifications is available on the Information Connection page at The City of Winnipeg, Corporate Finance, Purchasing Division website at http://www.winnipeg.ca/matmgt/Spec/Default.stm

The version in effect three (3) Business Days before the Submission Deadline shall apply.

Further to C2.4(d), Specifications included in the Tender shall govern over The City of Winnipeg Standard Construction Specifications.

SPEC NOTE: All specified proprietary goods/services (mfr, brand, model) must be approved as a single source prior to posting, unless requests for substitutes will be considered in accordance with B7”

A link to the manufacturer’s specifications or a copy of the manufacturer’s specifications must be provided in the Tender document

Bidders are reminded that requests for approval of substitutes as an approved equal or an approved alternative shall be made in accordance with B7. In every instance where a brand name or design specification is used, the City will also consider approved equals and/or approved alternatives in accordance with B7.

SPEC NOTE: Delete E1.4 if there are no drawings.

The following are applicable to the Work:

SPEC NOTE: List all specifications, provided as separate documents, which apply.  Do not list the Standard Construction Specifications (already listed above).  Do not list specifications included within this document.

| Specification No. | Specification Title |
| --- | --- |
|  | Table of Contents All pages, including Table of Contents or Index (if provided) must be listed. A Table of Contents or Index does not require a Specification No. |

SPEC NOTE: Each drawing is to be converted to PDF format as a separate file.  Therefore “Part F Drawings” is no longer applicable.  Do not include a drawing list in the Table of Contents.  Use Purchasing Division’s file naming convention format for the file name (nnnn-yyyy_Drawing_zzzz-Ra.pdf) “nnnn-yyyy” = Tender number,  “zzzz” = the Drawing No. or Drawing name (where no number, e.g., Cover sheet).  For Drawing No. include the prefix, suffix or sheet number as shown on the drawing, e.g., “P-3249-02”.  “Ra” = is the drawing revision level.  Use R0 for drawings with no revisions.  Therefore an example of a drawing file name is “214-2004_Drawing_P-3249-02_R0.pdf”.

Note: All information pertinent to the design (e.g., details, sections) must be placed on drawings that will be as-built to ensure that this information is archived.

| Drawing No. | Drawing Name/Title | Drawing (Original) Sheet Size |
| --- | --- | --- |
|  | Cover Sheet All drawings, including cover sheets/pages must be listed. .Cover sheets do not have to be numbered |  |

Mobilization and Demobilization Payment

SPEC NOTE: Use E2 in combination with the line item in Form B: Prices. If not using E2, delete the line item in the Form B and vice-versa. This clause is meant to cover fixed expenses per contract such as bonding and insurance. Consult with City Project Manager for further direction on its use.

# DESCRIPTION

This Specification shall cover all operations relating to the mobilization and demobilization of the Contractor to the project location(s).

The Work to be done by the Contractor under this Specification shall include the furnishing of all superintendence, overhead, labour, materials, equipment, tools, supplies, and all things necessary for and incidental to the satisfactory performance and completion of all Works as hereinafter specified.

The inclusion of a payment item for the Work under this Specification shall not release or reduce the responsibilities of the Contractor under any other specification in this Contract.

SPEC NOTE: reminder to add Mobilization and Demobilization to your Form B Prices if applicable

# SCOPE OF WORK

Further to C12 of the General Conditions, where Mobilization and Demobilization is included as a bid item, it shall consist of the following, as applicable:

Mobilization shall include, but not be limited to:

All activities and associated costs for transportation of the Contractor's personnel, equipment, and operating supplies to the site, and/or sites, and/or between sites;

Establishment of offices, buildings, other necessary general facilities and equipment parking/staging areas for the Contractor's operations at the site or sites;

Premiums paid for performance and payment bonds including coinsurance and reinsurance agreements as applicable;

General cleanup and housekeeping needed maintain a neat and orderly project site(s);

Other job related items.

Demobilization shall include, but not be limited to:

All activities and costs for transportation of personnel, equipment, and supplies not used in the project from the site, and/or sites, and/or between sites;

Disassembly, removal, and site cleanup and restoration of offices, buildings, and other facilities assembled on the site and/or sites;

Repair of access roads, temporary haul roads, and equipment parking areas leaving the project site in the same or better condition than at the start of the project;

General cleanup and housekeeping needed to restore a neat and orderly project site.

Access to the site, equipment parking, and staging areas are limited to that shown on the drawings or as approved by the Contract Administrator.

# MEASUREMENT AND PAYMENT

The lump-sum price for the Mobilization and Demobilization bid item shall not exceed five percent (5.00%) of the total bid price for the Contract.

Further to B10, B18, C12 and E2.6, should the lump sum price exceed 5% of the Total Bid Price the lump sum price will be reduced to 5% of the Total Bid Price, the Total Bid Price will be determined using the reduced lump sum price and payment will be based on the reduced lump sum price.

Payment for Mobilization:

60% of the lump-sum price will be paid to the contractor for Mobilization on the first Progress Estimate for the Contract.

Payment for Demobilization:

The remaining 40% of the lump-sum price will be paid upon:

Restoration of the site and/or sites to the satisfaction of the Contract Administrator;

Distribution of the Declaration of Total Performance.

SPEC NOTE: delete if Accessibility Site Plan is not applicable

Pay Reduction for Accessibility Plan

The Demobilization payment will be reduced by the number of pay adjustments incurred in accordance with D14 and as determined by the Contract Administrator.

Mobilization and Demobilization will be paid only once (to a maximum of 100%), regardless of the number of times the Contractor mobilizes to the site and/or sites.

SPEC NOTE: delete if Cash Allowance is not applicable or modify as needed

Cash Allowance for Additional Work

Additional Work may be necessitated due to unforeseen circumstances that may arise during the course of the project due to:

      - Additions to the scope of Work by the Contract Administrator, beyond that defined herein.

A cash allowance has been included on Form B: Prices. SPEC NOTE: Reminder to include a Cash Allowance line item on Form B: Prices

The City reserves the right to delete any or all of the Cash Allowance from the Contract if the Work intended to be covered by the Cash Allowance is not required, or if the Works intended are found to be more extensive than the provisional Cash Allowance.

Cost of additional work shall be evaluated by the methods outlined in C7.4, and a Change Order prepared by the Contract Administrator. Cost of the Change Order will be paid on the Progress Estimate and deducted from the Cash Allowance. If the valuation of the authorized work exceeds the Value of the Cash Allowance, the Contract Value will be adjusted by the shortfall.

Additional services and/or Work will not be initiated for:

Reasons of lack of performance or errors in execution.

Scheduling changes initiated by the City, where at least 24 hours’ notice is given prior to the Contractors schedule time to be on Site.

Should it be determined that additional material or services are required, the Contract Administrator shall approve the Work, prior to commencement of the additional Work.

Material Mark-Up Factors:

      - The base cost is to be the wholesale cost of the material, regardless of the Contractor or Subcontractor supplying the material.

      - In general, the party (Contractor or Subcontractor) supplying the material is the party that purchases the material from a supplier who does not perform any work on Site, unless otherwise determined by the Contract Administrator.

      - Where the Contractor is supplying the material, the mark-up on the material is limited to fifteen percent (15%).

      - Where the Contractor’s immediate Subcontractor is supplying the material the total mark-up on the material including all Subcontractors and the Contractor is limited to twenty-five percent (25%)

        - The Subcontractor’s mark-up on the material is limited to fifteen percent (15%);

        - The Contractor’s mark-up on the material is limited to ten percent (10%).

      - A Third-Level Subcontractor is a Subcontractor of a Subcontractor of the Contractor.

        - No Third-Level Subcontractors on this project are approved for additional mark-up.

In the event that a Third-Level Subcontractor is utilized, that is not approved for additional mark-up, the Contractor is responsible for coordinating the split of the maximum approved mark-up between the Contractor and Subcontractors.

Geotechnical Report

SPEC NOTE: Use E2 only if soils investigation information exists.  Disclose and include all geotechnical reports in Appendix ‘A’ following the Specifications.  Should the information deviate significantly from the sample report provided (see Appendix ‘A’) or if the report is large, review with the Streets Project Engineer/Coordinator.

Further to C3.1, the geotechnical report is provided to aid the Contractor’s evaluation of the pavement structure and/or (Delete “pavement structure and/or” for Street Renewals only) existing soil conditions.  The geotechnical report is contained in Appendix ‘A’.

Office Facilities

SPEC NOTE: Use E5 only if the Contractor is required to supply office facilities at the job site and/or at any location where material requiring inspection is being manufactured.  Identify the requirements for each facility.  Use the provided information as necessary.  Requirements should include only basic office space, furnishings and services such as desks, chairs, tables, file cabinets, light, heat, water and telephone.  Requirements should not include consumable supplies, computers, facsimile machines or cellular telephones.

The Contractor shall supply office facilities meeting the following requirements:

The field office shall be for the exclusive use of the Contract Administrator.

The building shall be conveniently located near the site of the Work.

The building shall have a minimum floor area of ^[15, 20, 25] square metres, ^[a height of 2.4m] with ^[a window/two windows for cross ventilation] and a door entrance with a suitable lock.

- Spec Note: Use the maximum number of attendees at site meetings to estimate size.

The building shall be suitable for all weather use.  It shall be equipped with an ^[electric] heater and air conditioner so that the room temperature can be maintained between either 16-18oC or 24-25oC.

The building shall be adequately lighted with ^[fluorescent fixtures and have a minimum of three wall outlets].

The building shall be furnished with ^[(one, two) desk, one drafting table, table 3m X 1.2m, one stool, one four drawer legal size filing cabinet, and a minimum of (5,6,8,12,15) chairs].

A portable toilet shall be located near the field office building.  The toilet shall have a locking door and be for the exclusive use of the Contract Administrator and other personnel from the City.

The field office building and the portable toilet shall be cleaned on a weekly basis immediately prior to each site meeting.  The Contract Administrator may request additional cleaning when they deem it necessary.

The Contractor shall be responsible for all installation and removal costs, all operating costs, and the general maintenance of the office facilities.

The office facilities will be provided from the date of the commencement of the Work to the date of ^[Substantial/Total Performance/the Contract is completed].

SPEC NOTE: Use E5.4 for multiple location contracts where it would be beneficial to have the field office moved once.

On a one time basis, where directed by the Contract Administrator, the Contractor shall relocate the office facilities to a location more convenient for the remaining Work.

Protection Of Existing Trees

The Contractor shall take the following precautionary steps to prevent damage from construction activities to existing boulevard trees within the limits of the construction area:

The Contractor shall not stockpile materials and soil or park vehicles and equipment on boulevards within 2 metres of trees.

Trees identified to be at risk by the Contract Administrator are to be strapped with 25 x 100 x 2400mm wood planks, or suitably protected as approved by the Contract Administrator.

Excavation shall be performed in a manner that minimizes damage to the existing root systems.  Where possible, excavation shall be carried out such that the edge of the excavation shall be a minimum of 1.5 times the diameter (measured in inches), with the outcome read in feet, from the closest edge of the trunk.  Where roots must be cut to facilitate excavation, they shall be pruned neatly at the face of excavation.

Operation of equipment within the dripline of the trees shall be kept to the minimum required to perform the work required.  Equipment shall not be parked, repaired, refuelled; construction materials shall not be stored, and earth materials shall not be stockpiled within the driplines of trees.  The dripline of a tree shall be considered to be the ground surface directly beneath the tips of its outermost branches.  The Contractor shall ensure that the operations do not cause flooding or sediment deposition on areas where trees are located.

Work on-site shall be carried out in such a manner so as to minimize damage to existing tree branches.  Where damage to branches does occur, they shall be neatly pruned.

All damage to existing trees caused by the Contractor’s activities shall be repaired to the requirements and satisfaction of the Contract Administrator and the City Forester or their designate.

No separate measurement or payment will be made for the protection of trees.

Except as required in E6.1(c) and E6.1(e), Elm trees shall not be pruned at any time between April 1 and July 31.

Traffic Control

SPEC NOTE: TRAFFIC CONTROL MUST BE REVIEWED WITH AND APPROVED BY THE STREETS PROJECT ENGINEER/COORDINATOR.

    - Further to 3.6, 3.7 and 3.8 of CW 1130:

      - Where directed by the Contract Administrator, the Contractor shall construct and maintain temporary asphalt ramps to alleviate vertical pavement obstructions such as manholes and planing drop-offs to the satisfaction of the Contract Administrator. Payment shall be in accordance with CW3410.

      - In accordance with the Manual of Temporary Traffic Control on City Streets (MTTC), the Contractor (“Construction Agency” in the Manual) shall be responsible for placing, maintaining and removing the appropriate temporary traffic control devices as specified by the MTTC, the Contract Drawings, Staging Plans and Traffic Management Plans or by the Traffic Management Branch of the City of Winnipeg Public Works Department. The Contractor shall bear all costs associated with the placement of temporary traffic control devices by their own forces or Subcontractor.

      - In addition, the Contractor shall be responsible for supplying, removing, placing and maintaining all regulatory signing including but not limited to:

        - Parking restrictions;

        - Stopping restrictions;

        - Turn restrictions;

        - Diamond lane removal;

        - Full or directional closures on a Regional Street;

        - Traffic routed across a median;

        - Full or directional closure of a non-regional street where there is a requirement for regulatory signs (turn restrictions, bus stop relocations, etc.) to implement the closure.

      - The Contractor shall remove and stockpile any regulatory signage not required during construction such as, but not limited to, parking restrictions, turn restrictions and loading restrictions.

    - Upon request from the Contract Administrator, the Contractor shall provide records demonstrating that the site has been maintained.

    - Further to E7.1(c) and E7.1(d) the Contractor shall make arrangements with the Traffic Services Branch of the City of Winnipeg to reinstall the permanent regulatory signs after the Contract Work is complete. The Contractor shall make arrangements to drop off the stockpiled materials to Traffic Services at 495 Archibald Street.

    - Any changes to the approved Traffic Management Plan must be submitted to the Contract Administrator a minimum of five (5) Working Days prior to the required change for approval.

    - If the Contract Administrator determines that the Contractor is not performing Traffic Control in accordance with this specification, Traffic Services may be engaged to perform the Traffic Control.  In this event the Contractor shall bear costs charged to the project by the Traffic Services Branch of the City of Winnipeg in connection with the required Works.

Traffic Management

SPEC NOTE: Use Traffic Management to establish regulations for the flow of traffic (i.e. lane closures and access, etc.)  Consider drawings to illustrate complex requirements.

TRAFFIC MANAGEMENT MUST BE REVIEWED WITH AND APPROVED BY THE STREETS PROJECT ENGINEER/ COORDINATOR AND THE TRAFFIC MANAGEMENT DIVISION.

SPEC NOTE: VERSION 1 – REGIONAL STREETS - Specify permitted lane closures, requirements and conditions to close/maintain traffic/turning storage lanes, approval processes to restrict private accesses and other traffic restrictions for the various locations/phases of the contract. Add specific permitted lane closures during milling and paving operations including requirements while working through intersecting regional and nonregional streets.

    - Further to 3.7 of CW 1130:

      - Single lane closures on intersecting and/or adjoining Regional Streets shall only be permitted during non-peak periods when required for construction activities when approved by the Traffic Management Branch. Storage/parking of materials, equipment or vehicles is not permitted on Regional Streets at any time unless approved by the Contract Administrator, in consultation with the Traffic Management Branch.

SPEC NOTE:  VERSION 1 - REGIONAL STREETS sample clause from a Reconstruction Project that has a 2 Phase contract and the phases were described in a “Sequence of the Work” clause.  Modify or add clauses as required.

          - Maintain a minimum of one lane of traffic [eastbound] (Phase I) and one lane of traffic [westbound] (Phase II) during their respective construction times, including during paving and milling operations. When no work is being performed on site, non-essential lane closures will not be permitted.

          - Maintain a minimum of two [northbound] lanes of traffic on ^[location] Street during the morning peak period (07:00 – 09:00) and maintain a minimum of two [southbound] lanes of traffic on ^[location] Street during the afternoon peak period (15:00 – 18:00).

            - Further to E8.1.2, in accordance with E7.1(c)(vi), the Traffic Services Branch will be responsible for routing traffic across the median twice per day. Costs associated with any additional requests by the Contractor to modify traffic control during non-peak periods will be the Contractor’s responsibility.

          - No lane closures of westbound traffic will be permitted during Phase I and no lane closures of eastbound traffic will be permitted during Phase II, without the written permission of the Contract Administrator; and

          - Where left turn lanes exist, an additional lane to accommodate the left turn storage lane shall be maintained at all times.

          - [North/South] traffic at ^[location] and ^[location] intersection must be maintained during construction to allow for one lane of traffic in each direction to go straight through and another lane in each direction to turn left.  When no work is being performed in the intersection and providing it is safe for vehicles, north and south lane closures in the intersection will not be permitted.

          - Intersecting local street, median opening and private approach access shall be maintained at all times unless joint/slab repairs or planing/paving operations require temporary closure.  Temporary closures are to be staggered such that consecutive intersections are not closed at the same time. Traffic on intersecting regional/collector streets (list streets) shall be maintained at all times as stated in E8.1.5 unless planing/paving operations require temporary complete closures. Temporary complete closures shall be no longer than 10 minutes during asphalt planing/paving operations and shall be completed during off peak hours.

          - Flag persons may be necessary to maintain the flow of traffic during certain work operations.

          - Should the Contractor be unable to maintain pedestrian or vehicular access to a residence or business, they shall review the planned disruption with the business or residence and the Contract Administrator, and take reasonable measures to minimize the impact.  The Contractor shall provide a minimum of 24 hours notification to the affected residence or business and the Contract Administrator, prior to disruption of access.

          - Pedestrian access must be maintained on the [north] side at all times.  One pedestrian crossing in the [east-west] direction must be maintained at each of the ^[location] and ^[location] intersections at all times.

          - Ambulance/emergency vehicle access must be maintained at all times.

SPEC NOTE: VERSION 2 – RESIDENTIAL STREETS - Specify permitted closures, requirements and conditions to close/maintain traffic lanes, approval processes to restrict private accesses and other traffic restrictions for the various locations of the contract. Specify permitted lane closures on intersecting or adjoining Regional Streets.

Guidelines:

- Where it is non-essential to maintain one lane of traffic on a residential street, the street can be closed i.e. an alternate means of access exists.

- The Contract Administrator should determine when and for how long a street can be closed to traffic, not the Contractor.

- If permissible, identify when the Contractor can close the street.

    - Further to 3.7 of CW 1130:

SPEC NOTE:  Residential Streets sample clauses.  Modify and add clauses as required.

          - The Contractor shall schedule construction activities to meet the following:

            - ^[location] at least one lane for local access traffic shall be maintained along this street during construction.  At least one intersection on adjacent bays shall be open at a time.

            - ^[location] local access and/or bus traffic shall be maintained when possible as determined by the Contract Administrator. The road shall be closed to traffic only with the approval of the Contract Administrator.

            - ^[location] will be closed to through traffic.  Local access and/or bus traffic shall be maintained.  The Contractor shall sign the street “Road Closed – No Exit” in accordance with the Manual of Temporary Traffic Control.

            - ^[location] will be closed to all traffic. The Contractor shall sign the street “Road Closed – No Exit” in accordance with the Manual of Temporary Traffic Control.

            - ^[location] intersecting street and private approach access shall be maintained at all times.

          - Should the Contractor be unable to maintain an existing access to a residence or business, they shall review the planned disruption with the business or residence and the Contract Administrator, and take reasonable measures to minimize the impact.  The Contractor shall provide a minimum of 24 hours notification to the affected residence or business and the Contract Administrator, prior to disruption of access.

          - Pedestrian and ambulance/emergency vehicle access must be maintained at all times.

Refuse and Recycling Collection

SPEC NOTE: Use E9 where access to refuse or recycling collection will be affected.  Contract Administrator to review collection day(s), times and locations with: WWD-SWSConstructionProjects@winnipeg.ca   for each street where collection may be affected.  W&W to provide standard wording for resident notices for affected streets. Ensure notices do not conflict with this clause.  Delete “refuse” or “recycling” if only one service is affected.

While access to refuse and/or recycling collection vehicles is restricted, on collection day(s) the Contractor shall move all of the affected property owners refuse and/or recycling materials to a nearby common area, prior to an established time, in accordance with E9.2 to permit the normal collection vehicles to collect the materials.  Immediately following recycling collection the Contractor shall return recycling receptacles to the addresses marked on the receptacles.  Spec Note: Where individual refuse collection is affected residents are to bag refuse in accordance with W&W guidelines.

Spec Note: Complete for each affected location.

Collection Schedule:

| - ^. Louelda Street, from McLeod Avenue to Tu-pelo Avenue. |  |
| --- | --- |
| - Collection Day(s): | - ^ 3 |
| - Collection Time: | - ^12:00 p.m. (noon) |
| - Common Collection Area: | - ^ Southeast Corner of McLeod Avenue & Louelda Street |
| - ^. |  |
| - Collection Day(s): | - ^ |
| - Collection Time: | - ^ |
| - Common Collection Area: | - ^ |

No measurement or payment will be made for the work associated with this specification.

Pedestrian Safety

SPEC NOTE: fencing protection for identified locations is to be incidental. Where non-identified locations require fencing during the course of the Work payment will be made to the Contractor in accordance with the General Conditions.

During the project, ^[identify criteria/locations], a temporary snow fence shall be installed ^[identify specific locations and/or criteria e.g., shafts].  The Contractor shall be responsible for maintaining the snow fence in a proper working condition.  No measurement for payment shall be made for this work.

Water Obtained From the City

Further to 3.7 of CW 1120, the Contractor shall pay for all costs, including sewer charges, associated with obtaining water from the City in accordance with the Waterworks and Sewer By-laws.

Surface Restorations

SPEC NOTE: Include this clause when there is a possibility that Total Performance will not be achieved in the year the Contract is commenced.  Note: When the Contract Administrator directs the Contractor to commence work that cannot be completed due to reasons beyond the Contractor’s control, it would be reasonable to provide compensation for both temporary repairs and maintenance.

Further to 3.3 of CW 1130, when Total Performance is not achieved in the year the Contract is commenced, the Contractor shall temporarily repair any Work commenced and not completed to the satisfaction of the Contract Administrator.  The Contractor shall maintain the temporary repairs in a safe condition as determined by the Contract Administrator until permanent repairs are completed.   The Contractor shall bear all costs associated with temporary repairs and their maintenance.

Infrastructure Signs

SPEC NOTE: This clause to be suitably modified for other project information signs.

The Contractor shall obtain infrastructure signs from the Traffic Services Sign Shop at 495 Archibald Street.  The Contractor shall mount each sign securely to a rigid backing material approved by the Contract Administrator.  The Contractor shall fasten each sign to a suitable support and erect and maintain one sign at each street as directed by the Contract Administrator.  When the Contract Administrator considers the Work on the street complete, the Contractor shall remove and dispose of the signs and supports.   No measurement for payment will be made for performing all operations herein described and all other items incidental to the work described

Patching of Existing Pavement

DESCRIPTION

General

This specification covers patching of existing concrete pavement in preparation for an asphalt overlay.

Referenced Standard Construction Specifications

CW 3110 – Sub-Grade, Sub-Base and Base Course Construction.

CW 3130 – Supply and Installation of Geotextile Fabrics.

CW 3410 – Asphaltic Concrete Pavement Works.

MATERIALS

Crushed Sub-Base Material

Crushed Sub-base material will have a maximum aggregate size of 50 millimetre and be supplied in accordance with CW 3110.

Geotextile Fabric

Geotextile fabric will be supplied in accordance with Section 2 of CW 3130.

Asphalt Material

Asphalt material will be Type 1A and will be supplied in accordance with Sections 5 and 6 of CW 3410.

CONSTRUCTION METHODS

General

Remove existing concrete pavement to a minimum width of 1.5 metres at locations as shown on the Drawings or as directed by the Contract Administrator in accordance with Section 3.1 of Specification CW 3110.

Excavate to a depth of 350 millimetres below the top of the existing pavement.

Compact existing sub-grade to a minimum of 95% Standard Proctor Density.

Place geotextile fabric in accordance with Specification CW 3130.

Place and compact crushed sub-base material in accordance with CW 3110 to a 300 millimetres compacted depth.  Compact to a minimum of 100% Standard Proctor Density.

Place and compact asphalt material to a 50 millimetres compacted depth matching the top of the existing concrete pavement.  Compact to an average of 95% percent of the 75 Blow Marshall Density of the paving mixture with no individual test being less than 90% percent.

Each layer must be levelled and accepted by the Contract Administrator before the succeeding layer may be placed.

Additional excavation and placement of sub-base material beyond the identified pavement structure will be completed in accordance with CW 3110 as directed by the Contract Administrator.

MEASUREMENT AND PAYMENT

Pavement Patching

Pavement patching will be measured on an area basis and paid for at the Contract Unit Price per square metre for “Pavement Patching”.  The area to be paid for will be the total number of square metres of pavement patched in accordance with this specification, accepted and measured by the Contract Administrator.

Supply and Installation of Pavement Repair Fabric

DESCRIPTION

General

This specification covers the supply and installation of pavement repair fabric.

Referenced Standard Construction

CW 3130 – Supply and Installation of Geotextile Fabrics.

MATERIALS

Storage and Handling

Store and handle material in accordance with Section 2 of CW 3130.

Pavement Repair Fabric

Pavement repair fabric will be Glas Grid Road Reinforcement Mesh - Style 8501.

CONSTRUCTION METHODS

General

Install pavement repair fabric at random locations as directed by the Contract Administrator.

The extent of the placement limits and quantities required will be determined by the Contract Administrator and provided 48 hours prior to the placement of asphalt.

Proceed with installation upon completion and acceptance of the asphalt levelling course.

Install fabric in accordance with the manufacturer’s specifications and recommendations.

Only construction equipment required to place the final asphalt surface course will be allowed to travel on the exposed fabric.

Replace damaged or improperly placed fabric.

Ensure temperature of the asphalt material does not exceed the melting point of the fabric.

MEASUREMENT AND PAYMENT

Pavement Repair Fabric

The supply and installation of the pavement repair fabric will be measured on an area basis and paid for at the Contract Unit Price per square metre for “Pavement Repair Fabric”.  The area to be paid for will be the total number of square metres of pavement repair fabric supplied and installed in accordance with this specification, accepted and measured by the Contract Administrator.

Partial Depth Patching of Existing Joints

# DESCRIPTION

General

This specification covers the Partial Depth Patching of existing concrete pavement joints.

Referenced Standard Construction Specifications

CW 3230 – Full-Depth Patching of Existing Slabs and Joints

CW 3410 – Asphalt Concrete Pavement Works

# MATERIALS

Asphalt Materials

Asphalt material will be Type 1A supplied in accordance with Sections 5 and 6 of CW 3410.

Tack Coat

Tack Coat will be undiluted SS-1 emulsified asphalt.

# CONSTRUCTION METHODS

Planing of Joints

Plane existing joints designated by the Contract Administrator to a minimum depth of 50 mm and a maximum of depth 90 mm to remove ravelled or deteriorated concrete.  Width of joint to be planed will vary with depth.

Should the depth of joint deterioration exceed the maximum indicated, as determined by the Contract Administrator, the entire joint shall be renewed and paid for in accordance with CW 3230 as a full depth joint repair.  Planing completed shall be paid for in accordance with Section E16.7 of this specification.

Dispose of material in accordance with Section 3.4 of CW 1130.

Placement of Asphalt Material

Prior to placement of asphalt material, the planed joint shall be swept or blow clean of any loose material.

Apply Tack Coat uniformly on the entire surface of the planed joint.  The application rate shall not exceed 0.23 litres per square metre.  The planed joint shall be dry prior to applying the tack coat.

Place and compact asphalt material in accordance with Section 9.3 of CW 3410 to the satisfaction of the Contract Administrator.  The finished elevation of the patch shall be flush with surrounding pavement surface.

Compact the asphalt material to an average 95% of the 75 blow Marshall Density of the paving mixture with no individual test being less than 90 %.

Ensure that no traffic is allowed to travel over the patched area until the asphalt has cooled to atmospheric temperature.

# MEASUREMENT AND PAYMENT

Partial Depth Planing of Existing Joints

Partial Depth Planing of Existing Joints will be measured on an area basis and paid for at the Contract Unit Price per square metre for “Partial Depth Planing of Existing Joints”.  The area to be paid for will be the total number of square metres of joints planed in accordance with this specification, accepted and measured by the Contract Administrator.

Asphalt Patching of Partial Depth Joints

Asphalt Patching of Partial Depth Joints will be measured on an area basis and paid for at the Contract Unit Price per square metre for “Asphalt Patching of Partial Depth Joints”. The area to be paid for will be the total number of square metres of joints patched in accordance with this specification, accepted, and measured by the Contract Administrator.

Salt Tolerant Grass Seeding

Description

Further to CW 3520 and CW3540, this specification shall cover sub-grade preparation and the supply and placement of Salt Tolerant Grass Seed.

Materials

Salt Tolerant Grass Seed

Salt Tolerant Grass Seed for regional and collector boulevards, medians and interchange areas shall be a mixture composed of:

Seventy percent (70%) Fults or Nuttals Alkaligrass (Puccinellia spp.), twenty percent (20%) Audubon or Aberdeen Creeping Red Fescue and ten percent (10%) Perennial Ryegrass.

equipment

Scarification equipment shall be suitable for the area being scarified, shall be capable of scarifying the sub-grade to the specified depth and shall be accepted by the Contract Administrator.  For confined areas a toothed bucket may be acceptable.  For larger areas tilling equipment may be required.

Construction Methods

Preparation of Existing Grade

Prior to placing topsoil, in areas to be seeded greater in width than 600mm, prepare the existing sub-grade by scarifying to a minimum depth of 75mm and to a maximum depth of 100mm to the satisfaction of the Contract Administrator.

Scarification shall consist of breaking up and loosening the sub-grade. No scarification shall occur within the edge of a tree canopy (or drip line).

Salt Tolerant Grass Seeding

Salt Tolerant Grass Seed shall be sown at a rate of 2.2 kilograms per 100 square meters.

Measurement and Payment

Supply, placement and maintenance of Salt Tolerant Grass Seed will be paid for at the Contract Unit Price per square metre for "Salt Tolerant Grass Seeding", measured as specified herein, which price shall be payment in full for supplying all materials and for completing all operations herein described and all other items incidental to the work included in this Specification.  Payment for Salt Tolerant Grass Seeding shall be in accordance with the following:

Sixty five (65%) percent of quantity following supply and placement.

Remaining thirty five (35%) percent of quantity following termination of the Maintenance Period.

Portland Cement Concrete Sidewalk With Block Outs For Indicator Surfaces

SPEC NOTE: Drawings with details showing the dimensions of the block outs with a cross-section(s) showing the profile and thickness of the sidewalk and/or sidewalk with monolithic curb must be included.  Include E spec for “Interlocking Paving Stones for Indicator Surface Bands”

# DESCRIPTION

This specification shall supplement CW 3325-R5 “Portland Cement Concrete Sidewalks”.

# CONSTRUCTION METHODS

Add the following to section 9 :

As shown on the drawings and as directed by the Contract Administrator, construct sidewalk with block outs and/or monolithic curb and sidewalk with block outs, to allow for the installation of indicator surfaces.

Verify dimensions of paving stones (indicator surface) prior to construction of the block-outs. Gaps between paving stones and concrete pavement shall not exceed five (5) millimetres.

Concrete curbs for monolithic curb and sidewalk with block outs shall be constructed in accordance with CW 3240.

# MEASUREMENT AND PAYMENT

Add the following to section 12 :

Construction of concrete sidewalks with block outs for indicator surfaces will be measured on surface area basis.  The surface area to be paid for shall be the number of square metres constructed in accordance with this specification and accepted by the Contract Administrator, as computed by measurements made by the Contract Administrator.

# Basis of payment

Add the following to section 13 :

Construction of concrete sidewalks with block outs for indicator surfaces will be paid for at the Contract Unit Price per square meter for the “Items of Work” listed here below, measured as specified herein, which price shall be payment in full for supplying all materials and for performing all operations herein described and all other items incidental to the work included in this specification.

Items of Work:

100 mm Sidewalk with Block Outs

150 mm Sidewalk with Block Outs

Monolithic Curb and 100 mm Sidewalk with Block Outs*

Monolithic Curb and 150 mm Sidewalk with Block Outs*

- * - reveal height and type

Concrete thickness greater than the specified sidewalk thickness as a result of shaping the base material to accommodate the block outs is incidental to the listed Items of Work.

Paving Stones for Indicator Surfaces

SPEC NOTE: Drawings with details showing the layout and pattern of the paving stones in the sidewalk block outs must be included.

# DESCRIPTION

This specification shall supplement CW 3330-R5 “Installation of Interlocking Paving Stones”

# Materials

Add the following to section 5 :

SPEC NOTE: VERSION 1 - Use this version if the paving stones for indicator surface bands will be specified on the drawings (good option if variation in the tender)

Paving Stones for indicator surfaces shall be as shown on the drawings.

SPEC NOTE: VERSION 2 - Use this version if the paving stones for indicator surface bands will NOT be specified on the drawings (good option if only one type specified for entire tender)

Paving Stones for indicator surfaces shall be :

SPEC NOTE:  - Typical pavers previously specified listed below, delete or add as required. Note the Endicott and Yankee Hill Brick pavers are identified in the Exchange District Design Guidelines.

Barkman Concrete paving stones -

Charcoal Holland Paver (60mm X 210 mm X 210 mm)

https://www.barkmanconcrete.com/

Endicott Clay Paver(92mm X 57mm X 194mm)- Dark Ironspot

https://endicott.com/

Yankee Hill Brick (92mm X 57mm X 194mm)- Dark Ironspot

http://yankeehillbrick.com/

# CONSTRUCTION METHODS

Add the following to section 9.2 “Preparation of Sub-grade, Sub-base and Sand-base” :

Preparation of Sand-Base for Paving Stones in Sidewalk Block Outs.

Place a 15mm layer of bedding sand in the blocked out sidewalk areas. SPEC NOTE: the bedding sand and paver dimensions must be considered in the block out dimensions on the drawing.

The bedding sand shall be spread and levelled so that the paving stones when installed are 5 mm higher than the finished grade.

No more sand shall be spread than can be covered in with paving stone on the same day.

The bedding sand shall not be compacted or disturbed prior to laying the paving stones.

Add the following to section 9.3 “Installation of Paving Stones” :

For indicator surface paving stones, commence installation of paving stones against the long edge of the block out to obtain the straightest possible course of installation.

# MEASUREMENT AND PAYMENT

Add the following to section 12 :

Supply and Installation of Paving Stones for Indicator Surfaces

Paving stones for indicator surfaces will be measured on surface area basis.  The surface area to be paid for shall be the number of square metres constructed in accordance with this specification and accepted by the Contract Administrator, as computed by measurements made by the contract Administrator.

# Basis of payment

Add the following to section 13 :

The supply and installation of paving stones for indicator surfaces will be paid for at the Contract Unit Price per square meter for “Paving Stone Indicator Surface”, measured as specified herein, which price shall be payment in full for supplying all materials and for performing all operations herein described and all other items incidental to the work included in this specification.

Concrete thickness greater than the specified sidewalk thickness as a result of shaping the base material to accommodate the block outs is incidental to the listed Items of Work.

Supply and Install Watermain and Water Service Insulation

# Description

Notwithstanding 3.12 of CW 2110, this specification covers the supply and installation of insulation in roadway excavations over watermains and water services.

Referenced Standard Construction Specifications

CW 2030 – Excavation Bedding and Backfill

CW 3110 – Sub –grade, Sub-base and Base Course Construction

Referenced Standard Details

SD-018 - Watermain and Water Service Insulation

# Materials

Acceptable insulation is:

Extruded Polystyrene rigid foam insulation – Type 4, 4” in thickness.

- DOW - Roofmate or Highload 40

- Owen’s Corning - Foamular 350 or Foamular 400.

- 2” X 48” X 96”, 2” X 24” X 96”, 4” X 24” X 96”

Sand Bedding:

In accordance with CW 2030

# Construction Methods

Prior to the installation of any sub-base material or geotextile material, locate all existing water services.    Further to SD-018, where directed by the Contract Administrator, excavate the sub-grade to allow the top of the insulation to be installed flush with the surrounding sub-grade.  Install the insulation on a level surface centered over the located watermain or water service for the full width of the roadway excavation.  Install sand bedding if required to level the surface. Stockpile and dispose of excavated material in accordance with CW 3110.

Thickness of insulation is 100 mm ( 4”).  If using 50 mm ( 2”) panels 2 layers are required.  Total width of insulation to be as directed by the Contract Administrator.  Place sufficient full width panels to meet or exceed the specified width.

Place insulation panels adjacent to each other over the specified area with no gaps between panels and less than 15mm of elevation difference along the adjoined edges. Where 2” thick panels are being used, offset the top layer to prevent the panel joints from aligning with the joints in the lower layer.

Use full panels of insulation where possible. Where necessary cut insulation panels to obtain coverage to specified lengths.  Insulation pieces shall be a minimum of dimension of 300 mm in width or length.

Take appropriate measures to ensure panels are not displaced when installing geotextiles and during backfilling operations.

# MEASUREMENT AND PAYMENT

Watermain and Water Service Insulation shall be measured on an area basis and paid for at the Contract Unit Price per square metre of “Watermain and Water Service Insulation”. The area to be paid for shall be the total square meters of watermain and water service insulation supplied and installed in accordance with this specification, accepted and measured by the Contract Administrator.

Excavation of the roadway subgrade in accordance with E20.6 will not be measured for payment and will be included in the payment for “Watermain and Water Service Insulation”.

Mix Design Proportion

General

Further to CW 3310-R18, this Specification covers the mix proportion for all concrete types related to, the construction of Portland Cement Concrete pavements, curbs, gutters, private approaches, bull-noses, median slabs, medians, safety medians and boulevard splash strips, sidewalks and other related concrete works.

Referenced Standard Construction Specifications

CW 3310 – Portland Cement Concrete Pavement Works

Mix Design

Further to CW 3310-R18 Table CW 3310.5, the minimum cementitious contents shall be as follows:

- Type 1 - 380 kg/m3

- Type 2 - 360 kg/m3

- Type 3 - 380 kg/m3

- Type 4 - 380 kg/m3

- Type 5 - 340 kg/m3

- Type 6 - 360 kg/m3

Requirements

The Mix Design Statements for all the concrete shall be submitted to the City of Winnipeg, Research and Standards Engineer for approval.

Quality Assurance

The Contract Administrator shall ensure the frequency and number of quality assurance tests in accordance with CW 3310.

^(Special Specification Title)